## Project Data
Project | Task | Dependencies | a | m | b
Project 1 | A |  | 5 | 6 | 8
Project 1 | B |  | 1 | 3 | 4
Project 1 | C |  | 2 | 4 | 5
Project 1 | D | A | 4 | 5 | 6
Project 1 | E | A | 7 | 8 | 10
Project 1 | F | A | 8 | 9 | 13
Project 1 | G | D | 5 | 9 | 19
Project 1 | H | D | 3 | 4 | 5
Project 1 | I | B, G | 4 | 8 | 10
Project 1 | J | B, G | 5 | 6 | 8
Project 1 | K | C, E | 9 | 10 | 15
Project 1 | L | C, E | 4 | 6 | 8
Project 1 | M | F, H, I, K | 3 | 4 | 5
Project 2 | A |  | 1 | 3 | 4
Project 2 | B |  | 5 | 7 | 8
Project 2 | C |  | 6 | 7 | 9
Project 2 | D | A | 1 | 7 | 9
Project 2 | E | A | 3 | 7 | 9
Project 2 | F | A | 7 | 8 | 10
Project 2 | G | B, E | 10 | 15 | 20
Project 2 | H | B, E | 12 | 13 | 14
Project 2 | I | C | 10 | 12 | 15
Project 2 | J | C | 8 | 10 | 12
Project 2 | K | F, I | 7 | 8 | 11
Project 2 | L | F, I | 2 | 4 | 8
Project 2 | M | D, K | 5 | 6 | 7

## Project-1 triangular(a,b,m)
Project 1 | [8 empty] | Trial | Project Duration | Success
Task | Immediate Ancestor | a | m | b | Start Time | U(0,1) | Duration | Finsih Time |  | 39.3452 | 0
A |  | 5 | 6 | 8 | 0 | 0.089162 | 5.5172 | 5.5172 | 1 | 39.3452 | 0
B |  | 1 | 3 | 4 | 0 | 0.85132 | 3.3321 | 3.3321 | 2 | 39.3452 | 0
C |  | 2 | 4 | 5 | 0 | 0.96683 | 4.6846 | 4.6846 | 3 | 39.3452 | 0
D | A | 4 | 5 | 6 | 5.5172 | 0.01686 | 4.1836 | 9.7008 | 4 | 39.3452 | 0
E | A | 7 | 8 | 10 | 5.5172 | 0.27637 | 7.9106 | 13.4277 | 5 | 39.3452 | 0
F | A | 8 | 9 | 13 | 5.5172 | 0.31817 | 9.3072 | 14.8244 | 6 | 39.3452 | 0
G | D | 5 | 9 | 19 | 9.7008 | 0.99864 | 18.564 | 28.2648 | 7 | 39.3452 | 0
H | D | 3 | 4 | 5 | 9.7008 | 0.74228 | 4.2821 | 13.9829 | 8 | 39.3452 | 0
I | B,G | 4 | 8 | 10 | 28.2648 | 0.57972 | 7.7301 | 35.9949 | 9 | 39.3452 | 0
J | B,G | 5 | 6 | 8 | 28.2648 | 0.40426 | 6.1094 | 34.3742 | 10 | 39.3452 | 0
K | C,E | 9 | 10 | 15 | 13.4277 | 0.36967 | 10.6514 | 24.0792 | 11 | 39.3452 | 0
L | C,E | 4 | 6 | 8 | 13.4277 | 0.3462 | 5.6642 | 19.092 | 12 | 39.3452 | 0
M | F,H,I,K | 3 | 4 | 5 | 35.9949 | 0.061357 | 3.3503 | 39.3452 | 13 | 39.3452 | 0
N | J,L,M | 0 | 0 | 0 | 39.3452 | 0.53868 | 0 | 39.3452 | 14 | 39.3452 | 0
[9 empty] | 15 | 39.3452 | 0
[9 empty] | 16 | 39.3452 | 0
[9 empty] | 17 | 39.3452 | 0
Deadline | Average Project Duration | Average Success R. | [6 empty] | 18 | 39.3452 | 0
32 | 39.3452 | 0 | [6 empty] | 19 | 39.3452 | 0
[9 empty] | 20 | 39.3452 | 0
[9 empty] | 21 | 39.3452 | 0
[9 empty] | 22 | 39.3452 | 0
[9 empty] | 23 | 39.3452 | 0
[9 empty] | 24 | 39.3452 | 0
[9 empty] | 25 | 39.3452 | 0
[9 empty] | 26 | 39.3452 | 0
[9 empty] | 27 | 39.3452 | 0
[9 empty] | 28 | 39.3452 | 0
[9 empty] | 29 | 39.3452 | 0
[9 empty] | 30 | 39.3452 | 0
[9 empty] | 31 | 39.3452 | 0
[9 empty] | 32 | 39.3452 | 0
[9 empty] | 33 | 39.3452 | 0
[9 empty] | 34 | 39.3452 | 0
[9 empty] | 35 | 39.3452 | 0
[9 empty] | 36 | 39.3452 | 0
[9 empty] | 37 | 39.3452 | 0
[9 empty] | 38 | 39.3452 | 0
[9 empty] | 39 | 39.3452 | 0
[9 empty] | 40 | 39.3452 | 0
[9 empty] | 41 | 39.3452 | 0
[9 empty] | 42 | 39.3452 | 0
[9 empty] | 43 | 39.3452 | 0
[9 empty] | 44 | 39.3452 | 0
[9 empty] | 45 | 39.3452 | 0
[9 empty] | 46 | 39.3452 | 0
[9 empty] | 47 | 39.3452 | 0
[9 empty] | 48 | 39.3452 | 0
[9 empty] | 49 | 39.3452 | 0
[9 empty] | 50 | 39.3452 | 0
[9 empty] | 51 | 39.3452 | 0
[9 empty] | 52 | 39.3452 | 0
[9 empty] | 53 | 39.3452 | 0
[9 empty] | 54 | 39.3452 | 0
[9 empty] | 55 | 39.3452 | 0
[9 empty] | 56 | 39.3452 | 0
[9 empty] | 57 | 39.3452 | 0
[9 empty] | 58 | 39.3452 | 0
[9 empty] | 59 | 39.3452 | 0
[9 empty] | 60 | 39.3452 | 0
[9 empty] | 61 | 39.3452 | 0
[9 empty] | 62 | 39.3452 | 0
[9 empty] | 63 | 39.3452 | 0
[9 empty] | 64 | 39.3452 | 0
[9 empty] | 65 | 39.3452 | 0
[9 empty] | 66 | 39.3452 | 0
[9 empty] | 67 | 39.3452 | 0
[9 empty] | 68 | 39.3452 | 0
[9 empty] | 69 | 39.3452 | 0
[9 empty] | 70 | 39.3452 | 0
[9 empty] | 71 | 39.3452 | 0
[9 empty] | 72 | 39.3452 | 0
[9 empty] | 73 | 39.3452 | 0
[9 empty] | 74 | 39.3452 | 0
[9 empty] | 75 | 39.3452 | 0
[9 empty] | 76 | 39.3452 | 0
[9 empty] | 77 | 39.3452 | 0
[9 empty] | 78 | 39.3452 | 0
[9 empty] | 79 | 39.3452 | 0
[9 empty] | 80 | 39.3452 | 0
[9 empty] | 81 | 39.3452 | 0
[9 empty] | 82 | 39.3452 | 0
[9 empty] | 83 | 39.3452 | 0
[9 empty] | 84 | 39.3452 | 0
[9 empty] | 85 | 39.3452 | 0
[9 empty] | 86 | 39.3452 | 0
[9 empty] | 87 | 39.3452 | 0
[9 empty] | 88 | 39.3452 | 0
[9 empty] | 89 | 39.3452 | 0
[9 empty] | 90 | 39.3452 | 0
[9 empty] | 91 | 39.3452 | 0
[9 empty] | 92 | 39.3452 | 0
[9 empty] | 93 | 39.3452 | 0
[9 empty] | 94 | 39.3452 | 0
[9 empty] | 95 | 39.3452 | 0
[9 empty] | 96 | 39.3452 | 0
[9 empty] | 97 | 39.3452 | 0
[9 empty] | 98 | 39.3452 | 0
[9 empty] | 99 | 39.3452 | 0
[9 empty] | 100 | 39.3452 | 0
[9 empty] | 101 | 39.3452 | 0
[9 empty] | 102 | 39.3452 | 0
[9 empty] | 103 | 39.3452 | 0
[9 empty] | 104 | 39.3452 | 0
[9 empty] | 105 | 39.3452 | 0
[9 empty] | 106 | 39.3452 | 0
[9 empty] | 107 | 39.3452 | 0
[9 empty] | 108 | 39.3452 | 0
[9 empty] | 109 | 39.3452 | 0
[9 empty] | 110 | 39.3452 | 0
[9 empty] | 111 | 39.3452 | 0
[9 empty] | 112 | 39.3452 | 0
[9 empty] | 113 | 39.3452 | 0
[9 empty] | 114 | 39.3452 | 0
[9 empty] | 115 | 39.3452 | 0
[9 empty] | 116 | 39.3452 | 0
[9 empty] | 117 | 39.3452 | 0
[9 empty] | 118 | 39.3452 | 0
[9 empty] | 119 | 39.3452 | 0
[9 empty] | 120 | 39.3452 | 0
[9 empty] | 121 | 39.3452 | 0
[9 empty] | 122 | 39.3452 | 0
[9 empty] | 123 | 39.3452 | 0
[9 empty] | 124 | 39.3452 | 0
[9 empty] | 125 | 39.3452 | 0
[9 empty] | 126 | 39.3452 | 0
[9 empty] | 127 | 39.3452 | 0
[9 empty] | 128 | 39.3452 | 0
[9 empty] | 129 | 39.3452 | 0
[9 empty] | 130 | 39.3452 | 0
[9 empty] | 131 | 39.3452 | 0
[9 empty] | 132 | 39.3452 | 0
[9 empty] | 133 | 39.3452 | 0
[9 empty] | 134 | 39.3452 | 0
[9 empty] | 135 | 39.3452 | 0
[9 empty] | 136 | 39.3452 | 0
[9 empty] | 137 | 39.3452 | 0
[9 empty] | 138 | 39.3452 | 0
[9 empty] | 139 | 39.3452 | 0
[9 empty] | 140 | 39.3452 | 0
[9 empty] | 141 | 39.3452 | 0
[9 empty] | 142 | 39.3452 | 0
[9 empty] | 143 | 39.3452 | 0
[9 empty] | 144 | 39.3452 | 0
[9 empty] | 145 | 39.3452 | 0
[9 empty] | 146 | 39.3452 | 0
[9 empty] | 147 | 39.3452 | 0
[9 empty] | 148 | 39.3452 | 0
[9 empty] | 149 | 39.3452 | 0
[9 empty] | 150 | 39.3452 | 0
[9 empty] | 151 | 39.3452 | 0
[9 empty] | 152 | 39.3452 | 0
[9 empty] | 153 | 39.3452 | 0
[9 empty] | 154 | 39.3452 | 0
[9 empty] | 155 | 39.3452 | 0
[9 empty] | 156 | 39.3452 | 0
[9 empty] | 157 | 39.3452 | 0
[9 empty] | 158 | 39.3452 | 0
[9 empty] | 159 | 39.3452 | 0
[9 empty] | 160 | 39.3452 | 0
[9 empty] | 161 | 39.3452 | 0
[9 empty] | 162 | 39.3452 | 0
[9 empty] | 163 | 39.3452 | 0
[9 empty] | 164 | 39.3452 | 0
[9 empty] | 165 | 39.3452 | 0
[9 empty] | 166 | 39.3452 | 0
[9 empty] | 167 | 39.3452 | 0
[9 empty] | 168 | 39.3452 | 0
[9 empty] | 169 | 39.3452 | 0
[9 empty] | 170 | 39.3452 | 0
[9 empty] | 171 | 39.3452 | 0
[9 empty] | 172 | 39.3452 | 0
[9 empty] | 173 | 39.3452 | 0
[9 empty] | 174 | 39.3452 | 0
[9 empty] | 175 | 39.3452 | 0
[9 empty] | 176 | 39.3452 | 0
[9 empty] | 177 | 39.3452 | 0
[9 empty] | 178 | 39.3452 | 0
[9 empty] | 179 | 39.3452 | 0
[9 empty] | 180 | 39.3452 | 0
[9 empty] | 181 | 39.3452 | 0
[9 empty] | 182 | 39.3452 | 0
[9 empty] | 183 | 39.3452 | 0
[9 empty] | 184 | 39.3452 | 0
[9 empty] | 185 | 39.3452 | 0
[9 empty] | 186 | 39.3452 | 0
[9 empty] | 187 | 39.3452 | 0
[9 empty] | 188 | 39.3452 | 0
[9 empty] | 189 | 39.3452 | 0
[9 empty] | 190 | 39.3452 | 0
[9 empty] | 191 | 39.3452 | 0
[9 empty] | 192 | 39.3452 | 0
[9 empty] | 193 | 39.3452 | 0
[9 empty] | 194 | 39.3452 | 0
[9 empty] | 195 | 39.3452 | 0
[9 empty] | 196 | 39.3452 | 0
[9 empty] | 197 | 39.3452 | 0
[9 empty] | 198 | 39.3452 | 0
[9 empty] | 199 | 39.3452 | 0
[9 empty] | 200 | 39.3452 | 0
[9 empty] | 201 | 39.3452 | 0
[9 empty] | 202 | 39.3452 | 0
[9 empty] | 203 | 39.3452 | 0
[9 empty] | 204 | 39.3452 | 0
[9 empty] | 205 | 39.3452 | 0
[9 empty] | 206 | 39.3452 | 0
[9 empty] | 207 | 39.3452 | 0
[9 empty] | 208 | 39.3452 | 0
[9 empty] | 209 | 39.3452 | 0
[9 empty] | 210 | 39.3452 | 0
[9 empty] | 211 | 39.3452 | 0
[9 empty] | 212 | 39.3452 | 0
[9 empty] | 213 | 39.3452 | 0
[9 empty] | 214 | 39.3452 | 0
[9 empty] | 215 | 39.3452 | 0
[9 empty] | 216 | 39.3452 | 0
[9 empty] | 217 | 39.3452 | 0
[9 empty] | 218 | 39.3452 | 0
[9 empty] | 219 | 39.3452 | 0
[9 empty] | 220 | 39.3452 | 0
[9 empty] | 221 | 39.3452 | 0
[9 empty] | 222 | 39.3452 | 0
[9 empty] | 223 | 39.3452 | 0
[9 empty] | 224 | 39.3452 | 0
[9 empty] | 225 | 39.3452 | 0
[9 empty] | 226 | 39.3452 | 0
[9 empty] | 227 | 39.3452 | 0
[9 empty] | 228 | 39.3452 | 0
[9 empty] | 229 | 39.3452 | 0
[9 empty] | 230 | 39.3452 | 0
[9 empty] | 231 | 39.3452 | 0
[9 empty] | 232 | 39.3452 | 0
[9 empty] | 233 | 39.3452 | 0
[9 empty] | 234 | 39.3452 | 0
[9 empty] | 235 | 39.3452 | 0
[9 empty] | 236 | 39.3452 | 0
[9 empty] | 237 | 39.3452 | 0
[9 empty] | 238 | 39.3452 | 0
[9 empty] | 239 | 39.3452 | 0
[9 empty] | 240 | 39.3452 | 0
[9 empty] | 241 | 39.3452 | 0
[9 empty] | 242 | 39.3452 | 0
[9 empty] | 243 | 39.3452 | 0
[9 empty] | 244 | 39.3452 | 0
[9 empty] | 245 | 39.3452 | 0
[9 empty] | 246 | 39.3452 | 0
[9 empty] | 247 | 39.3452 | 0
[9 empty] | 248 | 39.3452 | 0
[9 empty] | 249 | 39.3452 | 0
[9 empty] | 250 | 39.3452 | 0
[9 empty] | 251 | 39.3452 | 0
[9 empty] | 252 | 39.3452 | 0
[9 empty] | 253 | 39.3452 | 0
[9 empty] | 254 | 39.3452 | 0
[9 empty] | 255 | 39.3452 | 0
[9 empty] | 256 | 39.3452 | 0
[9 empty] | 257 | 39.3452 | 0
[9 empty] | 258 | 39.3452 | 0
[9 empty] | 259 | 39.3452 | 0
[9 empty] | 260 | 39.3452 | 0
[9 empty] | 261 | 39.3452 | 0
[9 empty] | 262 | 39.3452 | 0
[9 empty] | 263 | 39.3452 | 0
[9 empty] | 264 | 39.3452 | 0
[9 empty] | 265 | 39.3452 | 0
[9 empty] | 266 | 39.3452 | 0
[9 empty] | 267 | 39.3452 | 0
[9 empty] | 268 | 39.3452 | 0
[9 empty] | 269 | 39.3452 | 0
[9 empty] | 270 | 39.3452 | 0
[9 empty] | 271 | 39.3452 | 0
[9 empty] | 272 | 39.3452 | 0
[9 empty] | 273 | 39.3452 | 0
[9 empty] | 274 | 39.3452 | 0
[9 empty] | 275 | 39.3452 | 0
[9 empty] | 276 | 39.3452 | 0
[9 empty] | 277 | 39.3452 | 0
[9 empty] | 278 | 39.3452 | 0
[9 empty] | 279 | 39.3452 | 0
[9 empty] | 280 | 39.3452 | 0
[9 empty] | 281 | 39.3452 | 0
[9 empty] | 282 | 39.3452 | 0
[9 empty] | 283 | 39.3452 | 0
[9 empty] | 284 | 39.3452 | 0
[9 empty] | 285 | 39.3452 | 0
[9 empty] | 286 | 39.3452 | 0
[9 empty] | 287 | 39.3452 | 0
[9 empty] | 288 | 39.3452 | 0
[9 empty] | 289 | 39.3452 | 0
[9 empty] | 290 | 39.3452 | 0
[9 empty] | 291 | 39.3452 | 0
[9 empty] | 292 | 39.3452 | 0
[9 empty] | 293 | 39.3452 | 0
[9 empty] | 294 | 39.3452 | 0
[9 empty] | 295 | 39.3452 | 0
[9 empty] | 296 | 39.3452 | 0
[9 empty] | 297 | 39.3452 | 0
[9 empty] | 298 | 39.3452 | 0
[9 empty] | 299 | 39.3452 | 0
[9 empty] | 300 | 39.3452 | 0
[9 empty] | 301 | 39.3452 | 0
[9 empty] | 302 | 39.3452 | 0
[9 empty] | 303 | 39.3452 | 0
[9 empty] | 304 | 39.3452 | 0
[9 empty] | 305 | 39.3452 | 0
[9 empty] | 306 | 39.3452 | 0
[9 empty] | 307 | 39.3452 | 0
[9 empty] | 308 | 39.3452 | 0
[9 empty] | 309 | 39.3452 | 0
[9 empty] | 310 | 39.3452 | 0
[9 empty] | 311 | 39.3452 | 0
[9 empty] | 312 | 39.3452 | 0
[9 empty] | 313 | 39.3452 | 0
[9 empty] | 314 | 39.3452 | 0
[9 empty] | 315 | 39.3452 | 0
[9 empty] | 316 | 39.3452 | 0
[9 empty] | 317 | 39.3452 | 0
[9 empty] | 318 | 39.3452 | 0
[9 empty] | 319 | 39.3452 | 0
[9 empty] | 320 | 39.3452 | 0
[9 empty] | 321 | 39.3452 | 0
[9 empty] | 322 | 39.3452 | 0
[9 empty] | 323 | 39.3452 | 0
[9 empty] | 324 | 39.3452 | 0
[9 empty] | 325 | 39.3452 | 0
[9 empty] | 326 | 39.3452 | 0
[9 empty] | 327 | 39.3452 | 0
[9 empty] | 328 | 39.3452 | 0
[9 empty] | 329 | 39.3452 | 0
[9 empty] | 330 | 39.3452 | 0
[9 empty] | 331 | 39.3452 | 0
[9 empty] | 332 | 39.3452 | 0
[9 empty] | 333 | 39.3452 | 0
[9 empty] | 334 | 39.3452 | 0
[9 empty] | 335 | 39.3452 | 0
[9 empty] | 336 | 39.3452 | 0
[9 empty] | 337 | 39.3452 | 0
[9 empty] | 338 | 39.3452 | 0
[9 empty] | 339 | 39.3452 | 0
[9 empty] | 340 | 39.3452 | 0
[9 empty] | 341 | 39.3452 | 0
[9 empty] | 342 | 39.3452 | 0
[9 empty] | 343 | 39.3452 | 0
[9 empty] | 344 | 39.3452 | 0
[9 empty] | 345 | 39.3452 | 0
[9 empty] | 346 | 39.3452 | 0
[9 empty] | 347 | 39.3452 | 0
[9 empty] | 348 | 39.3452 | 0
[9 empty] | 349 | 39.3452 | 0
[9 empty] | 350 | 39.3452 | 0
[9 empty] | 351 | 39.3452 | 0
[9 empty] | 352 | 39.3452 | 0
[9 empty] | 353 | 39.3452 | 0
[9 empty] | 354 | 39.3452 | 0
[9 empty] | 355 | 39.3452 | 0
[9 empty] | 356 | 39.3452 | 0
[9 empty] | 357 | 39.3452 | 0
[9 empty] | 358 | 39.3452 | 0
[9 empty] | 359 | 39.3452 | 0
[9 empty] | 360 | 39.3452 | 0
[9 empty] | 361 | 39.3452 | 0
[9 empty] | 362 | 39.3452 | 0
[9 empty] | 363 | 39.3452 | 0
[9 empty] | 364 | 39.3452 | 0
[9 empty] | 365 | 39.3452 | 0
[9 empty] | 366 | 39.3452 | 0
[9 empty] | 367 | 39.3452 | 0
[9 empty] | 368 | 39.3452 | 0
[9 empty] | 369 | 39.3452 | 0
[9 empty] | 370 | 39.3452 | 0
[9 empty] | 371 | 39.3452 | 0
[9 empty] | 372 | 39.3452 | 0
[9 empty] | 373 | 39.3452 | 0
[9 empty] | 374 | 39.3452 | 0
[9 empty] | 375 | 39.3452 | 0
[9 empty] | 376 | 39.3452 | 0
[9 empty] | 377 | 39.3452 | 0
[9 empty] | 378 | 39.3452 | 0
[9 empty] | 379 | 39.3452 | 0
[9 empty] | 380 | 39.3452 | 0
[9 empty] | 381 | 39.3452 | 0
[9 empty] | 382 | 39.3452 | 0
[9 empty] | 383 | 39.3452 | 0
[9 empty] | 384 | 39.3452 | 0
[9 empty] | 385 | 39.3452 | 0
[9 empty] | 386 | 39.3452 | 0
[9 empty] | 387 | 39.3452 | 0
[9 empty] | 388 | 39.3452 | 0
[9 empty] | 389 | 39.3452 | 0
[9 empty] | 390 | 39.3452 | 0
[9 empty] | 391 | 39.3452 | 0
[9 empty] | 392 | 39.3452 | 0
[9 empty] | 393 | 39.3452 | 0
[9 empty] | 394 | 39.3452 | 0
[9 empty] | 395 | 39.3452 | 0
[9 empty] | 396 | 39.3452 | 0
[9 empty] | 397 | 39.3452 | 0
[9 empty] | 398 | 39.3452 | 0
[9 empty] | 399 | 39.3452 | 0
[9 empty] | 400 | 39.3452 | 0
[9 empty] | 401 | 39.3452 | 0
[9 empty] | 402 | 39.3452 | 0
[9 empty] | 403 | 39.3452 | 0
[9 empty] | 404 | 39.3452 | 0
[9 empty] | 405 | 39.3452 | 0
[9 empty] | 406 | 39.3452 | 0
[9 empty] | 407 | 39.3452 | 0
[9 empty] | 408 | 39.3452 | 0
[9 empty] | 409 | 39.3452 | 0
[9 empty] | 410 | 39.3452 | 0
[9 empty] | 411 | 39.3452 | 0
[9 empty] | 412 | 39.3452 | 0
[9 empty] | 413 | 39.3452 | 0
[9 empty] | 414 | 39.3452 | 0
[9 empty] | 415 | 39.3452 | 0
[9 empty] | 416 | 39.3452 | 0
[9 empty] | 417 | 39.3452 | 0
[9 empty] | 418 | 39.3452 | 0
[9 empty] | 419 | 39.3452 | 0
[9 empty] | 420 | 39.3452 | 0
[9 empty] | 421 | 39.3452 | 0
[9 empty] | 422 | 39.3452 | 0
[9 empty] | 423 | 39.3452 | 0
[9 empty] | 424 | 39.3452 | 0
[9 empty] | 425 | 39.3452 | 0
[9 empty] | 426 | 39.3452 | 0
[9 empty] | 427 | 39.3452 | 0
[9 empty] | 428 | 39.3452 | 0
[9 empty] | 429 | 39.3452 | 0
[9 empty] | 430 | 39.3452 | 0
[9 empty] | 431 | 39.3452 | 0
[9 empty] | 432 | 39.3452 | 0
[9 empty] | 433 | 39.3452 | 0
[9 empty] | 434 | 39.3452 | 0
[9 empty] | 435 | 39.3452 | 0
[9 empty] | 436 | 39.3452 | 0
[9 empty] | 437 | 39.3452 | 0
[9 empty] | 438 | 39.3452 | 0
[9 empty] | 439 | 39.3452 | 0
[9 empty] | 440 | 39.3452 | 0
[9 empty] | 441 | 39.3452 | 0
[9 empty] | 442 | 39.3452 | 0
[9 empty] | 443 | 39.3452 | 0
[9 empty] | 444 | 39.3452 | 0
[9 empty] | 445 | 39.3452 | 0
[9 empty] | 446 | 39.3452 | 0
[9 empty] | 447 | 39.3452 | 0
[9 empty] | 448 | 39.3452 | 0
[9 empty] | 449 | 39.3452 | 0
[9 empty] | 450 | 39.3452 | 0
[9 empty] | 451 | 39.3452 | 0
[9 empty] | 452 | 39.3452 | 0
[9 empty] | 453 | 39.3452 | 0
[9 empty] | 454 | 39.3452 | 0
[9 empty] | 455 | 39.3452 | 0
[9 empty] | 456 | 39.3452 | 0
[9 empty] | 457 | 39.3452 | 0
[9 empty] | 458 | 39.3452 | 0
[9 empty] | 459 | 39.3452 | 0
[9 empty] | 460 | 39.3452 | 0
[9 empty] | 461 | 39.3452 | 0
[9 empty] | 462 | 39.3452 | 0
[9 empty] | 463 | 39.3452 | 0
[9 empty] | 464 | 39.3452 | 0
[9 empty] | 465 | 39.3452 | 0
[9 empty] | 466 | 39.3452 | 0
[9 empty] | 467 | 39.3452 | 0
[9 empty] | 468 | 39.3452 | 0
[9 empty] | 469 | 39.3452 | 0
[9 empty] | 470 | 39.3452 | 0
[9 empty] | 471 | 39.3452 | 0
[9 empty] | 472 | 39.3452 | 0
[9 empty] | 473 | 39.3452 | 0
[9 empty] | 474 | 39.3452 | 0
[9 empty] | 475 | 39.3452 | 0
[9 empty] | 476 | 39.3452 | 0
[9 empty] | 477 | 39.3452 | 0
[9 empty] | 478 | 39.3452 | 0
[9 empty] | 479 | 39.3452 | 0
[9 empty] | 480 | 39.3452 | 0
[9 empty] | 481 | 39.3452 | 0
[9 empty] | 482 | 39.3452 | 0
[9 empty] | 483 | 39.3452 | 0
[9 empty] | 484 | 39.3452 | 0
[9 empty] | 485 | 39.3452 | 0
[9 empty] | 486 | 39.3452 | 0
[9 empty] | 487 | 39.3452 | 0
[9 empty] | 488 | 39.3452 | 0
[9 empty] | 489 | 39.3452 | 0
[9 empty] | 490 | 39.3452 | 0
[9 empty] | 491 | 39.3452 | 0
[9 empty] | 492 | 39.3452 | 0
[9 empty] | 493 | 39.3452 | 0
[9 empty] | 494 | 39.3452 | 0
[9 empty] | 495 | 39.3452 | 0
[9 empty] | 496 | 39.3452 | 0
[9 empty] | 497 | 39.3452 | 0
[9 empty] | 498 | 39.3452 | 0
[9 empty] | 499 | 39.3452 | 0
[9 empty] | 500 | 39.3452 | 0
[9 empty] | 501 | 39.3452 | 0
[9 empty] | 502 | 39.3452 | 0
[9 empty] | 503 | 39.3452 | 0
[9 empty] | 504 | 39.3452 | 0
[9 empty] | 505 | 39.3452 | 0
[9 empty] | 506 | 39.3452 | 0
[9 empty] | 507 | 39.3452 | 0
[9 empty] | 508 | 39.3452 | 0
[9 empty] | 509 | 39.3452 | 0
[9 empty] | 510 | 39.3452 | 0
[9 empty] | 511 | 39.3452 | 0
[9 empty] | 512 | 39.3452 | 0
[9 empty] | 513 | 39.3452 | 0
[9 empty] | 514 | 39.3452 | 0
[9 empty] | 515 | 39.3452 | 0
[9 empty] | 516 | 39.3452 | 0
[9 empty] | 517 | 39.3452 | 0
[9 empty] | 518 | 39.3452 | 0
[9 empty] | 519 | 39.3452 | 0
[9 empty] | 520 | 39.3452 | 0
[9 empty] | 521 | 39.3452 | 0
[9 empty] | 522 | 39.3452 | 0
[9 empty] | 523 | 39.3452 | 0
[9 empty] | 524 | 39.3452 | 0
[9 empty] | 525 | 39.3452 | 0
[9 empty] | 526 | 39.3452 | 0
[9 empty] | 527 | 39.3452 | 0
[9 empty] | 528 | 39.3452 | 0
[9 empty] | 529 | 39.3452 | 0
[9 empty] | 530 | 39.3452 | 0
[9 empty] | 531 | 39.3452 | 0
[9 empty] | 532 | 39.3452 | 0
[9 empty] | 533 | 39.3452 | 0
[9 empty] | 534 | 39.3452 | 0
[9 empty] | 535 | 39.3452 | 0
[9 empty] | 536 | 39.3452 | 0
[9 empty] | 537 | 39.3452 | 0
[9 empty] | 538 | 39.3452 | 0
[9 empty] | 539 | 39.3452 | 0
[9 empty] | 540 | 39.3452 | 0
[9 empty] | 541 | 39.3452 | 0
[9 empty] | 542 | 39.3452 | 0
[9 empty] | 543 | 39.3452 | 0
[9 empty] | 544 | 39.3452 | 0
[9 empty] | 545 | 39.3452 | 0
[9 empty] | 546 | 39.3452 | 0
[9 empty] | 547 | 39.3452 | 0
[9 empty] | 548 | 39.3452 | 0
[9 empty] | 549 | 39.3452 | 0
[9 empty] | 550 | 39.3452 | 0
[9 empty] | 551 | 39.3452 | 0
[9 empty] | 552 | 39.3452 | 0
[9 empty] | 553 | 39.3452 | 0
[9 empty] | 554 | 39.3452 | 0
[9 empty] | 555 | 39.3452 | 0
[9 empty] | 556 | 39.3452 | 0
[9 empty] | 557 | 39.3452 | 0
[9 empty] | 558 | 39.3452 | 0
[9 empty] | 559 | 39.3452 | 0
[9 empty] | 560 | 39.3452 | 0
[9 empty] | 561 | 39.3452 | 0
[9 empty] | 562 | 39.3452 | 0
[9 empty] | 563 | 39.3452 | 0
[9 empty] | 564 | 39.3452 | 0
[9 empty] | 565 | 39.3452 | 0
[9 empty] | 566 | 39.3452 | 0
[9 empty] | 567 | 39.3452 | 0
[9 empty] | 568 | 39.3452 | 0
[9 empty] | 569 | 39.3452 | 0
[9 empty] | 570 | 39.3452 | 0
[9 empty] | 571 | 39.3452 | 0
[9 empty] | 572 | 39.3452 | 0
[9 empty] | 573 | 39.3452 | 0
[9 empty] | 574 | 39.3452 | 0
[9 empty] | 575 | 39.3452 | 0
[9 empty] | 576 | 39.3452 | 0
[9 empty] | 577 | 39.3452 | 0
[9 empty] | 578 | 39.3452 | 0
[9 empty] | 579 | 39.3452 | 0
[9 empty] | 580 | 39.3452 | 0
[9 empty] | 581 | 39.3452 | 0
[9 empty] | 582 | 39.3452 | 0
[9 empty] | 583 | 39.3452 | 0
[9 empty] | 584 | 39.3452 | 0
[9 empty] | 585 | 39.3452 | 0
[9 empty] | 586 | 39.3452 | 0
[9 empty] | 587 | 39.3452 | 0
[9 empty] | 588 | 39.3452 | 0
[9 empty] | 589 | 39.3452 | 0
[9 empty] | 590 | 39.3452 | 0
[9 empty] | 591 | 39.3452 | 0
[9 empty] | 592 | 39.3452 | 0
[9 empty] | 593 | 39.3452 | 0
[9 empty] | 594 | 39.3452 | 0
[9 empty] | 595 | 39.3452 | 0
[9 empty] | 596 | 39.3452 | 0
[9 empty] | 597 | 39.3452 | 0
[9 empty] | 598 | 39.3452 | 0
[9 empty] | 599 | 39.3452 | 0
[9 empty] | 600 | 39.3452 | 0
[9 empty] | 601 | 39.3452 | 0
[9 empty] | 602 | 39.3452 | 0
[9 empty] | 603 | 39.3452 | 0
[9 empty] | 604 | 39.3452 | 0
[9 empty] | 605 | 39.3452 | 0
[9 empty] | 606 | 39.3452 | 0
[9 empty] | 607 | 39.3452 | 0
[9 empty] | 608 | 39.3452 | 0
[9 empty] | 609 | 39.3452 | 0
[9 empty] | 610 | 39.3452 | 0
[9 empty] | 611 | 39.3452 | 0
[9 empty] | 612 | 39.3452 | 0
[9 empty] | 613 | 39.3452 | 0
[9 empty] | 614 | 39.3452 | 0
[9 empty] | 615 | 39.3452 | 0
[9 empty] | 616 | 39.3452 | 0
[9 empty] | 617 | 39.3452 | 0
[9 empty] | 618 | 39.3452 | 0
[9 empty] | 619 | 39.3452 | 0
[9 empty] | 620 | 39.3452 | 0
[9 empty] | 621 | 39.3452 | 0
[9 empty] | 622 | 39.3452 | 0
[9 empty] | 623 | 39.3452 | 0
[9 empty] | 624 | 39.3452 | 0
[9 empty] | 625 | 39.3452 | 0
[9 empty] | 626 | 39.3452 | 0
[9 empty] | 627 | 39.3452 | 0
[9 empty] | 628 | 39.3452 | 0
[9 empty] | 629 | 39.3452 | 0
[9 empty] | 630 | 39.3452 | 0
[9 empty] | 631 | 39.3452 | 0
[9 empty] | 632 | 39.3452 | 0
[9 empty] | 633 | 39.3452 | 0
[9 empty] | 634 | 39.3452 | 0
[9 empty] | 635 | 39.3452 | 0
[9 empty] | 636 | 39.3452 | 0
[9 empty] | 637 | 39.3452 | 0
[9 empty] | 638 | 39.3452 | 0
[9 empty] | 639 | 39.3452 | 0
[9 empty] | 640 | 39.3452 | 0
[9 empty] | 641 | 39.3452 | 0
[9 empty] | 642 | 39.3452 | 0
[9 empty] | 643 | 39.3452 | 0
[9 empty] | 644 | 39.3452 | 0
[9 empty] | 645 | 39.3452 | 0
[9 empty] | 646 | 39.3452 | 0
[9 empty] | 647 | 39.3452 | 0
[9 empty] | 648 | 39.3452 | 0
[9 empty] | 649 | 39.3452 | 0
[9 empty] | 650 | 39.3452 | 0
[9 empty] | 651 | 39.3452 | 0
[9 empty] | 652 | 39.3452 | 0
[9 empty] | 653 | 39.3452 | 0
[9 empty] | 654 | 39.3452 | 0
[9 empty] | 655 | 39.3452 | 0
[9 empty] | 656 | 39.3452 | 0
[9 empty] | 657 | 39.3452 | 0
[9 empty] | 658 | 39.3452 | 0
[9 empty] | 659 | 39.3452 | 0
[9 empty] | 660 | 39.3452 | 0
[9 empty] | 661 | 39.3452 | 0
[9 empty] | 662 | 39.3452 | 0
[9 empty] | 663 | 39.3452 | 0
[9 empty] | 664 | 39.3452 | 0
[9 empty] | 665 | 39.3452 | 0
[9 empty] | 666 | 39.3452 | 0
[9 empty] | 667 | 39.3452 | 0
[9 empty] | 668 | 39.3452 | 0
[9 empty] | 669 | 39.3452 | 0
[9 empty] | 670 | 39.3452 | 0
[9 empty] | 671 | 39.3452 | 0
[9 empty] | 672 | 39.3452 | 0
[9 empty] | 673 | 39.3452 | 0
[9 empty] | 674 | 39.3452 | 0
[9 empty] | 675 | 39.3452 | 0
[9 empty] | 676 | 39.3452 | 0
[9 empty] | 677 | 39.3452 | 0
[9 empty] | 678 | 39.3452 | 0
[9 empty] | 679 | 39.3452 | 0
[9 empty] | 680 | 39.3452 | 0
[9 empty] | 681 | 39.3452 | 0
[9 empty] | 682 | 39.3452 | 0
[9 empty] | 683 | 39.3452 | 0
[9 empty] | 684 | 39.3452 | 0
[9 empty] | 685 | 39.3452 | 0
[9 empty] | 686 | 39.3452 | 0
[9 empty] | 687 | 39.3452 | 0
[9 empty] | 688 | 39.3452 | 0
[9 empty] | 689 | 39.3452 | 0
[9 empty] | 690 | 39.3452 | 0
[9 empty] | 691 | 39.3452 | 0
[9 empty] | 692 | 39.3452 | 0
[9 empty] | 693 | 39.3452 | 0
[9 empty] | 694 | 39.3452 | 0
[9 empty] | 695 | 39.3452 | 0
[9 empty] | 696 | 39.3452 | 0
[9 empty] | 697 | 39.3452 | 0
[9 empty] | 698 | 39.3452 | 0
[9 empty] | 699 | 39.3452 | 0
[9 empty] | 700 | 39.3452 | 0
[9 empty] | 701 | 39.3452 | 0
[9 empty] | 702 | 39.3452 | 0
[9 empty] | 703 | 39.3452 | 0
[9 empty] | 704 | 39.3452 | 0
[9 empty] | 705 | 39.3452 | 0
[9 empty] | 706 | 39.3452 | 0
[9 empty] | 707 | 39.3452 | 0
[9 empty] | 708 | 39.3452 | 0
[9 empty] | 709 | 39.3452 | 0
[9 empty] | 710 | 39.3452 | 0
[9 empty] | 711 | 39.3452 | 0
[9 empty] | 712 | 39.3452 | 0
[9 empty] | 713 | 39.3452 | 0
[9 empty] | 714 | 39.3452 | 0
[9 empty] | 715 | 39.3452 | 0
[9 empty] | 716 | 39.3452 | 0
[9 empty] | 717 | 39.3452 | 0
[9 empty] | 718 | 39.3452 | 0
[9 empty] | 719 | 39.3452 | 0
[9 empty] | 720 | 39.3452 | 0
[9 empty] | 721 | 39.3452 | 0
[9 empty] | 722 | 39.3452 | 0
[9 empty] | 723 | 39.3452 | 0
[9 empty] | 724 | 39.3452 | 0
[9 empty] | 725 | 39.3452 | 0
[9 empty] | 726 | 39.3452 | 0
[9 empty] | 727 | 39.3452 | 0
[9 empty] | 728 | 39.3452 | 0
[9 empty] | 729 | 39.3452 | 0
[9 empty] | 730 | 39.3452 | 0
[9 empty] | 731 | 39.3452 | 0
[9 empty] | 732 | 39.3452 | 0
[9 empty] | 733 | 39.3452 | 0
[9 empty] | 734 | 39.3452 | 0
[9 empty] | 735 | 39.3452 | 0
[9 empty] | 736 | 39.3452 | 0
[9 empty] | 737 | 39.3452 | 0
[9 empty] | 738 | 39.3452 | 0
[9 empty] | 739 | 39.3452 | 0
[9 empty] | 740 | 39.3452 | 0
[9 empty] | 741 | 39.3452 | 0
[9 empty] | 742 | 39.3452 | 0
[9 empty] | 743 | 39.3452 | 0
[9 empty] | 744 | 39.3452 | 0
[9 empty] | 745 | 39.3452 | 0
[9 empty] | 746 | 39.3452 | 0
[9 empty] | 747 | 39.3452 | 0
[9 empty] | 748 | 39.3452 | 0
[9 empty] | 749 | 39.3452 | 0
[9 empty] | 750 | 39.3452 | 0
[9 empty] | 751 | 39.3452 | 0
[9 empty] | 752 | 39.3452 | 0
[9 empty] | 753 | 39.3452 | 0
[9 empty] | 754 | 39.3452 | 0
[9 empty] | 755 | 39.3452 | 0
[9 empty] | 756 | 39.3452 | 0
[9 empty] | 757 | 39.3452 | 0
[9 empty] | 758 | 39.3452 | 0
[9 empty] | 759 | 39.3452 | 0
[9 empty] | 760 | 39.3452 | 0
[9 empty] | 761 | 39.3452 | 0
[9 empty] | 762 | 39.3452 | 0
[9 empty] | 763 | 39.3452 | 0
[9 empty] | 764 | 39.3452 | 0
[9 empty] | 765 | 39.3452 | 0
[9 empty] | 766 | 39.3452 | 0
[9 empty] | 767 | 39.3452 | 0
[9 empty] | 768 | 39.3452 | 0
[9 empty] | 769 | 39.3452 | 0
[9 empty] | 770 | 39.3452 | 0
[9 empty] | 771 | 39.3452 | 0
[9 empty] | 772 | 39.3452 | 0
[9 empty] | 773 | 39.3452 | 0
[9 empty] | 774 | 39.3452 | 0
[9 empty] | 775 | 39.3452 | 0
[9 empty] | 776 | 39.3452 | 0
[9 empty] | 777 | 39.3452 | 0
[9 empty] | 778 | 39.3452 | 0
[9 empty] | 779 | 39.3452 | 0
[9 empty] | 780 | 39.3452 | 0
[9 empty] | 781 | 39.3452 | 0
[9 empty] | 782 | 39.3452 | 0
[9 empty] | 783 | 39.3452 | 0
[9 empty] | 784 | 39.3452 | 0
[9 empty] | 785 | 39.3452 | 0
[9 empty] | 786 | 39.3452 | 0
[9 empty] | 787 | 39.3452 | 0
[9 empty] | 788 | 39.3452 | 0
[9 empty] | 789 | 39.3452 | 0
[9 empty] | 790 | 39.3452 | 0
[9 empty] | 791 | 39.3452 | 0
[9 empty] | 792 | 39.3452 | 0
[9 empty] | 793 | 39.3452 | 0
[9 empty] | 794 | 39.3452 | 0
[9 empty] | 795 | 39.3452 | 0
[9 empty] | 796 | 39.3452 | 0
[9 empty] | 797 | 39.3452 | 0
[9 empty] | 798 | 39.3452 | 0
[9 empty] | 799 | 39.3452 | 0
[9 empty] | 800 | 39.3452 | 0
[9 empty] | 801 | 39.3452 | 0
[9 empty] | 802 | 39.3452 | 0
[9 empty] | 803 | 39.3452 | 0
[9 empty] | 804 | 39.3452 | 0
[9 empty] | 805 | 39.3452 | 0
[9 empty] | 806 | 39.3452 | 0
[9 empty] | 807 | 39.3452 | 0
[9 empty] | 808 | 39.3452 | 0
[9 empty] | 809 | 39.3452 | 0
[9 empty] | 810 | 39.3452 | 0
[9 empty] | 811 | 39.3452 | 0
[9 empty] | 812 | 39.3452 | 0
[9 empty] | 813 | 39.3452 | 0
[9 empty] | 814 | 39.3452 | 0
[9 empty] | 815 | 39.3452 | 0
[9 empty] | 816 | 39.3452 | 0
[9 empty] | 817 | 39.3452 | 0
[9 empty] | 818 | 39.3452 | 0
[9 empty] | 819 | 39.3452 | 0
[9 empty] | 820 | 39.3452 | 0
[9 empty] | 821 | 39.3452 | 0
[9 empty] | 822 | 39.3452 | 0
[9 empty] | 823 | 39.3452 | 0
[9 empty] | 824 | 39.3452 | 0
[9 empty] | 825 | 39.3452 | 0
[9 empty] | 826 | 39.3452 | 0
[9 empty] | 827 | 39.3452 | 0
[9 empty] | 828 | 39.3452 | 0
[9 empty] | 829 | 39.3452 | 0
[9 empty] | 830 | 39.3452 | 0
[9 empty] | 831 | 39.3452 | 0
[9 empty] | 832 | 39.3452 | 0
[9 empty] | 833 | 39.3452 | 0
[9 empty] | 834 | 39.3452 | 0
[9 empty] | 835 | 39.3452 | 0
[9 empty] | 836 | 39.3452 | 0
[9 empty] | 837 | 39.3452 | 0
[9 empty] | 838 | 39.3452 | 0
[9 empty] | 839 | 39.3452 | 0
[9 empty] | 840 | 39.3452 | 0
[9 empty] | 841 | 39.3452 | 0
[9 empty] | 842 | 39.3452 | 0
[9 empty] | 843 | 39.3452 | 0
[9 empty] | 844 | 39.3452 | 0
[9 empty] | 845 | 39.3452 | 0
[9 empty] | 846 | 39.3452 | 0
[9 empty] | 847 | 39.3452 | 0
[9 empty] | 848 | 39.3452 | 0
[9 empty] | 849 | 39.3452 | 0
[9 empty] | 850 | 39.3452 | 0
[9 empty] | 851 | 39.3452 | 0
[9 empty] | 852 | 39.3452 | 0
[9 empty] | 853 | 39.3452 | 0
[9 empty] | 854 | 39.3452 | 0
[9 empty] | 855 | 39.3452 | 0
[9 empty] | 856 | 39.3452 | 0
[9 empty] | 857 | 39.3452 | 0
[9 empty] | 858 | 39.3452 | 0
[9 empty] | 859 | 39.3452 | 0
[9 empty] | 860 | 39.3452 | 0
[9 empty] | 861 | 39.3452 | 0
[9 empty] | 862 | 39.3452 | 0
[9 empty] | 863 | 39.3452 | 0
[9 empty] | 864 | 39.3452 | 0
[9 empty] | 865 | 39.3452 | 0
[9 empty] | 866 | 39.3452 | 0
[9 empty] | 867 | 39.3452 | 0
[9 empty] | 868 | 39.3452 | 0
[9 empty] | 869 | 39.3452 | 0
[9 empty] | 870 | 39.3452 | 0
[9 empty] | 871 | 39.3452 | 0
[9 empty] | 872 | 39.3452 | 0
[9 empty] | 873 | 39.3452 | 0
[9 empty] | 874 | 39.3452 | 0
[9 empty] | 875 | 39.3452 | 0
[9 empty] | 876 | 39.3452 | 0
[9 empty] | 877 | 39.3452 | 0
[9 empty] | 878 | 39.3452 | 0
[9 empty] | 879 | 39.3452 | 0
[9 empty] | 880 | 39.3452 | 0
[9 empty] | 881 | 39.3452 | 0
[9 empty] | 882 | 39.3452 | 0
[9 empty] | 883 | 39.3452 | 0
[9 empty] | 884 | 39.3452 | 0
[9 empty] | 885 | 39.3452 | 0
[9 empty] | 886 | 39.3452 | 0
[9 empty] | 887 | 39.3452 | 0
[9 empty] | 888 | 39.3452 | 0
[9 empty] | 889 | 39.3452 | 0
[9 empty] | 890 | 39.3452 | 0
[9 empty] | 891 | 39.3452 | 0
[9 empty] | 892 | 39.3452 | 0
[9 empty] | 893 | 39.3452 | 0
[9 empty] | 894 | 39.3452 | 0
[9 empty] | 895 | 39.3452 | 0
[9 empty] | 896 | 39.3452 | 0
[9 empty] | 897 | 39.3452 | 0
[9 empty] | 898 | 39.3452 | 0
[9 empty] | 899 | 39.3452 | 0
[9 empty] | 900 | 39.3452 | 0
[9 empty] | 901 | 39.3452 | 0
[9 empty] | 902 | 39.3452 | 0
[9 empty] | 903 | 39.3452 | 0
[9 empty] | 904 | 39.3452 | 0
[9 empty] | 905 | 39.3452 | 0
[9 empty] | 906 | 39.3452 | 0
[9 empty] | 907 | 39.3452 | 0
[9 empty] | 908 | 39.3452 | 0
[9 empty] | 909 | 39.3452 | 0
[9 empty] | 910 | 39.3452 | 0
[9 empty] | 911 | 39.3452 | 0
[9 empty] | 912 | 39.3452 | 0
[9 empty] | 913 | 39.3452 | 0
[9 empty] | 914 | 39.3452 | 0
[9 empty] | 915 | 39.3452 | 0
[9 empty] | 916 | 39.3452 | 0
[9 empty] | 917 | 39.3452 | 0
[9 empty] | 918 | 39.3452 | 0
[9 empty] | 919 | 39.3452 | 0
[9 empty] | 920 | 39.3452 | 0
[9 empty] | 921 | 39.3452 | 0
[9 empty] | 922 | 39.3452 | 0
[9 empty] | 923 | 39.3452 | 0
[9 empty] | 924 | 39.3452 | 0
[9 empty] | 925 | 39.3452 | 0
[9 empty] | 926 | 39.3452 | 0
[9 empty] | 927 | 39.3452 | 0
[9 empty] | 928 | 39.3452 | 0
[9 empty] | 929 | 39.3452 | 0
[9 empty] | 930 | 39.3452 | 0
[9 empty] | 931 | 39.3452 | 0
[9 empty] | 932 | 39.3452 | 0
[9 empty] | 933 | 39.3452 | 0
[9 empty] | 934 | 39.3452 | 0
[9 empty] | 935 | 39.3452 | 0
[9 empty] | 936 | 39.3452 | 0
[9 empty] | 937 | 39.3452 | 0
[9 empty] | 938 | 39.3452 | 0
[9 empty] | 939 | 39.3452 | 0
[9 empty] | 940 | 39.3452 | 0
[9 empty] | 941 | 39.3452 | 0
[9 empty] | 942 | 39.3452 | 0
[9 empty] | 943 | 39.3452 | 0
[9 empty] | 944 | 39.3452 | 0
[9 empty] | 945 | 39.3452 | 0
[9 empty] | 946 | 39.3452 | 0
[9 empty] | 947 | 39.3452 | 0
[9 empty] | 948 | 39.3452 | 0
[9 empty] | 949 | 39.3452 | 0
[9 empty] | 950 | 39.3452 | 0
[9 empty] | 951 | 39.3452 | 0
[9 empty] | 952 | 39.3452 | 0
[9 empty] | 953 | 39.3452 | 0
[9 empty] | 954 | 39.3452 | 0
[9 empty] | 955 | 39.3452 | 0
[9 empty] | 956 | 39.3452 | 0
[9 empty] | 957 | 39.3452 | 0
[9 empty] | 958 | 39.3452 | 0
[9 empty] | 959 | 39.3452 | 0
[9 empty] | 960 | 39.3452 | 0
[9 empty] | 961 | 39.3452 | 0
[9 empty] | 962 | 39.3452 | 0
[9 empty] | 963 | 39.3452 | 0
[9 empty] | 964 | 39.3452 | 0
[9 empty] | 965 | 39.3452 | 0
[9 empty] | 966 | 39.3452 | 0
[9 empty] | 967 | 39.3452 | 0
[9 empty] | 968 | 39.3452 | 0
[9 empty] | 969 | 39.3452 | 0
[9 empty] | 970 | 39.3452 | 0
[9 empty] | 971 | 39.3452 | 0
[9 empty] | 972 | 39.3452 | 0
[9 empty] | 973 | 39.3452 | 0
[9 empty] | 974 | 39.3452 | 0
[9 empty] | 975 | 39.3452 | 0
[9 empty] | 976 | 39.3452 | 0
[9 empty] | 977 | 39.3452 | 0
[9 empty] | 978 | 39.3452 | 0
[9 empty] | 979 | 39.3452 | 0
[9 empty] | 980 | 39.3452 | 0
[9 empty] | 981 | 39.3452 | 0
[9 empty] | 982 | 39.3452 | 0
[9 empty] | 983 | 39.3452 | 0
[9 empty] | 984 | 39.3452 | 0
[9 empty] | 985 | 39.3452 | 0
[9 empty] | 986 | 39.3452 | 0
[9 empty] | 987 | 39.3452 | 0
[9 empty] | 988 | 39.3452 | 0
[9 empty] | 989 | 39.3452 | 0
[9 empty] | 990 | 39.3452 | 0
[9 empty] | 991 | 39.3452 | 0
[9 empty] | 992 | 39.3452 | 0
[9 empty] | 993 | 39.3452 | 0
[9 empty] | 994 | 39.3452 | 0
[9 empty] | 995 | 39.3452 | 0
[9 empty] | 996 | 39.3452 | 0
[9 empty] | 997 | 39.3452 | 0
[9 empty] | 998 | 39.3452 | 0
[9 empty] | 999 | 39.3452 | 0
[9 empty] | 1000 | 39.3452 | 0

## Project-1 RT(a,b)
Project 1 | [8 empty] | Trial | Project Duration | Success
Task | Immediate Ancestor | a | m | b | Start Time | U(0,1) | Duration | Finsih Time |  | 34.3421 | 0
A |  | 5 | 6 | 8 | 0 | 0.17607 | 5.648 | 5.648 | 1 | 34.3421 | 0
B |  | 1 | 3 | 4 | 0 | 0.5757 | 3.702 | 3.702 | 2 | 34.3421 | 0
C |  | 2 | 4 | 5 | 0 | 0.11868 | 4.0946 | 4.0946 | 3 | 34.3421 | 0
D | A | 4 | 5 | 6 | 5.648 | 0.56787 | 5.2772 | 10.9252 | 4 | 34.3421 | 0
E | A | 7 | 8 | 10 | 5.648 | 0.70513 | 9.1154 | 14.7634 | 5 | 34.3421 | 0
F | A | 8 | 9 | 13 | 5.648 | 0.35634 | 10.7322 | 16.3801 | 6 | 34.3421 | 0
G | D | 5 | 9 | 19 | 10.9252 | 0.65497 | 14.1696 | 25.0948 | 7 | 34.3421 | 0
H | D | 3 | 4 | 5 | 10.9252 | 0.20544 | 3.4109 | 14.336 | 8 | 34.3421 | 0
I | B,G | 4 | 8 | 10 | 25.0948 | 0.14219 | 5.0777 | 30.1725 | 9 | 34.3421 | 0
J | B,G | 5 | 6 | 8 | 25.0948 | 0.55907 | 7.1015 | 32.1962 | 10 | 34.3421 | 0
K | C,E | 9 | 10 | 15 | 14.7634 | 0.9903 | 14.9418 | 29.7051 | 11 | 34.3421 | 0
L | C,E | 4 | 6 | 8 | 14.7634 | 0.80202 | 7.2081 | 21.9714 | 12 | 34.3421 | 0
M | F,H,I,K | 3 | 4 | 5 | 30.1725 | 0.55118 | 4.1696 | 34.3421 | 13 | 34.3421 | 0
N | J,L,M | 0 | 0 | 0 | 34.3421 | 0.9354 | 0 | 34.3421 | 14 | 34.3421 | 0
[9 empty] | 15 | 34.3421 | 0
[9 empty] | 16 | 34.3421 | 0
[9 empty] | 17 | 34.3421 | 0
[9 empty] | 18 | 34.3421 | 0
Deadline | Average Project Duration | Avg Success Rate | [6 empty] | 19 | 34.3421 | 0
32 | 34.3421 | 0 | [6 empty] | 20 | 34.3421 | 0
[9 empty] | 21 | 34.3421 | 0
[9 empty] | 22 | 34.3421 | 0
[9 empty] | 23 | 34.3421 | 0
[9 empty] | 24 | 34.3421 | 0
[9 empty] | 25 | 34.3421 | 0
[9 empty] | 26 | 34.3421 | 0
[9 empty] | 27 | 34.3421 | 0
[9 empty] | 28 | 34.3421 | 0
[9 empty] | 29 | 34.3421 | 0
[9 empty] | 30 | 34.3421 | 0
[9 empty] | 31 | 34.3421 | 0
[9 empty] | 32 | 34.3421 | 0
[9 empty] | 33 | 34.3421 | 0
[9 empty] | 34 | 34.3421 | 0
[9 empty] | 35 | 34.3421 | 0
[9 empty] | 36 | 34.3421 | 0
[9 empty] | 37 | 34.3421 | 0
[9 empty] | 38 | 34.3421 | 0
[9 empty] | 39 | 34.3421 | 0
[9 empty] | 40 | 34.3421 | 0
[9 empty] | 41 | 34.3421 | 0
[9 empty] | 42 | 34.3421 | 0
[9 empty] | 43 | 34.3421 | 0
[9 empty] | 44 | 34.3421 | 0
[9 empty] | 45 | 34.3421 | 0
[9 empty] | 46 | 34.3421 | 0
[9 empty] | 47 | 34.3421 | 0
[9 empty] | 48 | 34.3421 | 0
[9 empty] | 49 | 34.3421 | 0
[9 empty] | 50 | 34.3421 | 0
[9 empty] | 51 | 34.3421 | 0
[9 empty] | 52 | 34.3421 | 0
[9 empty] | 53 | 34.3421 | 0
[9 empty] | 54 | 34.3421 | 0
[9 empty] | 55 | 34.3421 | 0
[9 empty] | 56 | 34.3421 | 0
[9 empty] | 57 | 34.3421 | 0
[9 empty] | 58 | 34.3421 | 0
[9 empty] | 59 | 34.3421 | 0
[9 empty] | 60 | 34.3421 | 0
[9 empty] | 61 | 34.3421 | 0
[9 empty] | 62 | 34.3421 | 0
[9 empty] | 63 | 34.3421 | 0
[9 empty] | 64 | 34.3421 | 0
[9 empty] | 65 | 34.3421 | 0
[9 empty] | 66 | 34.3421 | 0
[9 empty] | 67 | 34.3421 | 0
[9 empty] | 68 | 34.3421 | 0
[9 empty] | 69 | 34.3421 | 0
[9 empty] | 70 | 34.3421 | 0
[9 empty] | 71 | 34.3421 | 0
[9 empty] | 72 | 34.3421 | 0
[9 empty] | 73 | 34.3421 | 0
[9 empty] | 74 | 34.3421 | 0
[9 empty] | 75 | 34.3421 | 0
[9 empty] | 76 | 34.3421 | 0
[9 empty] | 77 | 34.3421 | 0
[9 empty] | 78 | 34.3421 | 0
[9 empty] | 79 | 34.3421 | 0
[9 empty] | 80 | 34.3421 | 0
[9 empty] | 81 | 34.3421 | 0
[9 empty] | 82 | 34.3421 | 0
[9 empty] | 83 | 34.3421 | 0
[9 empty] | 84 | 34.3421 | 0
[9 empty] | 85 | 34.3421 | 0
[9 empty] | 86 | 34.3421 | 0
[9 empty] | 87 | 34.3421 | 0
[9 empty] | 88 | 34.3421 | 0
[9 empty] | 89 | 34.3421 | 0
[9 empty] | 90 | 34.3421 | 0
[9 empty] | 91 | 34.3421 | 0
[9 empty] | 92 | 34.3421 | 0
[9 empty] | 93 | 34.3421 | 0
[9 empty] | 94 | 34.3421 | 0
[9 empty] | 95 | 34.3421 | 0
[9 empty] | 96 | 34.3421 | 0
[9 empty] | 97 | 34.3421 | 0
[9 empty] | 98 | 34.3421 | 0
[9 empty] | 99 | 34.3421 | 0
[9 empty] | 100 | 34.3421 | 0
[9 empty] | 101 | 34.3421 | 0
[9 empty] | 102 | 34.3421 | 0
[9 empty] | 103 | 34.3421 | 0
[9 empty] | 104 | 34.3421 | 0
[9 empty] | 105 | 34.3421 | 0
[9 empty] | 106 | 34.3421 | 0
[9 empty] | 107 | 34.3421 | 0
[9 empty] | 108 | 34.3421 | 0
[9 empty] | 109 | 34.3421 | 0
[9 empty] | 110 | 34.3421 | 0
[9 empty] | 111 | 34.3421 | 0
[9 empty] | 112 | 34.3421 | 0
[9 empty] | 113 | 34.3421 | 0
[9 empty] | 114 | 34.3421 | 0
[9 empty] | 115 | 34.3421 | 0
[9 empty] | 116 | 34.3421 | 0
[9 empty] | 117 | 34.3421 | 0
[9 empty] | 118 | 34.3421 | 0
[9 empty] | 119 | 34.3421 | 0
[9 empty] | 120 | 34.3421 | 0
[9 empty] | 121 | 34.3421 | 0
[9 empty] | 122 | 34.3421 | 0
[9 empty] | 123 | 34.3421 | 0
[9 empty] | 124 | 34.3421 | 0
[9 empty] | 125 | 34.3421 | 0
[9 empty] | 126 | 34.3421 | 0
[9 empty] | 127 | 34.3421 | 0
[9 empty] | 128 | 34.3421 | 0
[9 empty] | 129 | 34.3421 | 0
[9 empty] | 130 | 34.3421 | 0
[9 empty] | 131 | 34.3421 | 0
[9 empty] | 132 | 34.3421 | 0
[9 empty] | 133 | 34.3421 | 0
[9 empty] | 134 | 34.3421 | 0
[9 empty] | 135 | 34.3421 | 0
[9 empty] | 136 | 34.3421 | 0
[9 empty] | 137 | 34.3421 | 0
[9 empty] | 138 | 34.3421 | 0
[9 empty] | 139 | 34.3421 | 0
[9 empty] | 140 | 34.3421 | 0
[9 empty] | 141 | 34.3421 | 0
[9 empty] | 142 | 34.3421 | 0
[9 empty] | 143 | 34.3421 | 0
[9 empty] | 144 | 34.3421 | 0
[9 empty] | 145 | 34.3421 | 0
[9 empty] | 146 | 34.3421 | 0
[9 empty] | 147 | 34.3421 | 0
[9 empty] | 148 | 34.3421 | 0
[9 empty] | 149 | 34.3421 | 0
[9 empty] | 150 | 34.3421 | 0
[9 empty] | 151 | 34.3421 | 0
[9 empty] | 152 | 34.3421 | 0
[9 empty] | 153 | 34.3421 | 0
[9 empty] | 154 | 34.3421 | 0
[9 empty] | 155 | 34.3421 | 0
[9 empty] | 156 | 34.3421 | 0
[9 empty] | 157 | 34.3421 | 0
[9 empty] | 158 | 34.3421 | 0
[9 empty] | 159 | 34.3421 | 0
[9 empty] | 160 | 34.3421 | 0
[9 empty] | 161 | 34.3421 | 0
[9 empty] | 162 | 34.3421 | 0
[9 empty] | 163 | 34.3421 | 0
[9 empty] | 164 | 34.3421 | 0
[9 empty] | 165 | 34.3421 | 0
[9 empty] | 166 | 34.3421 | 0
[9 empty] | 167 | 34.3421 | 0
[9 empty] | 168 | 34.3421 | 0
[9 empty] | 169 | 34.3421 | 0
[9 empty] | 170 | 34.3421 | 0
[9 empty] | 171 | 34.3421 | 0
[9 empty] | 172 | 34.3421 | 0
[9 empty] | 173 | 34.3421 | 0
[9 empty] | 174 | 34.3421 | 0
[9 empty] | 175 | 34.3421 | 0
[9 empty] | 176 | 34.3421 | 0
[9 empty] | 177 | 34.3421 | 0
[9 empty] | 178 | 34.3421 | 0
[9 empty] | 179 | 34.3421 | 0
[9 empty] | 180 | 34.3421 | 0
[9 empty] | 181 | 34.3421 | 0
[9 empty] | 182 | 34.3421 | 0
[9 empty] | 183 | 34.3421 | 0
[9 empty] | 184 | 34.3421 | 0
[9 empty] | 185 | 34.3421 | 0
[9 empty] | 186 | 34.3421 | 0
[9 empty] | 187 | 34.3421 | 0
[9 empty] | 188 | 34.3421 | 0
[9 empty] | 189 | 34.3421 | 0
[9 empty] | 190 | 34.3421 | 0
[9 empty] | 191 | 34.3421 | 0
[9 empty] | 192 | 34.3421 | 0
[9 empty] | 193 | 34.3421 | 0
[9 empty] | 194 | 34.3421 | 0
[9 empty] | 195 | 34.3421 | 0
[9 empty] | 196 | 34.3421 | 0
[9 empty] | 197 | 34.3421 | 0
[9 empty] | 198 | 34.3421 | 0
[9 empty] | 199 | 34.3421 | 0
[9 empty] | 200 | 34.3421 | 0
[9 empty] | 201 | 34.3421 | 0
[9 empty] | 202 | 34.3421 | 0
[9 empty] | 203 | 34.3421 | 0
[9 empty] | 204 | 34.3421 | 0
[9 empty] | 205 | 34.3421 | 0
[9 empty] | 206 | 34.3421 | 0
[9 empty] | 207 | 34.3421 | 0
[9 empty] | 208 | 34.3421 | 0
[9 empty] | 209 | 34.3421 | 0
[9 empty] | 210 | 34.3421 | 0
[9 empty] | 211 | 34.3421 | 0
[9 empty] | 212 | 34.3421 | 0
[9 empty] | 213 | 34.3421 | 0
[9 empty] | 214 | 34.3421 | 0
[9 empty] | 215 | 34.3421 | 0
[9 empty] | 216 | 34.3421 | 0
[9 empty] | 217 | 34.3421 | 0
[9 empty] | 218 | 34.3421 | 0
[9 empty] | 219 | 34.3421 | 0
[9 empty] | 220 | 34.3421 | 0
[9 empty] | 221 | 34.3421 | 0
[9 empty] | 222 | 34.3421 | 0
[9 empty] | 223 | 34.3421 | 0
[9 empty] | 224 | 34.3421 | 0
[9 empty] | 225 | 34.3421 | 0
[9 empty] | 226 | 34.3421 | 0
[9 empty] | 227 | 34.3421 | 0
[9 empty] | 228 | 34.3421 | 0
[9 empty] | 229 | 34.3421 | 0
[9 empty] | 230 | 34.3421 | 0
[9 empty] | 231 | 34.3421 | 0
[9 empty] | 232 | 34.3421 | 0
[9 empty] | 233 | 34.3421 | 0
[9 empty] | 234 | 34.3421 | 0
[9 empty] | 235 | 34.3421 | 0
[9 empty] | 236 | 34.3421 | 0
[9 empty] | 237 | 34.3421 | 0
[9 empty] | 238 | 34.3421 | 0
[9 empty] | 239 | 34.3421 | 0
[9 empty] | 240 | 34.3421 | 0
[9 empty] | 241 | 34.3421 | 0
[9 empty] | 242 | 34.3421 | 0
[9 empty] | 243 | 34.3421 | 0
[9 empty] | 244 | 34.3421 | 0
[9 empty] | 245 | 34.3421 | 0
[9 empty] | 246 | 34.3421 | 0
[9 empty] | 247 | 34.3421 | 0
[9 empty] | 248 | 34.3421 | 0
[9 empty] | 249 | 34.3421 | 0
[9 empty] | 250 | 34.3421 | 0
[9 empty] | 251 | 34.3421 | 0
[9 empty] | 252 | 34.3421 | 0
[9 empty] | 253 | 34.3421 | 0
[9 empty] | 254 | 34.3421 | 0
[9 empty] | 255 | 34.3421 | 0
[9 empty] | 256 | 34.3421 | 0
[9 empty] | 257 | 34.3421 | 0
[9 empty] | 258 | 34.3421 | 0
[9 empty] | 259 | 34.3421 | 0
[9 empty] | 260 | 34.3421 | 0
[9 empty] | 261 | 34.3421 | 0
[9 empty] | 262 | 34.3421 | 0
[9 empty] | 263 | 34.3421 | 0
[9 empty] | 264 | 34.3421 | 0
[9 empty] | 265 | 34.3421 | 0
[9 empty] | 266 | 34.3421 | 0
[9 empty] | 267 | 34.3421 | 0
[9 empty] | 268 | 34.3421 | 0
[9 empty] | 269 | 34.3421 | 0
[9 empty] | 270 | 34.3421 | 0
[9 empty] | 271 | 34.3421 | 0
[9 empty] | 272 | 34.3421 | 0
[9 empty] | 273 | 34.3421 | 0
[9 empty] | 274 | 34.3421 | 0
[9 empty] | 275 | 34.3421 | 0
[9 empty] | 276 | 34.3421 | 0
[9 empty] | 277 | 34.3421 | 0
[9 empty] | 278 | 34.3421 | 0
[9 empty] | 279 | 34.3421 | 0
[9 empty] | 280 | 34.3421 | 0
[9 empty] | 281 | 34.3421 | 0
[9 empty] | 282 | 34.3421 | 0
[9 empty] | 283 | 34.3421 | 0
[9 empty] | 284 | 34.3421 | 0
[9 empty] | 285 | 34.3421 | 0
[9 empty] | 286 | 34.3421 | 0
[9 empty] | 287 | 34.3421 | 0
[9 empty] | 288 | 34.3421 | 0
[9 empty] | 289 | 34.3421 | 0
[9 empty] | 290 | 34.3421 | 0
[9 empty] | 291 | 34.3421 | 0
[9 empty] | 292 | 34.3421 | 0
[9 empty] | 293 | 34.3421 | 0
[9 empty] | 294 | 34.3421 | 0
[9 empty] | 295 | 34.3421 | 0
[9 empty] | 296 | 34.3421 | 0
[9 empty] | 297 | 34.3421 | 0
[9 empty] | 298 | 34.3421 | 0
[9 empty] | 299 | 34.3421 | 0
[9 empty] | 300 | 34.3421 | 0
[9 empty] | 301 | 34.3421 | 0
[9 empty] | 302 | 34.3421 | 0
[9 empty] | 303 | 34.3421 | 0
[9 empty] | 304 | 34.3421 | 0
[9 empty] | 305 | 34.3421 | 0
[9 empty] | 306 | 34.3421 | 0
[9 empty] | 307 | 34.3421 | 0
[9 empty] | 308 | 34.3421 | 0
[9 empty] | 309 | 34.3421 | 0
[9 empty] | 310 | 34.3421 | 0
[9 empty] | 311 | 34.3421 | 0
[9 empty] | 312 | 34.3421 | 0
[9 empty] | 313 | 34.3421 | 0
[9 empty] | 314 | 34.3421 | 0
[9 empty] | 315 | 34.3421 | 0
[9 empty] | 316 | 34.3421 | 0
[9 empty] | 317 | 34.3421 | 0
[9 empty] | 318 | 34.3421 | 0
[9 empty] | 319 | 34.3421 | 0
[9 empty] | 320 | 34.3421 | 0
[9 empty] | 321 | 34.3421 | 0
[9 empty] | 322 | 34.3421 | 0
[9 empty] | 323 | 34.3421 | 0
[9 empty] | 324 | 34.3421 | 0
[9 empty] | 325 | 34.3421 | 0
[9 empty] | 326 | 34.3421 | 0
[9 empty] | 327 | 34.3421 | 0
[9 empty] | 328 | 34.3421 | 0
[9 empty] | 329 | 34.3421 | 0
[9 empty] | 330 | 34.3421 | 0
[9 empty] | 331 | 34.3421 | 0
[9 empty] | 332 | 34.3421 | 0
[9 empty] | 333 | 34.3421 | 0
[9 empty] | 334 | 34.3421 | 0
[9 empty] | 335 | 34.3421 | 0
[9 empty] | 336 | 34.3421 | 0
[9 empty] | 337 | 34.3421 | 0
[9 empty] | 338 | 34.3421 | 0
[9 empty] | 339 | 34.3421 | 0
[9 empty] | 340 | 34.3421 | 0
[9 empty] | 341 | 34.3421 | 0
[9 empty] | 342 | 34.3421 | 0
[9 empty] | 343 | 34.3421 | 0
[9 empty] | 344 | 34.3421 | 0
[9 empty] | 345 | 34.3421 | 0
[9 empty] | 346 | 34.3421 | 0
[9 empty] | 347 | 34.3421 | 0
[9 empty] | 348 | 34.3421 | 0
[9 empty] | 349 | 34.3421 | 0
[9 empty] | 350 | 34.3421 | 0
[9 empty] | 351 | 34.3421 | 0
[9 empty] | 352 | 34.3421 | 0
[9 empty] | 353 | 34.3421 | 0
[9 empty] | 354 | 34.3421 | 0
[9 empty] | 355 | 34.3421 | 0
[9 empty] | 356 | 34.3421 | 0
[9 empty] | 357 | 34.3421 | 0
[9 empty] | 358 | 34.3421 | 0
[9 empty] | 359 | 34.3421 | 0
[9 empty] | 360 | 34.3421 | 0
[9 empty] | 361 | 34.3421 | 0
[9 empty] | 362 | 34.3421 | 0
[9 empty] | 363 | 34.3421 | 0
[9 empty] | 364 | 34.3421 | 0
[9 empty] | 365 | 34.3421 | 0
[9 empty] | 366 | 34.3421 | 0
[9 empty] | 367 | 34.3421 | 0
[9 empty] | 368 | 34.3421 | 0
[9 empty] | 369 | 34.3421 | 0
[9 empty] | 370 | 34.3421 | 0
[9 empty] | 371 | 34.3421 | 0
[9 empty] | 372 | 34.3421 | 0
[9 empty] | 373 | 34.3421 | 0
[9 empty] | 374 | 34.3421 | 0
[9 empty] | 375 | 34.3421 | 0
[9 empty] | 376 | 34.3421 | 0
[9 empty] | 377 | 34.3421 | 0
[9 empty] | 378 | 34.3421 | 0
[9 empty] | 379 | 34.3421 | 0
[9 empty] | 380 | 34.3421 | 0
[9 empty] | 381 | 34.3421 | 0
[9 empty] | 382 | 34.3421 | 0
[9 empty] | 383 | 34.3421 | 0
[9 empty] | 384 | 34.3421 | 0
[9 empty] | 385 | 34.3421 | 0
[9 empty] | 386 | 34.3421 | 0
[9 empty] | 387 | 34.3421 | 0
[9 empty] | 388 | 34.3421 | 0
[9 empty] | 389 | 34.3421 | 0
[9 empty] | 390 | 34.3421 | 0
[9 empty] | 391 | 34.3421 | 0
[9 empty] | 392 | 34.3421 | 0
[9 empty] | 393 | 34.3421 | 0
[9 empty] | 394 | 34.3421 | 0
[9 empty] | 395 | 34.3421 | 0
[9 empty] | 396 | 34.3421 | 0
[9 empty] | 397 | 34.3421 | 0
[9 empty] | 398 | 34.3421 | 0
[9 empty] | 399 | 34.3421 | 0
[9 empty] | 400 | 34.3421 | 0
[9 empty] | 401 | 34.3421 | 0
[9 empty] | 402 | 34.3421 | 0
[9 empty] | 403 | 34.3421 | 0
[9 empty] | 404 | 34.3421 | 0
[9 empty] | 405 | 34.3421 | 0
[9 empty] | 406 | 34.3421 | 0
[9 empty] | 407 | 34.3421 | 0
[9 empty] | 408 | 34.3421 | 0
[9 empty] | 409 | 34.3421 | 0
[9 empty] | 410 | 34.3421 | 0
[9 empty] | 411 | 34.3421 | 0
[9 empty] | 412 | 34.3421 | 0
[9 empty] | 413 | 34.3421 | 0
[9 empty] | 414 | 34.3421 | 0
[9 empty] | 415 | 34.3421 | 0
[9 empty] | 416 | 34.3421 | 0
[9 empty] | 417 | 34.3421 | 0
[9 empty] | 418 | 34.3421 | 0
[9 empty] | 419 | 34.3421 | 0
[9 empty] | 420 | 34.3421 | 0
[9 empty] | 421 | 34.3421 | 0
[9 empty] | 422 | 34.3421 | 0
[9 empty] | 423 | 34.3421 | 0
[9 empty] | 424 | 34.3421 | 0
[9 empty] | 425 | 34.3421 | 0
[9 empty] | 426 | 34.3421 | 0
[9 empty] | 427 | 34.3421 | 0
[9 empty] | 428 | 34.3421 | 0
[9 empty] | 429 | 34.3421 | 0
[9 empty] | 430 | 34.3421 | 0
[9 empty] | 431 | 34.3421 | 0
[9 empty] | 432 | 34.3421 | 0
[9 empty] | 433 | 34.3421 | 0
[9 empty] | 434 | 34.3421 | 0
[9 empty] | 435 | 34.3421 | 0
[9 empty] | 436 | 34.3421 | 0
[9 empty] | 437 | 34.3421 | 0
[9 empty] | 438 | 34.3421 | 0
[9 empty] | 439 | 34.3421 | 0
[9 empty] | 440 | 34.3421 | 0
[9 empty] | 441 | 34.3421 | 0
[9 empty] | 442 | 34.3421 | 0
[9 empty] | 443 | 34.3421 | 0
[9 empty] | 444 | 34.3421 | 0
[9 empty] | 445 | 34.3421 | 0
[9 empty] | 446 | 34.3421 | 0
[9 empty] | 447 | 34.3421 | 0
[9 empty] | 448 | 34.3421 | 0
[9 empty] | 449 | 34.3421 | 0
[9 empty] | 450 | 34.3421 | 0
[9 empty] | 451 | 34.3421 | 0
[9 empty] | 452 | 34.3421 | 0
[9 empty] | 453 | 34.3421 | 0
[9 empty] | 454 | 34.3421 | 0
[9 empty] | 455 | 34.3421 | 0
[9 empty] | 456 | 34.3421 | 0
[9 empty] | 457 | 34.3421 | 0
[9 empty] | 458 | 34.3421 | 0
[9 empty] | 459 | 34.3421 | 0
[9 empty] | 460 | 34.3421 | 0
[9 empty] | 461 | 34.3421 | 0
[9 empty] | 462 | 34.3421 | 0
[9 empty] | 463 | 34.3421 | 0
[9 empty] | 464 | 34.3421 | 0
[9 empty] | 465 | 34.3421 | 0
[9 empty] | 466 | 34.3421 | 0
[9 empty] | 467 | 34.3421 | 0
[9 empty] | 468 | 34.3421 | 0
[9 empty] | 469 | 34.3421 | 0
[9 empty] | 470 | 34.3421 | 0
[9 empty] | 471 | 34.3421 | 0
[9 empty] | 472 | 34.3421 | 0
[9 empty] | 473 | 34.3421 | 0
[9 empty] | 474 | 34.3421 | 0
[9 empty] | 475 | 34.3421 | 0
[9 empty] | 476 | 34.3421 | 0
[9 empty] | 477 | 34.3421 | 0
[9 empty] | 478 | 34.3421 | 0
[9 empty] | 479 | 34.3421 | 0
[9 empty] | 480 | 34.3421 | 0
[9 empty] | 481 | 34.3421 | 0
[9 empty] | 482 | 34.3421 | 0
[9 empty] | 483 | 34.3421 | 0
[9 empty] | 484 | 34.3421 | 0
[9 empty] | 485 | 34.3421 | 0
[9 empty] | 486 | 34.3421 | 0
[9 empty] | 487 | 34.3421 | 0
[9 empty] | 488 | 34.3421 | 0
[9 empty] | 489 | 34.3421 | 0
[9 empty] | 490 | 34.3421 | 0
[9 empty] | 491 | 34.3421 | 0
[9 empty] | 492 | 34.3421 | 0
[9 empty] | 493 | 34.3421 | 0
[9 empty] | 494 | 34.3421 | 0
[9 empty] | 495 | 34.3421 | 0
[9 empty] | 496 | 34.3421 | 0
[9 empty] | 497 | 34.3421 | 0
[9 empty] | 498 | 34.3421 | 0
[9 empty] | 499 | 34.3421 | 0
[9 empty] | 500 | 34.3421 | 0
[9 empty] | 501 | 34.3421 | 0
[9 empty] | 502 | 34.3421 | 0
[9 empty] | 503 | 34.3421 | 0
[9 empty] | 504 | 34.3421 | 0
[9 empty] | 505 | 34.3421 | 0
[9 empty] | 506 | 34.3421 | 0
[9 empty] | 507 | 34.3421 | 0
[9 empty] | 508 | 34.3421 | 0
[9 empty] | 509 | 34.3421 | 0
[9 empty] | 510 | 34.3421 | 0
[9 empty] | 511 | 34.3421 | 0
[9 empty] | 512 | 34.3421 | 0
[9 empty] | 513 | 34.3421 | 0
[9 empty] | 514 | 34.3421 | 0
[9 empty] | 515 | 34.3421 | 0
[9 empty] | 516 | 34.3421 | 0
[9 empty] | 517 | 34.3421 | 0
[9 empty] | 518 | 34.3421 | 0
[9 empty] | 519 | 34.3421 | 0
[9 empty] | 520 | 34.3421 | 0
[9 empty] | 521 | 34.3421 | 0
[9 empty] | 522 | 34.3421 | 0
[9 empty] | 523 | 34.3421 | 0
[9 empty] | 524 | 34.3421 | 0
[9 empty] | 525 | 34.3421 | 0
[9 empty] | 526 | 34.3421 | 0
[9 empty] | 527 | 34.3421 | 0
[9 empty] | 528 | 34.3421 | 0
[9 empty] | 529 | 34.3421 | 0
[9 empty] | 530 | 34.3421 | 0
[9 empty] | 531 | 34.3421 | 0
[9 empty] | 532 | 34.3421 | 0
[9 empty] | 533 | 34.3421 | 0
[9 empty] | 534 | 34.3421 | 0
[9 empty] | 535 | 34.3421 | 0
[9 empty] | 536 | 34.3421 | 0
[9 empty] | 537 | 34.3421 | 0
[9 empty] | 538 | 34.3421 | 0
[9 empty] | 539 | 34.3421 | 0
[9 empty] | 540 | 34.3421 | 0
[9 empty] | 541 | 34.3421 | 0
[9 empty] | 542 | 34.3421 | 0
[9 empty] | 543 | 34.3421 | 0
[9 empty] | 544 | 34.3421 | 0
[9 empty] | 545 | 34.3421 | 0
[9 empty] | 546 | 34.3421 | 0
[9 empty] | 547 | 34.3421 | 0
[9 empty] | 548 | 34.3421 | 0
[9 empty] | 549 | 34.3421 | 0
[9 empty] | 550 | 34.3421 | 0
[9 empty] | 551 | 34.3421 | 0
[9 empty] | 552 | 34.3421 | 0
[9 empty] | 553 | 34.3421 | 0
[9 empty] | 554 | 34.3421 | 0
[9 empty] | 555 | 34.3421 | 0
[9 empty] | 556 | 34.3421 | 0
[9 empty] | 557 | 34.3421 | 0
[9 empty] | 558 | 34.3421 | 0
[9 empty] | 559 | 34.3421 | 0
[9 empty] | 560 | 34.3421 | 0
[9 empty] | 561 | 34.3421 | 0
[9 empty] | 562 | 34.3421 | 0
[9 empty] | 563 | 34.3421 | 0
[9 empty] | 564 | 34.3421 | 0
[9 empty] | 565 | 34.3421 | 0
[9 empty] | 566 | 34.3421 | 0
[9 empty] | 567 | 34.3421 | 0
[9 empty] | 568 | 34.3421 | 0
[9 empty] | 569 | 34.3421 | 0
[9 empty] | 570 | 34.3421 | 0
[9 empty] | 571 | 34.3421 | 0
[9 empty] | 572 | 34.3421 | 0
[9 empty] | 573 | 34.3421 | 0
[9 empty] | 574 | 34.3421 | 0
[9 empty] | 575 | 34.3421 | 0
[9 empty] | 576 | 34.3421 | 0
[9 empty] | 577 | 34.3421 | 0
[9 empty] | 578 | 34.3421 | 0
[9 empty] | 579 | 34.3421 | 0
[9 empty] | 580 | 34.3421 | 0
[9 empty] | 581 | 34.3421 | 0
[9 empty] | 582 | 34.3421 | 0
[9 empty] | 583 | 34.3421 | 0
[9 empty] | 584 | 34.3421 | 0
[9 empty] | 585 | 34.3421 | 0
[9 empty] | 586 | 34.3421 | 0
[9 empty] | 587 | 34.3421 | 0
[9 empty] | 588 | 34.3421 | 0
[9 empty] | 589 | 34.3421 | 0
[9 empty] | 590 | 34.3421 | 0
[9 empty] | 591 | 34.3421 | 0
[9 empty] | 592 | 34.3421 | 0
[9 empty] | 593 | 34.3421 | 0
[9 empty] | 594 | 34.3421 | 0
[9 empty] | 595 | 34.3421 | 0
[9 empty] | 596 | 34.3421 | 0
[9 empty] | 597 | 34.3421 | 0
[9 empty] | 598 | 34.3421 | 0
[9 empty] | 599 | 34.3421 | 0
[9 empty] | 600 | 34.3421 | 0
[9 empty] | 601 | 34.3421 | 0
[9 empty] | 602 | 34.3421 | 0
[9 empty] | 603 | 34.3421 | 0
[9 empty] | 604 | 34.3421 | 0
[9 empty] | 605 | 34.3421 | 0
[9 empty] | 606 | 34.3421 | 0
[9 empty] | 607 | 34.3421 | 0
[9 empty] | 608 | 34.3421 | 0
[9 empty] | 609 | 34.3421 | 0
[9 empty] | 610 | 34.3421 | 0
[9 empty] | 611 | 34.3421 | 0
[9 empty] | 612 | 34.3421 | 0
[9 empty] | 613 | 34.3421 | 0
[9 empty] | 614 | 34.3421 | 0
[9 empty] | 615 | 34.3421 | 0
[9 empty] | 616 | 34.3421 | 0
[9 empty] | 617 | 34.3421 | 0
[9 empty] | 618 | 34.3421 | 0
[9 empty] | 619 | 34.3421 | 0
[9 empty] | 620 | 34.3421 | 0
[9 empty] | 621 | 34.3421 | 0
[9 empty] | 622 | 34.3421 | 0
[9 empty] | 623 | 34.3421 | 0
[9 empty] | 624 | 34.3421 | 0
[9 empty] | 625 | 34.3421 | 0
[9 empty] | 626 | 34.3421 | 0
[9 empty] | 627 | 34.3421 | 0
[9 empty] | 628 | 34.3421 | 0
[9 empty] | 629 | 34.3421 | 0
[9 empty] | 630 | 34.3421 | 0
[9 empty] | 631 | 34.3421 | 0
[9 empty] | 632 | 34.3421 | 0
[9 empty] | 633 | 34.3421 | 0
[9 empty] | 634 | 34.3421 | 0
[9 empty] | 635 | 34.3421 | 0
[9 empty] | 636 | 34.3421 | 0
[9 empty] | 637 | 34.3421 | 0
[9 empty] | 638 | 34.3421 | 0
[9 empty] | 639 | 34.3421 | 0
[9 empty] | 640 | 34.3421 | 0
[9 empty] | 641 | 34.3421 | 0
[9 empty] | 642 | 34.3421 | 0
[9 empty] | 643 | 34.3421 | 0
[9 empty] | 644 | 34.3421 | 0
[9 empty] | 645 | 34.3421 | 0
[9 empty] | 646 | 34.3421 | 0
[9 empty] | 647 | 34.3421 | 0
[9 empty] | 648 | 34.3421 | 0
[9 empty] | 649 | 34.3421 | 0
[9 empty] | 650 | 34.3421 | 0
[9 empty] | 651 | 34.3421 | 0
[9 empty] | 652 | 34.3421 | 0
[9 empty] | 653 | 34.3421 | 0
[9 empty] | 654 | 34.3421 | 0
[9 empty] | 655 | 34.3421 | 0
[9 empty] | 656 | 34.3421 | 0
[9 empty] | 657 | 34.3421 | 0
[9 empty] | 658 | 34.3421 | 0
[9 empty] | 659 | 34.3421 | 0
[9 empty] | 660 | 34.3421 | 0
[9 empty] | 661 | 34.3421 | 0
[9 empty] | 662 | 34.3421 | 0
[9 empty] | 663 | 34.3421 | 0
[9 empty] | 664 | 34.3421 | 0
[9 empty] | 665 | 34.3421 | 0
[9 empty] | 666 | 34.3421 | 0
[9 empty] | 667 | 34.3421 | 0
[9 empty] | 668 | 34.3421 | 0
[9 empty] | 669 | 34.3421 | 0
[9 empty] | 670 | 34.3421 | 0
[9 empty] | 671 | 34.3421 | 0
[9 empty] | 672 | 34.3421 | 0
[9 empty] | 673 | 34.3421 | 0
[9 empty] | 674 | 34.3421 | 0
[9 empty] | 675 | 34.3421 | 0
[9 empty] | 676 | 34.3421 | 0
[9 empty] | 677 | 34.3421 | 0
[9 empty] | 678 | 34.3421 | 0
[9 empty] | 679 | 34.3421 | 0
[9 empty] | 680 | 34.3421 | 0
[9 empty] | 681 | 34.3421 | 0
[9 empty] | 682 | 34.3421 | 0
[9 empty] | 683 | 34.3421 | 0
[9 empty] | 684 | 34.3421 | 0
[9 empty] | 685 | 34.3421 | 0
[9 empty] | 686 | 34.3421 | 0
[9 empty] | 687 | 34.3421 | 0
[9 empty] | 688 | 34.3421 | 0
[9 empty] | 689 | 34.3421 | 0
[9 empty] | 690 | 34.3421 | 0
[9 empty] | 691 | 34.3421 | 0
[9 empty] | 692 | 34.3421 | 0
[9 empty] | 693 | 34.3421 | 0
[9 empty] | 694 | 34.3421 | 0
[9 empty] | 695 | 34.3421 | 0
[9 empty] | 696 | 34.3421 | 0
[9 empty] | 697 | 34.3421 | 0
[9 empty] | 698 | 34.3421 | 0
[9 empty] | 699 | 34.3421 | 0
[9 empty] | 700 | 34.3421 | 0
[9 empty] | 701 | 34.3421 | 0
[9 empty] | 702 | 34.3421 | 0
[9 empty] | 703 | 34.3421 | 0
[9 empty] | 704 | 34.3421 | 0
[9 empty] | 705 | 34.3421 | 0
[9 empty] | 706 | 34.3421 | 0
[9 empty] | 707 | 34.3421 | 0
[9 empty] | 708 | 34.3421 | 0
[9 empty] | 709 | 34.3421 | 0
[9 empty] | 710 | 34.3421 | 0
[9 empty] | 711 | 34.3421 | 0
[9 empty] | 712 | 34.3421 | 0
[9 empty] | 713 | 34.3421 | 0
[9 empty] | 714 | 34.3421 | 0
[9 empty] | 715 | 34.3421 | 0
[9 empty] | 716 | 34.3421 | 0
[9 empty] | 717 | 34.3421 | 0
[9 empty] | 718 | 34.3421 | 0
[9 empty] | 719 | 34.3421 | 0
[9 empty] | 720 | 34.3421 | 0
[9 empty] | 721 | 34.3421 | 0
[9 empty] | 722 | 34.3421 | 0
[9 empty] | 723 | 34.3421 | 0
[9 empty] | 724 | 34.3421 | 0
[9 empty] | 725 | 34.3421 | 0
[9 empty] | 726 | 34.3421 | 0
[9 empty] | 727 | 34.3421 | 0
[9 empty] | 728 | 34.3421 | 0
[9 empty] | 729 | 34.3421 | 0
[9 empty] | 730 | 34.3421 | 0
[9 empty] | 731 | 34.3421 | 0
[9 empty] | 732 | 34.3421 | 0
[9 empty] | 733 | 34.3421 | 0
[9 empty] | 734 | 34.3421 | 0
[9 empty] | 735 | 34.3421 | 0
[9 empty] | 736 | 34.3421 | 0
[9 empty] | 737 | 34.3421 | 0
[9 empty] | 738 | 34.3421 | 0
[9 empty] | 739 | 34.3421 | 0
[9 empty] | 740 | 34.3421 | 0
[9 empty] | 741 | 34.3421 | 0
[9 empty] | 742 | 34.3421 | 0
[9 empty] | 743 | 34.3421 | 0
[9 empty] | 744 | 34.3421 | 0
[9 empty] | 745 | 34.3421 | 0
[9 empty] | 746 | 34.3421 | 0
[9 empty] | 747 | 34.3421 | 0
[9 empty] | 748 | 34.3421 | 0
[9 empty] | 749 | 34.3421 | 0
[9 empty] | 750 | 34.3421 | 0
[9 empty] | 751 | 34.3421 | 0
[9 empty] | 752 | 34.3421 | 0
[9 empty] | 753 | 34.3421 | 0
[9 empty] | 754 | 34.3421 | 0
[9 empty] | 755 | 34.3421 | 0
[9 empty] | 756 | 34.3421 | 0
[9 empty] | 757 | 34.3421 | 0
[9 empty] | 758 | 34.3421 | 0
[9 empty] | 759 | 34.3421 | 0
[9 empty] | 760 | 34.3421 | 0
[9 empty] | 761 | 34.3421 | 0
[9 empty] | 762 | 34.3421 | 0
[9 empty] | 763 | 34.3421 | 0
[9 empty] | 764 | 34.3421 | 0
[9 empty] | 765 | 34.3421 | 0
[9 empty] | 766 | 34.3421 | 0
[9 empty] | 767 | 34.3421 | 0
[9 empty] | 768 | 34.3421 | 0
[9 empty] | 769 | 34.3421 | 0
[9 empty] | 770 | 34.3421 | 0
[9 empty] | 771 | 34.3421 | 0
[9 empty] | 772 | 34.3421 | 0
[9 empty] | 773 | 34.3421 | 0
[9 empty] | 774 | 34.3421 | 0
[9 empty] | 775 | 34.3421 | 0
[9 empty] | 776 | 34.3421 | 0
[9 empty] | 777 | 34.3421 | 0
[9 empty] | 778 | 34.3421 | 0
[9 empty] | 779 | 34.3421 | 0
[9 empty] | 780 | 34.3421 | 0
[9 empty] | 781 | 34.3421 | 0
[9 empty] | 782 | 34.3421 | 0
[9 empty] | 783 | 34.3421 | 0
[9 empty] | 784 | 34.3421 | 0
[9 empty] | 785 | 34.3421 | 0
[9 empty] | 786 | 34.3421 | 0
[9 empty] | 787 | 34.3421 | 0
[9 empty] | 788 | 34.3421 | 0
[9 empty] | 789 | 34.3421 | 0
[9 empty] | 790 | 34.3421 | 0
[9 empty] | 791 | 34.3421 | 0
[9 empty] | 792 | 34.3421 | 0
[9 empty] | 793 | 34.3421 | 0
[9 empty] | 794 | 34.3421 | 0
[9 empty] | 795 | 34.3421 | 0
[9 empty] | 796 | 34.3421 | 0
[9 empty] | 797 | 34.3421 | 0
[9 empty] | 798 | 34.3421 | 0
[9 empty] | 799 | 34.3421 | 0
[9 empty] | 800 | 34.3421 | 0
[9 empty] | 801 | 34.3421 | 0
[9 empty] | 802 | 34.3421 | 0
[9 empty] | 803 | 34.3421 | 0
[9 empty] | 804 | 34.3421 | 0
[9 empty] | 805 | 34.3421 | 0
[9 empty] | 806 | 34.3421 | 0
[9 empty] | 807 | 34.3421 | 0
[9 empty] | 808 | 34.3421 | 0
[9 empty] | 809 | 34.3421 | 0
[9 empty] | 810 | 34.3421 | 0
[9 empty] | 811 | 34.3421 | 0
[9 empty] | 812 | 34.3421 | 0
[9 empty] | 813 | 34.3421 | 0
[9 empty] | 814 | 34.3421 | 0
[9 empty] | 815 | 34.3421 | 0
[9 empty] | 816 | 34.3421 | 0
[9 empty] | 817 | 34.3421 | 0
[9 empty] | 818 | 34.3421 | 0
[9 empty] | 819 | 34.3421 | 0
[9 empty] | 820 | 34.3421 | 0
[9 empty] | 821 | 34.3421 | 0
[9 empty] | 822 | 34.3421 | 0
[9 empty] | 823 | 34.3421 | 0
[9 empty] | 824 | 34.3421 | 0
[9 empty] | 825 | 34.3421 | 0
[9 empty] | 826 | 34.3421 | 0
[9 empty] | 827 | 34.3421 | 0
[9 empty] | 828 | 34.3421 | 0
[9 empty] | 829 | 34.3421 | 0
[9 empty] | 830 | 34.3421 | 0
[9 empty] | 831 | 34.3421 | 0
[9 empty] | 832 | 34.3421 | 0
[9 empty] | 833 | 34.3421 | 0
[9 empty] | 834 | 34.3421 | 0
[9 empty] | 835 | 34.3421 | 0
[9 empty] | 836 | 34.3421 | 0
[9 empty] | 837 | 34.3421 | 0
[9 empty] | 838 | 34.3421 | 0
[9 empty] | 839 | 34.3421 | 0
[9 empty] | 840 | 34.3421 | 0
[9 empty] | 841 | 34.3421 | 0
[9 empty] | 842 | 34.3421 | 0
[9 empty] | 843 | 34.3421 | 0
[9 empty] | 844 | 34.3421 | 0
[9 empty] | 845 | 34.3421 | 0
[9 empty] | 846 | 34.3421 | 0
[9 empty] | 847 | 34.3421 | 0
[9 empty] | 848 | 34.3421 | 0
[9 empty] | 849 | 34.3421 | 0
[9 empty] | 850 | 34.3421 | 0
[9 empty] | 851 | 34.3421 | 0
[9 empty] | 852 | 34.3421 | 0
[9 empty] | 853 | 34.3421 | 0
[9 empty] | 854 | 34.3421 | 0
[9 empty] | 855 | 34.3421 | 0
[9 empty] | 856 | 34.3421 | 0
[9 empty] | 857 | 34.3421 | 0
[9 empty] | 858 | 34.3421 | 0
[9 empty] | 859 | 34.3421 | 0
[9 empty] | 860 | 34.3421 | 0
[9 empty] | 861 | 34.3421 | 0
[9 empty] | 862 | 34.3421 | 0
[9 empty] | 863 | 34.3421 | 0
[9 empty] | 864 | 34.3421 | 0
[9 empty] | 865 | 34.3421 | 0
[9 empty] | 866 | 34.3421 | 0
[9 empty] | 867 | 34.3421 | 0
[9 empty] | 868 | 34.3421 | 0
[9 empty] | 869 | 34.3421 | 0
[9 empty] | 870 | 34.3421 | 0
[9 empty] | 871 | 34.3421 | 0
[9 empty] | 872 | 34.3421 | 0
[9 empty] | 873 | 34.3421 | 0
[9 empty] | 874 | 34.3421 | 0
[9 empty] | 875 | 34.3421 | 0
[9 empty] | 876 | 34.3421 | 0
[9 empty] | 877 | 34.3421 | 0
[9 empty] | 878 | 34.3421 | 0
[9 empty] | 879 | 34.3421 | 0
[9 empty] | 880 | 34.3421 | 0
[9 empty] | 881 | 34.3421 | 0
[9 empty] | 882 | 34.3421 | 0
[9 empty] | 883 | 34.3421 | 0
[9 empty] | 884 | 34.3421 | 0
[9 empty] | 885 | 34.3421 | 0
[9 empty] | 886 | 34.3421 | 0
[9 empty] | 887 | 34.3421 | 0
[9 empty] | 888 | 34.3421 | 0
[9 empty] | 889 | 34.3421 | 0
[9 empty] | 890 | 34.3421 | 0
[9 empty] | 891 | 34.3421 | 0
[9 empty] | 892 | 34.3421 | 0
[9 empty] | 893 | 34.3421 | 0
[9 empty] | 894 | 34.3421 | 0
[9 empty] | 895 | 34.3421 | 0
[9 empty] | 896 | 34.3421 | 0
[9 empty] | 897 | 34.3421 | 0
[9 empty] | 898 | 34.3421 | 0
[9 empty] | 899 | 34.3421 | 0
[9 empty] | 900 | 34.3421 | 0
[9 empty] | 901 | 34.3421 | 0
[9 empty] | 902 | 34.3421 | 0
[9 empty] | 903 | 34.3421 | 0
[9 empty] | 904 | 34.3421 | 0
[9 empty] | 905 | 34.3421 | 0
[9 empty] | 906 | 34.3421 | 0
[9 empty] | 907 | 34.3421 | 0
[9 empty] | 908 | 34.3421 | 0
[9 empty] | 909 | 34.3421 | 0
[9 empty] | 910 | 34.3421 | 0
[9 empty] | 911 | 34.3421 | 0
[9 empty] | 912 | 34.3421 | 0
[9 empty] | 913 | 34.3421 | 0
[9 empty] | 914 | 34.3421 | 0
[9 empty] | 915 | 34.3421 | 0
[9 empty] | 916 | 34.3421 | 0
[9 empty] | 917 | 34.3421 | 0
[9 empty] | 918 | 34.3421 | 0
[9 empty] | 919 | 34.3421 | 0
[9 empty] | 920 | 34.3421 | 0
[9 empty] | 921 | 34.3421 | 0
[9 empty] | 922 | 34.3421 | 0
[9 empty] | 923 | 34.3421 | 0
[9 empty] | 924 | 34.3421 | 0
[9 empty] | 925 | 34.3421 | 0
[9 empty] | 926 | 34.3421 | 0
[9 empty] | 927 | 34.3421 | 0
[9 empty] | 928 | 34.3421 | 0
[9 empty] | 929 | 34.3421 | 0
[9 empty] | 930 | 34.3421 | 0
[9 empty] | 931 | 34.3421 | 0
[9 empty] | 932 | 34.3421 | 0
[9 empty] | 933 | 34.3421 | 0
[9 empty] | 934 | 34.3421 | 0
[9 empty] | 935 | 34.3421 | 0
[9 empty] | 936 | 34.3421 | 0
[9 empty] | 937 | 34.3421 | 0
[9 empty] | 938 | 34.3421 | 0
[9 empty] | 939 | 34.3421 | 0
[9 empty] | 940 | 34.3421 | 0
[9 empty] | 941 | 34.3421 | 0
[9 empty] | 942 | 34.3421 | 0
[9 empty] | 943 | 34.3421 | 0
[9 empty] | 944 | 34.3421 | 0
[9 empty] | 945 | 34.3421 | 0
[9 empty] | 946 | 34.3421 | 0
[9 empty] | 947 | 34.3421 | 0
[9 empty] | 948 | 34.3421 | 0
[9 empty] | 949 | 34.3421 | 0
[9 empty] | 950 | 34.3421 | 0
[9 empty] | 951 | 34.3421 | 0
[9 empty] | 952 | 34.3421 | 0
[9 empty] | 953 | 34.3421 | 0
[9 empty] | 954 | 34.3421 | 0
[9 empty] | 955 | 34.3421 | 0
[9 empty] | 956 | 34.3421 | 0
[9 empty] | 957 | 34.3421 | 0
[9 empty] | 958 | 34.3421 | 0
[9 empty] | 959 | 34.3421 | 0
[9 empty] | 960 | 34.3421 | 0
[9 empty] | 961 | 34.3421 | 0
[9 empty] | 962 | 34.3421 | 0
[9 empty] | 963 | 34.3421 | 0
[9 empty] | 964 | 34.3421 | 0
[9 empty] | 965 | 34.3421 | 0
[9 empty] | 966 | 34.3421 | 0
[9 empty] | 967 | 34.3421 | 0
[9 empty] | 968 | 34.3421 | 0
[9 empty] | 969 | 34.3421 | 0
[9 empty] | 970 | 34.3421 | 0
[9 empty] | 971 | 34.3421 | 0
[9 empty] | 972 | 34.3421 | 0
[9 empty] | 973 | 34.3421 | 0
[9 empty] | 974 | 34.3421 | 0
[9 empty] | 975 | 34.3421 | 0
[9 empty] | 976 | 34.3421 | 0
[9 empty] | 977 | 34.3421 | 0
[9 empty] | 978 | 34.3421 | 0
[9 empty] | 979 | 34.3421 | 0
[9 empty] | 980 | 34.3421 | 0
[9 empty] | 981 | 34.3421 | 0
[9 empty] | 982 | 34.3421 | 0
[9 empty] | 983 | 34.3421 | 0
[9 empty] | 984 | 34.3421 | 0
[9 empty] | 985 | 34.3421 | 0
[9 empty] | 986 | 34.3421 | 0
[9 empty] | 987 | 34.3421 | 0
[9 empty] | 988 | 34.3421 | 0
[9 empty] | 989 | 34.3421 | 0
[9 empty] | 990 | 34.3421 | 0
[9 empty] | 991 | 34.3421 | 0
[9 empty] | 992 | 34.3421 | 0
[9 empty] | 993 | 34.3421 | 0
[9 empty] | 994 | 34.3421 | 0
[9 empty] | 995 | 34.3421 | 0
[9 empty] | 996 | 34.3421 | 0
[9 empty] | 997 | 34.3421 | 0
[9 empty] | 998 | 34.3421 | 0
[9 empty] | 999 | 34.3421 | 0
[9 empty] | 1000 | 34.3421 | 0

## Project-1 LT(a,b)
Project 1 | [8 empty] | Trial | Project Duration | Success
Task | Immediate Ancestor | a | m | b | Start Time | U(0,1) | Duration | Finsih Time |  | 38.2705 | 0
A |  | 5 | 6 | 8 | 0 | 0.29252 | 5.8775 | 5.8775 | 1 | 38.2705 | 0
B |  | 1 | 3 | 4 | 0 | 0.86229 | 3.5869 | 3.5869 | 2 | 38.2705 | 0
C |  | 2 | 4 | 5 | 0 | 0.39062 | 4.9632 | 4.9632 | 3 | 38.2705 | 0
D | A | 4 | 5 | 6 | 5.8775 | 0.75291 | 5.5058 | 11.3834 | 4 | 38.2705 | 0
E | A | 7 | 8 | 10 | 5.8775 | 0.32745 | 8.073 | 13.9505 | 5 | 38.2705 | 0
F | A | 8 | 9 | 13 | 5.8775 | 0.44937 | 11.8792 | 17.7568 | 6 | 38.2705 | 0
G | D | 5 | 9 | 19 | 11.3834 | 0.23222 | 15.8913 | 27.2746 | 7 | 38.2705 | 0
H | D | 3 | 4 | 5 | 11.3834 | 0.96273 | 4.9255 | 16.3088 | 8 | 38.2705 | 0
I | B,G | 4 | 8 | 10 | 27.2746 | 0.49164 | 6.9498 | 34.2244 | 9 | 38.2705 | 0
J | B,G | 5 | 6 | 8 | 27.2746 | 0.89651 | 7.7196 | 34.9943 | 10 | 38.2705 | 0
K | C,E | 9 | 10 | 15 | 13.9505 | 0.93041 | 14.5824 | 28.533 | 11 | 38.2705 | 0
L | C,E | 4 | 6 | 8 | 13.9505 | 0.83028 | 7.3211 | 21.2717 | 12 | 38.2705 | 0
M | F,H,I,K | 3 | 4 | 5 | 34.2244 | 0.52302 | 4.046 | 38.2705 | 13 | 38.2705 | 0
N | J,L,M | 0 | 0 | 0 | 38.2705 | 0.70166 | 0 | 38.2705 | 14 | 38.2705 | 0
[9 empty] | 15 | 38.2705 | 0
[9 empty] | 16 | 38.2705 | 0
[9 empty] | 17 | 38.2705 | 0
[9 empty] | 18 | 38.2705 | 0
Deadline | Average Project Duration | Avg Success Rate | [6 empty] | 19 | 38.2705 | 0
32 | 38.2705 | 0 | [6 empty] | 20 | 38.2705 | 0
[9 empty] | 21 | 38.2705 | 0
[9 empty] | 22 | 38.2705 | 0
[9 empty] | 23 | 38.2705 | 0
[9 empty] | 24 | 38.2705 | 0
[9 empty] | 25 | 38.2705 | 0
[9 empty] | 26 | 38.2705 | 0
[9 empty] | 27 | 38.2705 | 0
[9 empty] | 28 | 38.2705 | 0
[9 empty] | 29 | 38.2705 | 0
[9 empty] | 30 | 38.2705 | 0
[9 empty] | 31 | 38.2705 | 0
[9 empty] | 32 | 38.2705 | 0
[9 empty] | 33 | 38.2705 | 0
[9 empty] | 34 | 38.2705 | 0
[9 empty] | 35 | 38.2705 | 0
[9 empty] | 36 | 38.2705 | 0
[9 empty] | 37 | 38.2705 | 0
[9 empty] | 38 | 38.2705 | 0
[9 empty] | 39 | 38.2705 | 0
[9 empty] | 40 | 38.2705 | 0
[9 empty] | 41 | 38.2705 | 0
[9 empty] | 42 | 38.2705 | 0
[9 empty] | 43 | 38.2705 | 0
[9 empty] | 44 | 38.2705 | 0
[9 empty] | 45 | 38.2705 | 0
[9 empty] | 46 | 38.2705 | 0
[9 empty] | 47 | 38.2705 | 0
[9 empty] | 48 | 38.2705 | 0
[9 empty] | 49 | 38.2705 | 0
[9 empty] | 50 | 38.2705 | 0
[9 empty] | 51 | 38.2705 | 0
[9 empty] | 52 | 38.2705 | 0
[9 empty] | 53 | 38.2705 | 0
[9 empty] | 54 | 38.2705 | 0
[9 empty] | 55 | 38.2705 | 0
[9 empty] | 56 | 38.2705 | 0
[9 empty] | 57 | 38.2705 | 0
[9 empty] | 58 | 38.2705 | 0
[9 empty] | 59 | 38.2705 | 0
[9 empty] | 60 | 38.2705 | 0
[9 empty] | 61 | 38.2705 | 0
[9 empty] | 62 | 38.2705 | 0
[9 empty] | 63 | 38.2705 | 0
[9 empty] | 64 | 38.2705 | 0
[9 empty] | 65 | 38.2705 | 0
[9 empty] | 66 | 38.2705 | 0
[9 empty] | 67 | 38.2705 | 0
[9 empty] | 68 | 38.2705 | 0
[9 empty] | 69 | 38.2705 | 0
[9 empty] | 70 | 38.2705 | 0
[9 empty] | 71 | 38.2705 | 0
[9 empty] | 72 | 38.2705 | 0
[9 empty] | 73 | 38.2705 | 0
[9 empty] | 74 | 38.2705 | 0
[9 empty] | 75 | 38.2705 | 0
[9 empty] | 76 | 38.2705 | 0
[9 empty] | 77 | 38.2705 | 0
[9 empty] | 78 | 38.2705 | 0
[9 empty] | 79 | 38.2705 | 0
[9 empty] | 80 | 38.2705 | 0
[9 empty] | 81 | 38.2705 | 0
[9 empty] | 82 | 38.2705 | 0
[9 empty] | 83 | 38.2705 | 0
[9 empty] | 84 | 38.2705 | 0
[9 empty] | 85 | 38.2705 | 0
[9 empty] | 86 | 38.2705 | 0
[9 empty] | 87 | 38.2705 | 0
[9 empty] | 88 | 38.2705 | 0
[9 empty] | 89 | 38.2705 | 0
[9 empty] | 90 | 38.2705 | 0
[9 empty] | 91 | 38.2705 | 0
[9 empty] | 92 | 38.2705 | 0
[9 empty] | 93 | 38.2705 | 0
[9 empty] | 94 | 38.2705 | 0
[9 empty] | 95 | 38.2705 | 0
[9 empty] | 96 | 38.2705 | 0
[9 empty] | 97 | 38.2705 | 0
[9 empty] | 98 | 38.2705 | 0
[9 empty] | 99 | 38.2705 | 0
[9 empty] | 100 | 38.2705 | 0
[9 empty] | 101 | 38.2705 | 0
[9 empty] | 102 | 38.2705 | 0
[9 empty] | 103 | 38.2705 | 0
[9 empty] | 104 | 38.2705 | 0
[9 empty] | 105 | 38.2705 | 0
[9 empty] | 106 | 38.2705 | 0
[9 empty] | 107 | 38.2705 | 0
[9 empty] | 108 | 38.2705 | 0
[9 empty] | 109 | 38.2705 | 0
[9 empty] | 110 | 38.2705 | 0
[9 empty] | 111 | 38.2705 | 0
[9 empty] | 112 | 38.2705 | 0
[9 empty] | 113 | 38.2705 | 0
[9 empty] | 114 | 38.2705 | 0
[9 empty] | 115 | 38.2705 | 0
[9 empty] | 116 | 38.2705 | 0
[9 empty] | 117 | 38.2705 | 0
[9 empty] | 118 | 38.2705 | 0
[9 empty] | 119 | 38.2705 | 0
[9 empty] | 120 | 38.2705 | 0
[9 empty] | 121 | 38.2705 | 0
[9 empty] | 122 | 38.2705 | 0
[9 empty] | 123 | 38.2705 | 0
[9 empty] | 124 | 38.2705 | 0
[9 empty] | 125 | 38.2705 | 0
[9 empty] | 126 | 38.2705 | 0
[9 empty] | 127 | 38.2705 | 0
[9 empty] | 128 | 38.2705 | 0
[9 empty] | 129 | 38.2705 | 0
[9 empty] | 130 | 38.2705 | 0
[9 empty] | 131 | 38.2705 | 0
[9 empty] | 132 | 38.2705 | 0
[9 empty] | 133 | 38.2705 | 0
[9 empty] | 134 | 38.2705 | 0
[9 empty] | 135 | 38.2705 | 0
[9 empty] | 136 | 38.2705 | 0
[9 empty] | 137 | 38.2705 | 0
[9 empty] | 138 | 38.2705 | 0
[9 empty] | 139 | 38.2705 | 0
[9 empty] | 140 | 38.2705 | 0
[9 empty] | 141 | 38.2705 | 0
[9 empty] | 142 | 38.2705 | 0
[9 empty] | 143 | 38.2705 | 0
[9 empty] | 144 | 38.2705 | 0
[9 empty] | 145 | 38.2705 | 0
[9 empty] | 146 | 38.2705 | 0
[9 empty] | 147 | 38.2705 | 0
[9 empty] | 148 | 38.2705 | 0
[9 empty] | 149 | 38.2705 | 0
[9 empty] | 150 | 38.2705 | 0
[9 empty] | 151 | 38.2705 | 0
[9 empty] | 152 | 38.2705 | 0
[9 empty] | 153 | 38.2705 | 0
[9 empty] | 154 | 38.2705 | 0
[9 empty] | 155 | 38.2705 | 0
[9 empty] | 156 | 38.2705 | 0
[9 empty] | 157 | 38.2705 | 0
[9 empty] | 158 | 38.2705 | 0
[9 empty] | 159 | 38.2705 | 0
[9 empty] | 160 | 38.2705 | 0
[9 empty] | 161 | 38.2705 | 0
[9 empty] | 162 | 38.2705 | 0
[9 empty] | 163 | 38.2705 | 0
[9 empty] | 164 | 38.2705 | 0
[9 empty] | 165 | 38.2705 | 0
[9 empty] | 166 | 38.2705 | 0
[9 empty] | 167 | 38.2705 | 0
[9 empty] | 168 | 38.2705 | 0
[9 empty] | 169 | 38.2705 | 0
[9 empty] | 170 | 38.2705 | 0
[9 empty] | 171 | 38.2705 | 0
[9 empty] | 172 | 38.2705 | 0
[9 empty] | 173 | 38.2705 | 0
[9 empty] | 174 | 38.2705 | 0
[9 empty] | 175 | 38.2705 | 0
[9 empty] | 176 | 38.2705 | 0
[9 empty] | 177 | 38.2705 | 0
[9 empty] | 178 | 38.2705 | 0
[9 empty] | 179 | 38.2705 | 0
[9 empty] | 180 | 38.2705 | 0
[9 empty] | 181 | 38.2705 | 0
[9 empty] | 182 | 38.2705 | 0
[9 empty] | 183 | 38.2705 | 0
[9 empty] | 184 | 38.2705 | 0
[9 empty] | 185 | 38.2705 | 0
[9 empty] | 186 | 38.2705 | 0
[9 empty] | 187 | 38.2705 | 0
[9 empty] | 188 | 38.2705 | 0
[9 empty] | 189 | 38.2705 | 0
[9 empty] | 190 | 38.2705 | 0
[9 empty] | 191 | 38.2705 | 0
[9 empty] | 192 | 38.2705 | 0
[9 empty] | 193 | 38.2705 | 0
[9 empty] | 194 | 38.2705 | 0
[9 empty] | 195 | 38.2705 | 0
[9 empty] | 196 | 38.2705 | 0
[9 empty] | 197 | 38.2705 | 0
[9 empty] | 198 | 38.2705 | 0
[9 empty] | 199 | 38.2705 | 0
[9 empty] | 200 | 38.2705 | 0
[9 empty] | 201 | 38.2705 | 0
[9 empty] | 202 | 38.2705 | 0
[9 empty] | 203 | 38.2705 | 0
[9 empty] | 204 | 38.2705 | 0
[9 empty] | 205 | 38.2705 | 0
[9 empty] | 206 | 38.2705 | 0
[9 empty] | 207 | 38.2705 | 0
[9 empty] | 208 | 38.2705 | 0
[9 empty] | 209 | 38.2705 | 0
[9 empty] | 210 | 38.2705 | 0
[9 empty] | 211 | 38.2705 | 0
[9 empty] | 212 | 38.2705 | 0
[9 empty] | 213 | 38.2705 | 0
[9 empty] | 214 | 38.2705 | 0
[9 empty] | 215 | 38.2705 | 0
[9 empty] | 216 | 38.2705 | 0
[9 empty] | 217 | 38.2705 | 0
[9 empty] | 218 | 38.2705 | 0
[9 empty] | 219 | 38.2705 | 0
[9 empty] | 220 | 38.2705 | 0
[9 empty] | 221 | 38.2705 | 0
[9 empty] | 222 | 38.2705 | 0
[9 empty] | 223 | 38.2705 | 0
[9 empty] | 224 | 38.2705 | 0
[9 empty] | 225 | 38.2705 | 0
[9 empty] | 226 | 38.2705 | 0
[9 empty] | 227 | 38.2705 | 0
[9 empty] | 228 | 38.2705 | 0
[9 empty] | 229 | 38.2705 | 0
[9 empty] | 230 | 38.2705 | 0
[9 empty] | 231 | 38.2705 | 0
[9 empty] | 232 | 38.2705 | 0
[9 empty] | 233 | 38.2705 | 0
[9 empty] | 234 | 38.2705 | 0
[9 empty] | 235 | 38.2705 | 0
[9 empty] | 236 | 38.2705 | 0
[9 empty] | 237 | 38.2705 | 0
[9 empty] | 238 | 38.2705 | 0
[9 empty] | 239 | 38.2705 | 0
[9 empty] | 240 | 38.2705 | 0
[9 empty] | 241 | 38.2705 | 0
[9 empty] | 242 | 38.2705 | 0
[9 empty] | 243 | 38.2705 | 0
[9 empty] | 244 | 38.2705 | 0
[9 empty] | 245 | 38.2705 | 0
[9 empty] | 246 | 38.2705 | 0
[9 empty] | 247 | 38.2705 | 0
[9 empty] | 248 | 38.2705 | 0
[9 empty] | 249 | 38.2705 | 0
[9 empty] | 250 | 38.2705 | 0
[9 empty] | 251 | 38.2705 | 0
[9 empty] | 252 | 38.2705 | 0
[9 empty] | 253 | 38.2705 | 0
[9 empty] | 254 | 38.2705 | 0
[9 empty] | 255 | 38.2705 | 0
[9 empty] | 256 | 38.2705 | 0
[9 empty] | 257 | 38.2705 | 0
[9 empty] | 258 | 38.2705 | 0
[9 empty] | 259 | 38.2705 | 0
[9 empty] | 260 | 38.2705 | 0
[9 empty] | 261 | 38.2705 | 0
[9 empty] | 262 | 38.2705 | 0
[9 empty] | 263 | 38.2705 | 0
[9 empty] | 264 | 38.2705 | 0
[9 empty] | 265 | 38.2705 | 0
[9 empty] | 266 | 38.2705 | 0
[9 empty] | 267 | 38.2705 | 0
[9 empty] | 268 | 38.2705 | 0
[9 empty] | 269 | 38.2705 | 0
[9 empty] | 270 | 38.2705 | 0
[9 empty] | 271 | 38.2705 | 0
[9 empty] | 272 | 38.2705 | 0
[9 empty] | 273 | 38.2705 | 0
[9 empty] | 274 | 38.2705 | 0
[9 empty] | 275 | 38.2705 | 0
[9 empty] | 276 | 38.2705 | 0
[9 empty] | 277 | 38.2705 | 0
[9 empty] | 278 | 38.2705 | 0
[9 empty] | 279 | 38.2705 | 0
[9 empty] | 280 | 38.2705 | 0
[9 empty] | 281 | 38.2705 | 0
[9 empty] | 282 | 38.2705 | 0
[9 empty] | 283 | 38.2705 | 0
[9 empty] | 284 | 38.2705 | 0
[9 empty] | 285 | 38.2705 | 0
[9 empty] | 286 | 38.2705 | 0
[9 empty] | 287 | 38.2705 | 0
[9 empty] | 288 | 38.2705 | 0
[9 empty] | 289 | 38.2705 | 0
[9 empty] | 290 | 38.2705 | 0
[9 empty] | 291 | 38.2705 | 0
[9 empty] | 292 | 38.2705 | 0
[9 empty] | 293 | 38.2705 | 0
[9 empty] | 294 | 38.2705 | 0
[9 empty] | 295 | 38.2705 | 0
[9 empty] | 296 | 38.2705 | 0
[9 empty] | 297 | 38.2705 | 0
[9 empty] | 298 | 38.2705 | 0
[9 empty] | 299 | 38.2705 | 0
[9 empty] | 300 | 38.2705 | 0
[9 empty] | 301 | 38.2705 | 0
[9 empty] | 302 | 38.2705 | 0
[9 empty] | 303 | 38.2705 | 0
[9 empty] | 304 | 38.2705 | 0
[9 empty] | 305 | 38.2705 | 0
[9 empty] | 306 | 38.2705 | 0
[9 empty] | 307 | 38.2705 | 0
[9 empty] | 308 | 38.2705 | 0
[9 empty] | 309 | 38.2705 | 0
[9 empty] | 310 | 38.2705 | 0
[9 empty] | 311 | 38.2705 | 0
[9 empty] | 312 | 38.2705 | 0
[9 empty] | 313 | 38.2705 | 0
[9 empty] | 314 | 38.2705 | 0
[9 empty] | 315 | 38.2705 | 0
[9 empty] | 316 | 38.2705 | 0
[9 empty] | 317 | 38.2705 | 0
[9 empty] | 318 | 38.2705 | 0
[9 empty] | 319 | 38.2705 | 0
[9 empty] | 320 | 38.2705 | 0
[9 empty] | 321 | 38.2705 | 0
[9 empty] | 322 | 38.2705 | 0
[9 empty] | 323 | 38.2705 | 0
[9 empty] | 324 | 38.2705 | 0
[9 empty] | 325 | 38.2705 | 0
[9 empty] | 326 | 38.2705 | 0
[9 empty] | 327 | 38.2705 | 0
[9 empty] | 328 | 38.2705 | 0
[9 empty] | 329 | 38.2705 | 0
[9 empty] | 330 | 38.2705 | 0
[9 empty] | 331 | 38.2705 | 0
[9 empty] | 332 | 38.2705 | 0
[9 empty] | 333 | 38.2705 | 0
[9 empty] | 334 | 38.2705 | 0
[9 empty] | 335 | 38.2705 | 0
[9 empty] | 336 | 38.2705 | 0
[9 empty] | 337 | 38.2705 | 0
[9 empty] | 338 | 38.2705 | 0
[9 empty] | 339 | 38.2705 | 0
[9 empty] | 340 | 38.2705 | 0
[9 empty] | 341 | 38.2705 | 0
[9 empty] | 342 | 38.2705 | 0
[9 empty] | 343 | 38.2705 | 0
[9 empty] | 344 | 38.2705 | 0
[9 empty] | 345 | 38.2705 | 0
[9 empty] | 346 | 38.2705 | 0
[9 empty] | 347 | 38.2705 | 0
[9 empty] | 348 | 38.2705 | 0
[9 empty] | 349 | 38.2705 | 0
[9 empty] | 350 | 38.2705 | 0
[9 empty] | 351 | 38.2705 | 0
[9 empty] | 352 | 38.2705 | 0
[9 empty] | 353 | 38.2705 | 0
[9 empty] | 354 | 38.2705 | 0
[9 empty] | 355 | 38.2705 | 0
[9 empty] | 356 | 38.2705 | 0
[9 empty] | 357 | 38.2705 | 0
[9 empty] | 358 | 38.2705 | 0
[9 empty] | 359 | 38.2705 | 0
[9 empty] | 360 | 38.2705 | 0
[9 empty] | 361 | 38.2705 | 0
[9 empty] | 362 | 38.2705 | 0
[9 empty] | 363 | 38.2705 | 0
[9 empty] | 364 | 38.2705 | 0
[9 empty] | 365 | 38.2705 | 0
[9 empty] | 366 | 38.2705 | 0
[9 empty] | 367 | 38.2705 | 0
[9 empty] | 368 | 38.2705 | 0
[9 empty] | 369 | 38.2705 | 0
[9 empty] | 370 | 38.2705 | 0
[9 empty] | 371 | 38.2705 | 0
[9 empty] | 372 | 38.2705 | 0
[9 empty] | 373 | 38.2705 | 0
[9 empty] | 374 | 38.2705 | 0
[9 empty] | 375 | 38.2705 | 0
[9 empty] | 376 | 38.2705 | 0
[9 empty] | 377 | 38.2705 | 0
[9 empty] | 378 | 38.2705 | 0
[9 empty] | 379 | 38.2705 | 0
[9 empty] | 380 | 38.2705 | 0
[9 empty] | 381 | 38.2705 | 0
[9 empty] | 382 | 38.2705 | 0
[9 empty] | 383 | 38.2705 | 0
[9 empty] | 384 | 38.2705 | 0
[9 empty] | 385 | 38.2705 | 0
[9 empty] | 386 | 38.2705 | 0
[9 empty] | 387 | 38.2705 | 0
[9 empty] | 388 | 38.2705 | 0
[9 empty] | 389 | 38.2705 | 0
[9 empty] | 390 | 38.2705 | 0
[9 empty] | 391 | 38.2705 | 0
[9 empty] | 392 | 38.2705 | 0
[9 empty] | 393 | 38.2705 | 0
[9 empty] | 394 | 38.2705 | 0
[9 empty] | 395 | 38.2705 | 0
[9 empty] | 396 | 38.2705 | 0
[9 empty] | 397 | 38.2705 | 0
[9 empty] | 398 | 38.2705 | 0
[9 empty] | 399 | 38.2705 | 0
[9 empty] | 400 | 38.2705 | 0
[9 empty] | 401 | 38.2705 | 0
[9 empty] | 402 | 38.2705 | 0
[9 empty] | 403 | 38.2705 | 0
[9 empty] | 404 | 38.2705 | 0
[9 empty] | 405 | 38.2705 | 0
[9 empty] | 406 | 38.2705 | 0
[9 empty] | 407 | 38.2705 | 0
[9 empty] | 408 | 38.2705 | 0
[9 empty] | 409 | 38.2705 | 0
[9 empty] | 410 | 38.2705 | 0
[9 empty] | 411 | 38.2705 | 0
[9 empty] | 412 | 38.2705 | 0
[9 empty] | 413 | 38.2705 | 0
[9 empty] | 414 | 38.2705 | 0
[9 empty] | 415 | 38.2705 | 0
[9 empty] | 416 | 38.2705 | 0
[9 empty] | 417 | 38.2705 | 0
[9 empty] | 418 | 38.2705 | 0
[9 empty] | 419 | 38.2705 | 0
[9 empty] | 420 | 38.2705 | 0
[9 empty] | 421 | 38.2705 | 0
[9 empty] | 422 | 38.2705 | 0
[9 empty] | 423 | 38.2705 | 0
[9 empty] | 424 | 38.2705 | 0
[9 empty] | 425 | 38.2705 | 0
[9 empty] | 426 | 38.2705 | 0
[9 empty] | 427 | 38.2705 | 0
[9 empty] | 428 | 38.2705 | 0
[9 empty] | 429 | 38.2705 | 0
[9 empty] | 430 | 38.2705 | 0
[9 empty] | 431 | 38.2705 | 0
[9 empty] | 432 | 38.2705 | 0
[9 empty] | 433 | 38.2705 | 0
[9 empty] | 434 | 38.2705 | 0
[9 empty] | 435 | 38.2705 | 0
[9 empty] | 436 | 38.2705 | 0
[9 empty] | 437 | 38.2705 | 0
[9 empty] | 438 | 38.2705 | 0
[9 empty] | 439 | 38.2705 | 0
[9 empty] | 440 | 38.2705 | 0
[9 empty] | 441 | 38.2705 | 0
[9 empty] | 442 | 38.2705 | 0
[9 empty] | 443 | 38.2705 | 0
[9 empty] | 444 | 38.2705 | 0
[9 empty] | 445 | 38.2705 | 0
[9 empty] | 446 | 38.2705 | 0
[9 empty] | 447 | 38.2705 | 0
[9 empty] | 448 | 38.2705 | 0
[9 empty] | 449 | 38.2705 | 0
[9 empty] | 450 | 38.2705 | 0
[9 empty] | 451 | 38.2705 | 0
[9 empty] | 452 | 38.2705 | 0
[9 empty] | 453 | 38.2705 | 0
[9 empty] | 454 | 38.2705 | 0
[9 empty] | 455 | 38.2705 | 0
[9 empty] | 456 | 38.2705 | 0
[9 empty] | 457 | 38.2705 | 0
[9 empty] | 458 | 38.2705 | 0
[9 empty] | 459 | 38.2705 | 0
[9 empty] | 460 | 38.2705 | 0
[9 empty] | 461 | 38.2705 | 0
[9 empty] | 462 | 38.2705 | 0
[9 empty] | 463 | 38.2705 | 0
[9 empty] | 464 | 38.2705 | 0
[9 empty] | 465 | 38.2705 | 0
[9 empty] | 466 | 38.2705 | 0
[9 empty] | 467 | 38.2705 | 0
[9 empty] | 468 | 38.2705 | 0
[9 empty] | 469 | 38.2705 | 0
[9 empty] | 470 | 38.2705 | 0
[9 empty] | 471 | 38.2705 | 0
[9 empty] | 472 | 38.2705 | 0
[9 empty] | 473 | 38.2705 | 0
[9 empty] | 474 | 38.2705 | 0
[9 empty] | 475 | 38.2705 | 0
[9 empty] | 476 | 38.2705 | 0
[9 empty] | 477 | 38.2705 | 0
[9 empty] | 478 | 38.2705 | 0
[9 empty] | 479 | 38.2705 | 0
[9 empty] | 480 | 38.2705 | 0
[9 empty] | 481 | 38.2705 | 0
[9 empty] | 482 | 38.2705 | 0
[9 empty] | 483 | 38.2705 | 0
[9 empty] | 484 | 38.2705 | 0
[9 empty] | 485 | 38.2705 | 0
[9 empty] | 486 | 38.2705 | 0
[9 empty] | 487 | 38.2705 | 0
[9 empty] | 488 | 38.2705 | 0
[9 empty] | 489 | 38.2705 | 0
[9 empty] | 490 | 38.2705 | 0
[9 empty] | 491 | 38.2705 | 0
[9 empty] | 492 | 38.2705 | 0
[9 empty] | 493 | 38.2705 | 0
[9 empty] | 494 | 38.2705 | 0
[9 empty] | 495 | 38.2705 | 0
[9 empty] | 496 | 38.2705 | 0
[9 empty] | 497 | 38.2705 | 0
[9 empty] | 498 | 38.2705 | 0
[9 empty] | 499 | 38.2705 | 0
[9 empty] | 500 | 38.2705 | 0
[9 empty] | 501 | 38.2705 | 0
[9 empty] | 502 | 38.2705 | 0
[9 empty] | 503 | 38.2705 | 0
[9 empty] | 504 | 38.2705 | 0
[9 empty] | 505 | 38.2705 | 0
[9 empty] | 506 | 38.2705 | 0
[9 empty] | 507 | 38.2705 | 0
[9 empty] | 508 | 38.2705 | 0
[9 empty] | 509 | 38.2705 | 0
[9 empty] | 510 | 38.2705 | 0
[9 empty] | 511 | 38.2705 | 0
[9 empty] | 512 | 38.2705 | 0
[9 empty] | 513 | 38.2705 | 0
[9 empty] | 514 | 38.2705 | 0
[9 empty] | 515 | 38.2705 | 0
[9 empty] | 516 | 38.2705 | 0
[9 empty] | 517 | 38.2705 | 0
[9 empty] | 518 | 38.2705 | 0
[9 empty] | 519 | 38.2705 | 0
[9 empty] | 520 | 38.2705 | 0
[9 empty] | 521 | 38.2705 | 0
[9 empty] | 522 | 38.2705 | 0
[9 empty] | 523 | 38.2705 | 0
[9 empty] | 524 | 38.2705 | 0
[9 empty] | 525 | 38.2705 | 0
[9 empty] | 526 | 38.2705 | 0
[9 empty] | 527 | 38.2705 | 0
[9 empty] | 528 | 38.2705 | 0
[9 empty] | 529 | 38.2705 | 0
[9 empty] | 530 | 38.2705 | 0
[9 empty] | 531 | 38.2705 | 0
[9 empty] | 532 | 38.2705 | 0
[9 empty] | 533 | 38.2705 | 0
[9 empty] | 534 | 38.2705 | 0
[9 empty] | 535 | 38.2705 | 0
[9 empty] | 536 | 38.2705 | 0
[9 empty] | 537 | 38.2705 | 0
[9 empty] | 538 | 38.2705 | 0
[9 empty] | 539 | 38.2705 | 0
[9 empty] | 540 | 38.2705 | 0
[9 empty] | 541 | 38.2705 | 0
[9 empty] | 542 | 38.2705 | 0
[9 empty] | 543 | 38.2705 | 0
[9 empty] | 544 | 38.2705 | 0
[9 empty] | 545 | 38.2705 | 0
[9 empty] | 546 | 38.2705 | 0
[9 empty] | 547 | 38.2705 | 0
[9 empty] | 548 | 38.2705 | 0
[9 empty] | 549 | 38.2705 | 0
[9 empty] | 550 | 38.2705 | 0
[9 empty] | 551 | 38.2705 | 0
[9 empty] | 552 | 38.2705 | 0
[9 empty] | 553 | 38.2705 | 0
[9 empty] | 554 | 38.2705 | 0
[9 empty] | 555 | 38.2705 | 0
[9 empty] | 556 | 38.2705 | 0
[9 empty] | 557 | 38.2705 | 0
[9 empty] | 558 | 38.2705 | 0
[9 empty] | 559 | 38.2705 | 0
[9 empty] | 560 | 38.2705 | 0
[9 empty] | 561 | 38.2705 | 0
[9 empty] | 562 | 38.2705 | 0
[9 empty] | 563 | 38.2705 | 0
[9 empty] | 564 | 38.2705 | 0
[9 empty] | 565 | 38.2705 | 0
[9 empty] | 566 | 38.2705 | 0
[9 empty] | 567 | 38.2705 | 0
[9 empty] | 568 | 38.2705 | 0
[9 empty] | 569 | 38.2705 | 0
[9 empty] | 570 | 38.2705 | 0
[9 empty] | 571 | 38.2705 | 0
[9 empty] | 572 | 38.2705 | 0
[9 empty] | 573 | 38.2705 | 0
[9 empty] | 574 | 38.2705 | 0
[9 empty] | 575 | 38.2705 | 0
[9 empty] | 576 | 38.2705 | 0
[9 empty] | 577 | 38.2705 | 0
[9 empty] | 578 | 38.2705 | 0
[9 empty] | 579 | 38.2705 | 0
[9 empty] | 580 | 38.2705 | 0
[9 empty] | 581 | 38.2705 | 0
[9 empty] | 582 | 38.2705 | 0
[9 empty] | 583 | 38.2705 | 0
[9 empty] | 584 | 38.2705 | 0
[9 empty] | 585 | 38.2705 | 0
[9 empty] | 586 | 38.2705 | 0
[9 empty] | 587 | 38.2705 | 0
[9 empty] | 588 | 38.2705 | 0
[9 empty] | 589 | 38.2705 | 0
[9 empty] | 590 | 38.2705 | 0
[9 empty] | 591 | 38.2705 | 0
[9 empty] | 592 | 38.2705 | 0
[9 empty] | 593 | 38.2705 | 0
[9 empty] | 594 | 38.2705 | 0
[9 empty] | 595 | 38.2705 | 0
[9 empty] | 596 | 38.2705 | 0
[9 empty] | 597 | 38.2705 | 0
[9 empty] | 598 | 38.2705 | 0
[9 empty] | 599 | 38.2705 | 0
[9 empty] | 600 | 38.2705 | 0
[9 empty] | 601 | 38.2705 | 0
[9 empty] | 602 | 38.2705 | 0
[9 empty] | 603 | 38.2705 | 0
[9 empty] | 604 | 38.2705 | 0
[9 empty] | 605 | 38.2705 | 0
[9 empty] | 606 | 38.2705 | 0
[9 empty] | 607 | 38.2705 | 0
[9 empty] | 608 | 38.2705 | 0
[9 empty] | 609 | 38.2705 | 0
[9 empty] | 610 | 38.2705 | 0
[9 empty] | 611 | 38.2705 | 0
[9 empty] | 612 | 38.2705 | 0
[9 empty] | 613 | 38.2705 | 0
[9 empty] | 614 | 38.2705 | 0
[9 empty] | 615 | 38.2705 | 0
[9 empty] | 616 | 38.2705 | 0
[9 empty] | 617 | 38.2705 | 0
[9 empty] | 618 | 38.2705 | 0
[9 empty] | 619 | 38.2705 | 0
[9 empty] | 620 | 38.2705 | 0
[9 empty] | 621 | 38.2705 | 0
[9 empty] | 622 | 38.2705 | 0
[9 empty] | 623 | 38.2705 | 0
[9 empty] | 624 | 38.2705 | 0
[9 empty] | 625 | 38.2705 | 0
[9 empty] | 626 | 38.2705 | 0
[9 empty] | 627 | 38.2705 | 0
[9 empty] | 628 | 38.2705 | 0
[9 empty] | 629 | 38.2705 | 0
[9 empty] | 630 | 38.2705 | 0
[9 empty] | 631 | 38.2705 | 0
[9 empty] | 632 | 38.2705 | 0
[9 empty] | 633 | 38.2705 | 0
[9 empty] | 634 | 38.2705 | 0
[9 empty] | 635 | 38.2705 | 0
[9 empty] | 636 | 38.2705 | 0
[9 empty] | 637 | 38.2705 | 0
[9 empty] | 638 | 38.2705 | 0
[9 empty] | 639 | 38.2705 | 0
[9 empty] | 640 | 38.2705 | 0
[9 empty] | 641 | 38.2705 | 0
[9 empty] | 642 | 38.2705 | 0
[9 empty] | 643 | 38.2705 | 0
[9 empty] | 644 | 38.2705 | 0
[9 empty] | 645 | 38.2705 | 0
[9 empty] | 646 | 38.2705 | 0
[9 empty] | 647 | 38.2705 | 0
[9 empty] | 648 | 38.2705 | 0
[9 empty] | 649 | 38.2705 | 0
[9 empty] | 650 | 38.2705 | 0
[9 empty] | 651 | 38.2705 | 0
[9 empty] | 652 | 38.2705 | 0
[9 empty] | 653 | 38.2705 | 0
[9 empty] | 654 | 38.2705 | 0
[9 empty] | 655 | 38.2705 | 0
[9 empty] | 656 | 38.2705 | 0
[9 empty] | 657 | 38.2705 | 0
[9 empty] | 658 | 38.2705 | 0
[9 empty] | 659 | 38.2705 | 0
[9 empty] | 660 | 38.2705 | 0
[9 empty] | 661 | 38.2705 | 0
[9 empty] | 662 | 38.2705 | 0
[9 empty] | 663 | 38.2705 | 0
[9 empty] | 664 | 38.2705 | 0
[9 empty] | 665 | 38.2705 | 0
[9 empty] | 666 | 38.2705 | 0
[9 empty] | 667 | 38.2705 | 0
[9 empty] | 668 | 38.2705 | 0
[9 empty] | 669 | 38.2705 | 0
[9 empty] | 670 | 38.2705 | 0
[9 empty] | 671 | 38.2705 | 0
[9 empty] | 672 | 38.2705 | 0
[9 empty] | 673 | 38.2705 | 0
[9 empty] | 674 | 38.2705 | 0
[9 empty] | 675 | 38.2705 | 0
[9 empty] | 676 | 38.2705 | 0
[9 empty] | 677 | 38.2705 | 0
[9 empty] | 678 | 38.2705 | 0
[9 empty] | 679 | 38.2705 | 0
[9 empty] | 680 | 38.2705 | 0
[9 empty] | 681 | 38.2705 | 0
[9 empty] | 682 | 38.2705 | 0
[9 empty] | 683 | 38.2705 | 0
[9 empty] | 684 | 38.2705 | 0
[9 empty] | 685 | 38.2705 | 0
[9 empty] | 686 | 38.2705 | 0
[9 empty] | 687 | 38.2705 | 0
[9 empty] | 688 | 38.2705 | 0
[9 empty] | 689 | 38.2705 | 0
[9 empty] | 690 | 38.2705 | 0
[9 empty] | 691 | 38.2705 | 0
[9 empty] | 692 | 38.2705 | 0
[9 empty] | 693 | 38.2705 | 0
[9 empty] | 694 | 38.2705 | 0
[9 empty] | 695 | 38.2705 | 0
[9 empty] | 696 | 38.2705 | 0
[9 empty] | 697 | 38.2705 | 0
[9 empty] | 698 | 38.2705 | 0
[9 empty] | 699 | 38.2705 | 0
[9 empty] | 700 | 38.2705 | 0
[9 empty] | 701 | 38.2705 | 0
[9 empty] | 702 | 38.2705 | 0
[9 empty] | 703 | 38.2705 | 0
[9 empty] | 704 | 38.2705 | 0
[9 empty] | 705 | 38.2705 | 0
[9 empty] | 706 | 38.2705 | 0
[9 empty] | 707 | 38.2705 | 0
[9 empty] | 708 | 38.2705 | 0
[9 empty] | 709 | 38.2705 | 0
[9 empty] | 710 | 38.2705 | 0
[9 empty] | 711 | 38.2705 | 0
[9 empty] | 712 | 38.2705 | 0
[9 empty] | 713 | 38.2705 | 0
[9 empty] | 714 | 38.2705 | 0
[9 empty] | 715 | 38.2705 | 0
[9 empty] | 716 | 38.2705 | 0
[9 empty] | 717 | 38.2705 | 0
[9 empty] | 718 | 38.2705 | 0
[9 empty] | 719 | 38.2705 | 0
[9 empty] | 720 | 38.2705 | 0
[9 empty] | 721 | 38.2705 | 0
[9 empty] | 722 | 38.2705 | 0
[9 empty] | 723 | 38.2705 | 0
[9 empty] | 724 | 38.2705 | 0
[9 empty] | 725 | 38.2705 | 0
[9 empty] | 726 | 38.2705 | 0
[9 empty] | 727 | 38.2705 | 0
[9 empty] | 728 | 38.2705 | 0
[9 empty] | 729 | 38.2705 | 0
[9 empty] | 730 | 38.2705 | 0
[9 empty] | 731 | 38.2705 | 0
[9 empty] | 732 | 38.2705 | 0
[9 empty] | 733 | 38.2705 | 0
[9 empty] | 734 | 38.2705 | 0
[9 empty] | 735 | 38.2705 | 0
[9 empty] | 736 | 38.2705 | 0
[9 empty] | 737 | 38.2705 | 0
[9 empty] | 738 | 38.2705 | 0
[9 empty] | 739 | 38.2705 | 0
[9 empty] | 740 | 38.2705 | 0
[9 empty] | 741 | 38.2705 | 0
[9 empty] | 742 | 38.2705 | 0
[9 empty] | 743 | 38.2705 | 0
[9 empty] | 744 | 38.2705 | 0
[9 empty] | 745 | 38.2705 | 0
[9 empty] | 746 | 38.2705 | 0
[9 empty] | 747 | 38.2705 | 0
[9 empty] | 748 | 38.2705 | 0
[9 empty] | 749 | 38.2705 | 0
[9 empty] | 750 | 38.2705 | 0
[9 empty] | 751 | 38.2705 | 0
[9 empty] | 752 | 38.2705 | 0
[9 empty] | 753 | 38.2705 | 0
[9 empty] | 754 | 38.2705 | 0
[9 empty] | 755 | 38.2705 | 0
[9 empty] | 756 | 38.2705 | 0
[9 empty] | 757 | 38.2705 | 0
[9 empty] | 758 | 38.2705 | 0
[9 empty] | 759 | 38.2705 | 0
[9 empty] | 760 | 38.2705 | 0
[9 empty] | 761 | 38.2705 | 0
[9 empty] | 762 | 38.2705 | 0
[9 empty] | 763 | 38.2705 | 0
[9 empty] | 764 | 38.2705 | 0
[9 empty] | 765 | 38.2705 | 0
[9 empty] | 766 | 38.2705 | 0
[9 empty] | 767 | 38.2705 | 0
[9 empty] | 768 | 38.2705 | 0
[9 empty] | 769 | 38.2705 | 0
[9 empty] | 770 | 38.2705 | 0
[9 empty] | 771 | 38.2705 | 0
[9 empty] | 772 | 38.2705 | 0
[9 empty] | 773 | 38.2705 | 0
[9 empty] | 774 | 38.2705 | 0
[9 empty] | 775 | 38.2705 | 0
[9 empty] | 776 | 38.2705 | 0
[9 empty] | 777 | 38.2705 | 0
[9 empty] | 778 | 38.2705 | 0
[9 empty] | 779 | 38.2705 | 0
[9 empty] | 780 | 38.2705 | 0
[9 empty] | 781 | 38.2705 | 0
[9 empty] | 782 | 38.2705 | 0
[9 empty] | 783 | 38.2705 | 0
[9 empty] | 784 | 38.2705 | 0
[9 empty] | 785 | 38.2705 | 0
[9 empty] | 786 | 38.2705 | 0
[9 empty] | 787 | 38.2705 | 0
[9 empty] | 788 | 38.2705 | 0
[9 empty] | 789 | 38.2705 | 0
[9 empty] | 790 | 38.2705 | 0
[9 empty] | 791 | 38.2705 | 0
[9 empty] | 792 | 38.2705 | 0
[9 empty] | 793 | 38.2705 | 0
[9 empty] | 794 | 38.2705 | 0
[9 empty] | 795 | 38.2705 | 0
[9 empty] | 796 | 38.2705 | 0
[9 empty] | 797 | 38.2705 | 0
[9 empty] | 798 | 38.2705 | 0
[9 empty] | 799 | 38.2705 | 0
[9 empty] | 800 | 38.2705 | 0
[9 empty] | 801 | 38.2705 | 0
[9 empty] | 802 | 38.2705 | 0
[9 empty] | 803 | 38.2705 | 0
[9 empty] | 804 | 38.2705 | 0
[9 empty] | 805 | 38.2705 | 0
[9 empty] | 806 | 38.2705 | 0
[9 empty] | 807 | 38.2705 | 0
[9 empty] | 808 | 38.2705 | 0
[9 empty] | 809 | 38.2705 | 0
[9 empty] | 810 | 38.2705 | 0
[9 empty] | 811 | 38.2705 | 0
[9 empty] | 812 | 38.2705 | 0
[9 empty] | 813 | 38.2705 | 0
[9 empty] | 814 | 38.2705 | 0
[9 empty] | 815 | 38.2705 | 0
[9 empty] | 816 | 38.2705 | 0
[9 empty] | 817 | 38.2705 | 0
[9 empty] | 818 | 38.2705 | 0
[9 empty] | 819 | 38.2705 | 0
[9 empty] | 820 | 38.2705 | 0
[9 empty] | 821 | 38.2705 | 0
[9 empty] | 822 | 38.2705 | 0
[9 empty] | 823 | 38.2705 | 0
[9 empty] | 824 | 38.2705 | 0
[9 empty] | 825 | 38.2705 | 0
[9 empty] | 826 | 38.2705 | 0
[9 empty] | 827 | 38.2705 | 0
[9 empty] | 828 | 38.2705 | 0
[9 empty] | 829 | 38.2705 | 0
[9 empty] | 830 | 38.2705 | 0
[9 empty] | 831 | 38.2705 | 0
[9 empty] | 832 | 38.2705 | 0
[9 empty] | 833 | 38.2705 | 0
[9 empty] | 834 | 38.2705 | 0
[9 empty] | 835 | 38.2705 | 0
[9 empty] | 836 | 38.2705 | 0
[9 empty] | 837 | 38.2705 | 0
[9 empty] | 838 | 38.2705 | 0
[9 empty] | 839 | 38.2705 | 0
[9 empty] | 840 | 38.2705 | 0
[9 empty] | 841 | 38.2705 | 0
[9 empty] | 842 | 38.2705 | 0
[9 empty] | 843 | 38.2705 | 0
[9 empty] | 844 | 38.2705 | 0
[9 empty] | 845 | 38.2705 | 0
[9 empty] | 846 | 38.2705 | 0
[9 empty] | 847 | 38.2705 | 0
[9 empty] | 848 | 38.2705 | 0
[9 empty] | 849 | 38.2705 | 0
[9 empty] | 850 | 38.2705 | 0
[9 empty] | 851 | 38.2705 | 0
[9 empty] | 852 | 38.2705 | 0
[9 empty] | 853 | 38.2705 | 0
[9 empty] | 854 | 38.2705 | 0
[9 empty] | 855 | 38.2705 | 0
[9 empty] | 856 | 38.2705 | 0
[9 empty] | 857 | 38.2705 | 0
[9 empty] | 858 | 38.2705 | 0
[9 empty] | 859 | 38.2705 | 0
[9 empty] | 860 | 38.2705 | 0
[9 empty] | 861 | 38.2705 | 0
[9 empty] | 862 | 38.2705 | 0
[9 empty] | 863 | 38.2705 | 0
[9 empty] | 864 | 38.2705 | 0
[9 empty] | 865 | 38.2705 | 0
[9 empty] | 866 | 38.2705 | 0
[9 empty] | 867 | 38.2705 | 0
[9 empty] | 868 | 38.2705 | 0
[9 empty] | 869 | 38.2705 | 0
[9 empty] | 870 | 38.2705 | 0
[9 empty] | 871 | 38.2705 | 0
[9 empty] | 872 | 38.2705 | 0
[9 empty] | 873 | 38.2705 | 0
[9 empty] | 874 | 38.2705 | 0
[9 empty] | 875 | 38.2705 | 0
[9 empty] | 876 | 38.2705 | 0
[9 empty] | 877 | 38.2705 | 0
[9 empty] | 878 | 38.2705 | 0
[9 empty] | 879 | 38.2705 | 0
[9 empty] | 880 | 38.2705 | 0
[9 empty] | 881 | 38.2705 | 0
[9 empty] | 882 | 38.2705 | 0
[9 empty] | 883 | 38.2705 | 0
[9 empty] | 884 | 38.2705 | 0
[9 empty] | 885 | 38.2705 | 0
[9 empty] | 886 | 38.2705 | 0
[9 empty] | 887 | 38.2705 | 0
[9 empty] | 888 | 38.2705 | 0
[9 empty] | 889 | 38.2705 | 0
[9 empty] | 890 | 38.2705 | 0
[9 empty] | 891 | 38.2705 | 0
[9 empty] | 892 | 38.2705 | 0
[9 empty] | 893 | 38.2705 | 0
[9 empty] | 894 | 38.2705 | 0
[9 empty] | 895 | 38.2705 | 0
[9 empty] | 896 | 38.2705 | 0
[9 empty] | 897 | 38.2705 | 0
[9 empty] | 898 | 38.2705 | 0
[9 empty] | 899 | 38.2705 | 0
[9 empty] | 900 | 38.2705 | 0
[9 empty] | 901 | 38.2705 | 0
[9 empty] | 902 | 38.2705 | 0
[9 empty] | 903 | 38.2705 | 0
[9 empty] | 904 | 38.2705 | 0
[9 empty] | 905 | 38.2705 | 0
[9 empty] | 906 | 38.2705 | 0
[9 empty] | 907 | 38.2705 | 0
[9 empty] | 908 | 38.2705 | 0
[9 empty] | 909 | 38.2705 | 0
[9 empty] | 910 | 38.2705 | 0
[9 empty] | 911 | 38.2705 | 0
[9 empty] | 912 | 38.2705 | 0
[9 empty] | 913 | 38.2705 | 0
[9 empty] | 914 | 38.2705 | 0
[9 empty] | 915 | 38.2705 | 0
[9 empty] | 916 | 38.2705 | 0
[9 empty] | 917 | 38.2705 | 0
[9 empty] | 918 | 38.2705 | 0
[9 empty] | 919 | 38.2705 | 0
[9 empty] | 920 | 38.2705 | 0
[9 empty] | 921 | 38.2705 | 0
[9 empty] | 922 | 38.2705 | 0
[9 empty] | 923 | 38.2705 | 0
[9 empty] | 924 | 38.2705 | 0
[9 empty] | 925 | 38.2705 | 0
[9 empty] | 926 | 38.2705 | 0
[9 empty] | 927 | 38.2705 | 0
[9 empty] | 928 | 38.2705 | 0
[9 empty] | 929 | 38.2705 | 0
[9 empty] | 930 | 38.2705 | 0
[9 empty] | 931 | 38.2705 | 0
[9 empty] | 932 | 38.2705 | 0
[9 empty] | 933 | 38.2705 | 0
[9 empty] | 934 | 38.2705 | 0
[9 empty] | 935 | 38.2705 | 0
[9 empty] | 936 | 38.2705 | 0
[9 empty] | 937 | 38.2705 | 0
[9 empty] | 938 | 38.2705 | 0
[9 empty] | 939 | 38.2705 | 0
[9 empty] | 940 | 38.2705 | 0
[9 empty] | 941 | 38.2705 | 0
[9 empty] | 942 | 38.2705 | 0
[9 empty] | 943 | 38.2705 | 0
[9 empty] | 944 | 38.2705 | 0
[9 empty] | 945 | 38.2705 | 0
[9 empty] | 946 | 38.2705 | 0
[9 empty] | 947 | 38.2705 | 0
[9 empty] | 948 | 38.2705 | 0
[9 empty] | 949 | 38.2705 | 0
[9 empty] | 950 | 38.2705 | 0
[9 empty] | 951 | 38.2705 | 0
[9 empty] | 952 | 38.2705 | 0
[9 empty] | 953 | 38.2705 | 0
[9 empty] | 954 | 38.2705 | 0
[9 empty] | 955 | 38.2705 | 0
[9 empty] | 956 | 38.2705 | 0
[9 empty] | 957 | 38.2705 | 0
[9 empty] | 958 | 38.2705 | 0
[9 empty] | 959 | 38.2705 | 0
[9 empty] | 960 | 38.2705 | 0
[9 empty] | 961 | 38.2705 | 0
[9 empty] | 962 | 38.2705 | 0
[9 empty] | 963 | 38.2705 | 0
[9 empty] | 964 | 38.2705 | 0
[9 empty] | 965 | 38.2705 | 0
[9 empty] | 966 | 38.2705 | 0
[9 empty] | 967 | 38.2705 | 0
[9 empty] | 968 | 38.2705 | 0
[9 empty] | 969 | 38.2705 | 0
[9 empty] | 970 | 38.2705 | 0
[9 empty] | 971 | 38.2705 | 0
[9 empty] | 972 | 38.2705 | 0
[9 empty] | 973 | 38.2705 | 0
[9 empty] | 974 | 38.2705 | 0
[9 empty] | 975 | 38.2705 | 0
[9 empty] | 976 | 38.2705 | 0
[9 empty] | 977 | 38.2705 | 0
[9 empty] | 978 | 38.2705 | 0
[9 empty] | 979 | 38.2705 | 0
[9 empty] | 980 | 38.2705 | 0
[9 empty] | 981 | 38.2705 | 0
[9 empty] | 982 | 38.2705 | 0
[9 empty] | 983 | 38.2705 | 0
[9 empty] | 984 | 38.2705 | 0
[9 empty] | 985 | 38.2705 | 0
[9 empty] | 986 | 38.2705 | 0
[9 empty] | 987 | 38.2705 | 0
[9 empty] | 988 | 38.2705 | 0
[9 empty] | 989 | 38.2705 | 0
[9 empty] | 990 | 38.2705 | 0
[9 empty] | 991 | 38.2705 | 0
[9 empty] | 992 | 38.2705 | 0
[9 empty] | 993 | 38.2705 | 0
[9 empty] | 994 | 38.2705 | 0
[9 empty] | 995 | 38.2705 | 0
[9 empty] | 996 | 38.2705 | 0
[9 empty] | 997 | 38.2705 | 0
[9 empty] | 998 | 38.2705 | 0
[9 empty] | 999 | 38.2705 | 0
[9 empty] | 1000 | 38.2705 | 0

## Project-2 triangular(a,b,m)
Project 1 | [8 empty] | Trial | Project Duration | Success
Task | Immediate Ancestor | a | m | b | Start Time | U(0,1) | Duration | Finsih Time |  | 37.1746 | 1
A |  | 1 | 3 | 4 | 0 | 0.6292 | 2.943 | 2.943 | 1 | 37.1746 | 1
B |  | 5 | 7 | 8 | 0 | 0.078107 | 5.6846 | 5.6846 | 2 | 37.1746 | 1
C |  | 6 | 7 | 9 | 0 | 0.40019 | 7.1029 | 7.1029 | 3 | 37.1746 | 1
D |  | 1 | 2 | 3 | 0 | 0.51099 | 2.0111 | 2.0111 | 4 | 37.1746 | 1
E | A | 3 | 4 | 5 | 2.943 | 0.54291 | 4.0439 | 6.9869 | 5 | 37.1746 | 1
F | A | 7 | 8 | 9 | 2.943 | 0.28736 | 7.7581 | 10.7011 | 6 | 37.1746 | 1
G | B,E | 10 | 15 | 20 | 6.9869 | 0.16502 | 12.8725 | 19.8593 | 7 | 37.1746 | 1
H | B,E | 12 | 13 | 14 | 6.9869 | 0.74529 | 13.2863 | 20.2731 | 8 | 37.1746 | 1
I | C | 10 | 12 | 15 | 7.1029 | 0.93861 | 14.0404 | 21.1433 | 9 | 37.1746 | 1
J | C | 8 | 10 | 12 | 7.1029 | 0.54172 | 10.0853 | 17.1882 | 10 | 37.1746 | 1
K | F,I | 7 | 8 | 11 | 21.1433 | 0.80561 | 9.4727 | 30.616 | 11 | 37.1746 | 1
L | F,I | 2 | 4 | 8 | 21.1433 | 0.57236 | 4.7964 | 25.9397 | 12 | 37.1746 | 1
M | D,K | 5 | 6 | 7 | 30.616 | 0.90257 | 6.5586 | 37.1746 | 13 | 37.1746 | 1
N | H,J,L,M | 0 | 0 | 0 | 37.1746 | 0.23153 | 0 | 37.1746 | 14 | 37.1746 | 1
[9 empty] | 15 | 37.1746 | 1
[9 empty] | 16 | 37.1746 | 1
[9 empty] | 17 | 37.1746 | 1
[9 empty] | 18 | 37.1746 | 1
Deadline | Average Project Duration | Avg Success Rate | [6 empty] | 19 | 37.1746 | 1
48 | 37.1746 | 100 | [6 empty] | 20 | 37.1746 | 1
[9 empty] | 21 | 37.1746 | 1
[9 empty] | 22 | 37.1746 | 1
[9 empty] | 23 | 37.1746 | 1
[9 empty] | 24 | 37.1746 | 1
[9 empty] | 25 | 37.1746 | 1
[9 empty] | 26 | 37.1746 | 1
[9 empty] | 27 | 37.1746 | 1
[9 empty] | 28 | 37.1746 | 1
[9 empty] | 29 | 37.1746 | 1
[9 empty] | 30 | 37.1746 | 1
[9 empty] | 31 | 37.1746 | 1
[9 empty] | 32 | 37.1746 | 1
[9 empty] | 33 | 37.1746 | 1
[9 empty] | 34 | 37.1746 | 1
[9 empty] | 35 | 37.1746 | 1
[9 empty] | 36 | 37.1746 | 1
[9 empty] | 37 | 37.1746 | 1
[9 empty] | 38 | 37.1746 | 1
[9 empty] | 39 | 37.1746 | 1
[9 empty] | 40 | 37.1746 | 1
[9 empty] | 41 | 37.1746 | 1
[9 empty] | 42 | 37.1746 | 1
[9 empty] | 43 | 37.1746 | 1
[9 empty] | 44 | 37.1746 | 1
[9 empty] | 45 | 37.1746 | 1
[9 empty] | 46 | 37.1746 | 1
[9 empty] | 47 | 37.1746 | 1
[9 empty] | 48 | 37.1746 | 1
[9 empty] | 49 | 37.1746 | 1
[9 empty] | 50 | 37.1746 | 1
[9 empty] | 51 | 37.1746 | 1
[9 empty] | 52 | 37.1746 | 1
[9 empty] | 53 | 37.1746 | 1
[9 empty] | 54 | 37.1746 | 1
[9 empty] | 55 | 37.1746 | 1
[9 empty] | 56 | 37.1746 | 1
[9 empty] | 57 | 37.1746 | 1
[9 empty] | 58 | 37.1746 | 1
[9 empty] | 59 | 37.1746 | 1
[9 empty] | 60 | 37.1746 | 1
[9 empty] | 61 | 37.1746 | 1
[9 empty] | 62 | 37.1746 | 1
[9 empty] | 63 | 37.1746 | 1
[9 empty] | 64 | 37.1746 | 1
[9 empty] | 65 | 37.1746 | 1
[9 empty] | 66 | 37.1746 | 1
[9 empty] | 67 | 37.1746 | 1
[9 empty] | 68 | 37.1746 | 1
[9 empty] | 69 | 37.1746 | 1
[9 empty] | 70 | 37.1746 | 1
[9 empty] | 71 | 37.1746 | 1
[9 empty] | 72 | 37.1746 | 1
[9 empty] | 73 | 37.1746 | 1
[9 empty] | 74 | 37.1746 | 1
[9 empty] | 75 | 37.1746 | 1
[9 empty] | 76 | 37.1746 | 1
[9 empty] | 77 | 37.1746 | 1
[9 empty] | 78 | 37.1746 | 1
[9 empty] | 79 | 37.1746 | 1
[9 empty] | 80 | 37.1746 | 1
[9 empty] | 81 | 37.1746 | 1
[9 empty] | 82 | 37.1746 | 1
[9 empty] | 83 | 37.1746 | 1
[9 empty] | 84 | 37.1746 | 1
[9 empty] | 85 | 37.1746 | 1
[9 empty] | 86 | 37.1746 | 1
[9 empty] | 87 | 37.1746 | 1
[9 empty] | 88 | 37.1746 | 1
[9 empty] | 89 | 37.1746 | 1
[9 empty] | 90 | 37.1746 | 1
[9 empty] | 91 | 37.1746 | 1
[9 empty] | 92 | 37.1746 | 1
[9 empty] | 93 | 37.1746 | 1
[9 empty] | 94 | 37.1746 | 1
[9 empty] | 95 | 37.1746 | 1
[9 empty] | 96 | 37.1746 | 1
[9 empty] | 97 | 37.1746 | 1
[9 empty] | 98 | 37.1746 | 1
[9 empty] | 99 | 37.1746 | 1
[9 empty] | 100 | 37.1746 | 1
[9 empty] | 101 | 37.1746 | 1
[9 empty] | 102 | 37.1746 | 1
[9 empty] | 103 | 37.1746 | 1
[9 empty] | 104 | 37.1746 | 1
[9 empty] | 105 | 37.1746 | 1
[9 empty] | 106 | 37.1746 | 1
[9 empty] | 107 | 37.1746 | 1
[9 empty] | 108 | 37.1746 | 1
[9 empty] | 109 | 37.1746 | 1
[9 empty] | 110 | 37.1746 | 1
[9 empty] | 111 | 37.1746 | 1
[9 empty] | 112 | 37.1746 | 1
[9 empty] | 113 | 37.1746 | 1
[9 empty] | 114 | 37.1746 | 1
[9 empty] | 115 | 37.1746 | 1
[9 empty] | 116 | 37.1746 | 1
[9 empty] | 117 | 37.1746 | 1
[9 empty] | 118 | 37.1746 | 1
[9 empty] | 119 | 37.1746 | 1
[9 empty] | 120 | 37.1746 | 1
[9 empty] | 121 | 37.1746 | 1
[9 empty] | 122 | 37.1746 | 1
[9 empty] | 123 | 37.1746 | 1
[9 empty] | 124 | 37.1746 | 1
[9 empty] | 125 | 37.1746 | 1
[9 empty] | 126 | 37.1746 | 1
[9 empty] | 127 | 37.1746 | 1
[9 empty] | 128 | 37.1746 | 1
[9 empty] | 129 | 37.1746 | 1
[9 empty] | 130 | 37.1746 | 1
[9 empty] | 131 | 37.1746 | 1
[9 empty] | 132 | 37.1746 | 1
[9 empty] | 133 | 37.1746 | 1
[9 empty] | 134 | 37.1746 | 1
[9 empty] | 135 | 37.1746 | 1
[9 empty] | 136 | 37.1746 | 1
[9 empty] | 137 | 37.1746 | 1
[9 empty] | 138 | 37.1746 | 1
[9 empty] | 139 | 37.1746 | 1
[9 empty] | 140 | 37.1746 | 1
[9 empty] | 141 | 37.1746 | 1
[9 empty] | 142 | 37.1746 | 1
[9 empty] | 143 | 37.1746 | 1
[9 empty] | 144 | 37.1746 | 1
[9 empty] | 145 | 37.1746 | 1
[9 empty] | 146 | 37.1746 | 1
[9 empty] | 147 | 37.1746 | 1
[9 empty] | 148 | 37.1746 | 1
[9 empty] | 149 | 37.1746 | 1
[9 empty] | 150 | 37.1746 | 1
[9 empty] | 151 | 37.1746 | 1
[9 empty] | 152 | 37.1746 | 1
[9 empty] | 153 | 37.1746 | 1
[9 empty] | 154 | 37.1746 | 1
[9 empty] | 155 | 37.1746 | 1
[9 empty] | 156 | 37.1746 | 1
[9 empty] | 157 | 37.1746 | 1
[9 empty] | 158 | 37.1746 | 1
[9 empty] | 159 | 37.1746 | 1
[9 empty] | 160 | 37.1746 | 1
[9 empty] | 161 | 37.1746 | 1
[9 empty] | 162 | 37.1746 | 1
[9 empty] | 163 | 37.1746 | 1
[9 empty] | 164 | 37.1746 | 1
[9 empty] | 165 | 37.1746 | 1
[9 empty] | 166 | 37.1746 | 1
[9 empty] | 167 | 37.1746 | 1
[9 empty] | 168 | 37.1746 | 1
[9 empty] | 169 | 37.1746 | 1
[9 empty] | 170 | 37.1746 | 1
[9 empty] | 171 | 37.1746 | 1
[9 empty] | 172 | 37.1746 | 1
[9 empty] | 173 | 37.1746 | 1
[9 empty] | 174 | 37.1746 | 1
[9 empty] | 175 | 37.1746 | 1
[9 empty] | 176 | 37.1746 | 1
[9 empty] | 177 | 37.1746 | 1
[9 empty] | 178 | 37.1746 | 1
[9 empty] | 179 | 37.1746 | 1
[9 empty] | 180 | 37.1746 | 1
[9 empty] | 181 | 37.1746 | 1
[9 empty] | 182 | 37.1746 | 1
[9 empty] | 183 | 37.1746 | 1
[9 empty] | 184 | 37.1746 | 1
[9 empty] | 185 | 37.1746 | 1
[9 empty] | 186 | 37.1746 | 1
[9 empty] | 187 | 37.1746 | 1
[9 empty] | 188 | 37.1746 | 1
[9 empty] | 189 | 37.1746 | 1
[9 empty] | 190 | 37.1746 | 1
[9 empty] | 191 | 37.1746 | 1
[9 empty] | 192 | 37.1746 | 1
[9 empty] | 193 | 37.1746 | 1
[9 empty] | 194 | 37.1746 | 1
[9 empty] | 195 | 37.1746 | 1
[9 empty] | 196 | 37.1746 | 1
[9 empty] | 197 | 37.1746 | 1
[9 empty] | 198 | 37.1746 | 1
[9 empty] | 199 | 37.1746 | 1
[9 empty] | 200 | 37.1746 | 1
[9 empty] | 201 | 37.1746 | 1
[9 empty] | 202 | 37.1746 | 1
[9 empty] | 203 | 37.1746 | 1
[9 empty] | 204 | 37.1746 | 1
[9 empty] | 205 | 37.1746 | 1
[9 empty] | 206 | 37.1746 | 1
[9 empty] | 207 | 37.1746 | 1
[9 empty] | 208 | 37.1746 | 1
[9 empty] | 209 | 37.1746 | 1
[9 empty] | 210 | 37.1746 | 1
[9 empty] | 211 | 37.1746 | 1
[9 empty] | 212 | 37.1746 | 1
[9 empty] | 213 | 37.1746 | 1
[9 empty] | 214 | 37.1746 | 1
[9 empty] | 215 | 37.1746 | 1
[9 empty] | 216 | 37.1746 | 1
[9 empty] | 217 | 37.1746 | 1
[9 empty] | 218 | 37.1746 | 1
[9 empty] | 219 | 37.1746 | 1
[9 empty] | 220 | 37.1746 | 1
[9 empty] | 221 | 37.1746 | 1
[9 empty] | 222 | 37.1746 | 1
[9 empty] | 223 | 37.1746 | 1
[9 empty] | 224 | 37.1746 | 1
[9 empty] | 225 | 37.1746 | 1
[9 empty] | 226 | 37.1746 | 1
[9 empty] | 227 | 37.1746 | 1
[9 empty] | 228 | 37.1746 | 1
[9 empty] | 229 | 37.1746 | 1
[9 empty] | 230 | 37.1746 | 1
[9 empty] | 231 | 37.1746 | 1
[9 empty] | 232 | 37.1746 | 1
[9 empty] | 233 | 37.1746 | 1
[9 empty] | 234 | 37.1746 | 1
[9 empty] | 235 | 37.1746 | 1
[9 empty] | 236 | 37.1746 | 1
[9 empty] | 237 | 37.1746 | 1
[9 empty] | 238 | 37.1746 | 1
[9 empty] | 239 | 37.1746 | 1
[9 empty] | 240 | 37.1746 | 1
[9 empty] | 241 | 37.1746 | 1
[9 empty] | 242 | 37.1746 | 1
[9 empty] | 243 | 37.1746 | 1
[9 empty] | 244 | 37.1746 | 1
[9 empty] | 245 | 37.1746 | 1
[9 empty] | 246 | 37.1746 | 1
[9 empty] | 247 | 37.1746 | 1
[9 empty] | 248 | 37.1746 | 1
[9 empty] | 249 | 37.1746 | 1
[9 empty] | 250 | 37.1746 | 1
[9 empty] | 251 | 37.1746 | 1
[9 empty] | 252 | 37.1746 | 1
[9 empty] | 253 | 37.1746 | 1
[9 empty] | 254 | 37.1746 | 1
[9 empty] | 255 | 37.1746 | 1
[9 empty] | 256 | 37.1746 | 1
[9 empty] | 257 | 37.1746 | 1
[9 empty] | 258 | 37.1746 | 1
[9 empty] | 259 | 37.1746 | 1
[9 empty] | 260 | 37.1746 | 1
[9 empty] | 261 | 37.1746 | 1
[9 empty] | 262 | 37.1746 | 1
[9 empty] | 263 | 37.1746 | 1
[9 empty] | 264 | 37.1746 | 1
[9 empty] | 265 | 37.1746 | 1
[9 empty] | 266 | 37.1746 | 1
[9 empty] | 267 | 37.1746 | 1
[9 empty] | 268 | 37.1746 | 1
[9 empty] | 269 | 37.1746 | 1
[9 empty] | 270 | 37.1746 | 1
[9 empty] | 271 | 37.1746 | 1
[9 empty] | 272 | 37.1746 | 1
[9 empty] | 273 | 37.1746 | 1
[9 empty] | 274 | 37.1746 | 1
[9 empty] | 275 | 37.1746 | 1
[9 empty] | 276 | 37.1746 | 1
[9 empty] | 277 | 37.1746 | 1
[9 empty] | 278 | 37.1746 | 1
[9 empty] | 279 | 37.1746 | 1
[9 empty] | 280 | 37.1746 | 1
[9 empty] | 281 | 37.1746 | 1
[9 empty] | 282 | 37.1746 | 1
[9 empty] | 283 | 37.1746 | 1
[9 empty] | 284 | 37.1746 | 1
[9 empty] | 285 | 37.1746 | 1
[9 empty] | 286 | 37.1746 | 1
[9 empty] | 287 | 37.1746 | 1
[9 empty] | 288 | 37.1746 | 1
[9 empty] | 289 | 37.1746 | 1
[9 empty] | 290 | 37.1746 | 1
[9 empty] | 291 | 37.1746 | 1
[9 empty] | 292 | 37.1746 | 1
[9 empty] | 293 | 37.1746 | 1
[9 empty] | 294 | 37.1746 | 1
[9 empty] | 295 | 37.1746 | 1
[9 empty] | 296 | 37.1746 | 1
[9 empty] | 297 | 37.1746 | 1
[9 empty] | 298 | 37.1746 | 1
[9 empty] | 299 | 37.1746 | 1
[9 empty] | 300 | 37.1746 | 1
[9 empty] | 301 | 37.1746 | 1
[9 empty] | 302 | 37.1746 | 1
[9 empty] | 303 | 37.1746 | 1
[9 empty] | 304 | 37.1746 | 1
[9 empty] | 305 | 37.1746 | 1
[9 empty] | 306 | 37.1746 | 1
[9 empty] | 307 | 37.1746 | 1
[9 empty] | 308 | 37.1746 | 1
[9 empty] | 309 | 37.1746 | 1
[9 empty] | 310 | 37.1746 | 1
[9 empty] | 311 | 37.1746 | 1
[9 empty] | 312 | 37.1746 | 1
[9 empty] | 313 | 37.1746 | 1
[9 empty] | 314 | 37.1746 | 1
[9 empty] | 315 | 37.1746 | 1
[9 empty] | 316 | 37.1746 | 1
[9 empty] | 317 | 37.1746 | 1
[9 empty] | 318 | 37.1746 | 1
[9 empty] | 319 | 37.1746 | 1
[9 empty] | 320 | 37.1746 | 1
[9 empty] | 321 | 37.1746 | 1
[9 empty] | 322 | 37.1746 | 1
[9 empty] | 323 | 37.1746 | 1
[9 empty] | 324 | 37.1746 | 1
[9 empty] | 325 | 37.1746 | 1
[9 empty] | 326 | 37.1746 | 1
[9 empty] | 327 | 37.1746 | 1
[9 empty] | 328 | 37.1746 | 1
[9 empty] | 329 | 37.1746 | 1
[9 empty] | 330 | 37.1746 | 1
[9 empty] | 331 | 37.1746 | 1
[9 empty] | 332 | 37.1746 | 1
[9 empty] | 333 | 37.1746 | 1
[9 empty] | 334 | 37.1746 | 1
[9 empty] | 335 | 37.1746 | 1
[9 empty] | 336 | 37.1746 | 1
[9 empty] | 337 | 37.1746 | 1
[9 empty] | 338 | 37.1746 | 1
[9 empty] | 339 | 37.1746 | 1
[9 empty] | 340 | 37.1746 | 1
[9 empty] | 341 | 37.1746 | 1
[9 empty] | 342 | 37.1746 | 1
[9 empty] | 343 | 37.1746 | 1
[9 empty] | 344 | 37.1746 | 1
[9 empty] | 345 | 37.1746 | 1
[9 empty] | 346 | 37.1746 | 1
[9 empty] | 347 | 37.1746 | 1
[9 empty] | 348 | 37.1746 | 1
[9 empty] | 349 | 37.1746 | 1
[9 empty] | 350 | 37.1746 | 1
[9 empty] | 351 | 37.1746 | 1
[9 empty] | 352 | 37.1746 | 1
[9 empty] | 353 | 37.1746 | 1
[9 empty] | 354 | 37.1746 | 1
[9 empty] | 355 | 37.1746 | 1
[9 empty] | 356 | 37.1746 | 1
[9 empty] | 357 | 37.1746 | 1
[9 empty] | 358 | 37.1746 | 1
[9 empty] | 359 | 37.1746 | 1
[9 empty] | 360 | 37.1746 | 1
[9 empty] | 361 | 37.1746 | 1
[9 empty] | 362 | 37.1746 | 1
[9 empty] | 363 | 37.1746 | 1
[9 empty] | 364 | 37.1746 | 1
[9 empty] | 365 | 37.1746 | 1
[9 empty] | 366 | 37.1746 | 1
[9 empty] | 367 | 37.1746 | 1
[9 empty] | 368 | 37.1746 | 1
[9 empty] | 369 | 37.1746 | 1
[9 empty] | 370 | 37.1746 | 1
[9 empty] | 371 | 37.1746 | 1
[9 empty] | 372 | 37.1746 | 1
[9 empty] | 373 | 37.1746 | 1
[9 empty] | 374 | 37.1746 | 1
[9 empty] | 375 | 37.1746 | 1
[9 empty] | 376 | 37.1746 | 1
[9 empty] | 377 | 37.1746 | 1
[9 empty] | 378 | 37.1746 | 1
[9 empty] | 379 | 37.1746 | 1
[9 empty] | 380 | 37.1746 | 1
[9 empty] | 381 | 37.1746 | 1
[9 empty] | 382 | 37.1746 | 1
[9 empty] | 383 | 37.1746 | 1
[9 empty] | 384 | 37.1746 | 1
[9 empty] | 385 | 37.1746 | 1
[9 empty] | 386 | 37.1746 | 1
[9 empty] | 387 | 37.1746 | 1
[9 empty] | 388 | 37.1746 | 1
[9 empty] | 389 | 37.1746 | 1
[9 empty] | 390 | 37.1746 | 1
[9 empty] | 391 | 37.1746 | 1
[9 empty] | 392 | 37.1746 | 1
[9 empty] | 393 | 37.1746 | 1
[9 empty] | 394 | 37.1746 | 1
[9 empty] | 395 | 37.1746 | 1
[9 empty] | 396 | 37.1746 | 1
[9 empty] | 397 | 37.1746 | 1
[9 empty] | 398 | 37.1746 | 1
[9 empty] | 399 | 37.1746 | 1
[9 empty] | 400 | 37.1746 | 1
[9 empty] | 401 | 37.1746 | 1
[9 empty] | 402 | 37.1746 | 1
[9 empty] | 403 | 37.1746 | 1
[9 empty] | 404 | 37.1746 | 1
[9 empty] | 405 | 37.1746 | 1
[9 empty] | 406 | 37.1746 | 1
[9 empty] | 407 | 37.1746 | 1
[9 empty] | 408 | 37.1746 | 1
[9 empty] | 409 | 37.1746 | 1
[9 empty] | 410 | 37.1746 | 1
[9 empty] | 411 | 37.1746 | 1
[9 empty] | 412 | 37.1746 | 1
[9 empty] | 413 | 37.1746 | 1
[9 empty] | 414 | 37.1746 | 1
[9 empty] | 415 | 37.1746 | 1
[9 empty] | 416 | 37.1746 | 1
[9 empty] | 417 | 37.1746 | 1
[9 empty] | 418 | 37.1746 | 1
[9 empty] | 419 | 37.1746 | 1
[9 empty] | 420 | 37.1746 | 1
[9 empty] | 421 | 37.1746 | 1
[9 empty] | 422 | 37.1746 | 1
[9 empty] | 423 | 37.1746 | 1
[9 empty] | 424 | 37.1746 | 1
[9 empty] | 425 | 37.1746 | 1
[9 empty] | 426 | 37.1746 | 1
[9 empty] | 427 | 37.1746 | 1
[9 empty] | 428 | 37.1746 | 1
[9 empty] | 429 | 37.1746 | 1
[9 empty] | 430 | 37.1746 | 1
[9 empty] | 431 | 37.1746 | 1
[9 empty] | 432 | 37.1746 | 1
[9 empty] | 433 | 37.1746 | 1
[9 empty] | 434 | 37.1746 | 1
[9 empty] | 435 | 37.1746 | 1
[9 empty] | 436 | 37.1746 | 1
[9 empty] | 437 | 37.1746 | 1
[9 empty] | 438 | 37.1746 | 1
[9 empty] | 439 | 37.1746 | 1
[9 empty] | 440 | 37.1746 | 1
[9 empty] | 441 | 37.1746 | 1
[9 empty] | 442 | 37.1746 | 1
[9 empty] | 443 | 37.1746 | 1
[9 empty] | 444 | 37.1746 | 1
[9 empty] | 445 | 37.1746 | 1
[9 empty] | 446 | 37.1746 | 1
[9 empty] | 447 | 37.1746 | 1
[9 empty] | 448 | 37.1746 | 1
[9 empty] | 449 | 37.1746 | 1
[9 empty] | 450 | 37.1746 | 1
[9 empty] | 451 | 37.1746 | 1
[9 empty] | 452 | 37.1746 | 1
[9 empty] | 453 | 37.1746 | 1
[9 empty] | 454 | 37.1746 | 1
[9 empty] | 455 | 37.1746 | 1
[9 empty] | 456 | 37.1746 | 1
[9 empty] | 457 | 37.1746 | 1
[9 empty] | 458 | 37.1746 | 1
[9 empty] | 459 | 37.1746 | 1
[9 empty] | 460 | 37.1746 | 1
[9 empty] | 461 | 37.1746 | 1
[9 empty] | 462 | 37.1746 | 1
[9 empty] | 463 | 37.1746 | 1
[9 empty] | 464 | 37.1746 | 1
[9 empty] | 465 | 37.1746 | 1
[9 empty] | 466 | 37.1746 | 1
[9 empty] | 467 | 37.1746 | 1
[9 empty] | 468 | 37.1746 | 1
[9 empty] | 469 | 37.1746 | 1
[9 empty] | 470 | 37.1746 | 1
[9 empty] | 471 | 37.1746 | 1
[9 empty] | 472 | 37.1746 | 1
[9 empty] | 473 | 37.1746 | 1
[9 empty] | 474 | 37.1746 | 1
[9 empty] | 475 | 37.1746 | 1
[9 empty] | 476 | 37.1746 | 1
[9 empty] | 477 | 37.1746 | 1
[9 empty] | 478 | 37.1746 | 1
[9 empty] | 479 | 37.1746 | 1
[9 empty] | 480 | 37.1746 | 1
[9 empty] | 481 | 37.1746 | 1
[9 empty] | 482 | 37.1746 | 1
[9 empty] | 483 | 37.1746 | 1
[9 empty] | 484 | 37.1746 | 1
[9 empty] | 485 | 37.1746 | 1
[9 empty] | 486 | 37.1746 | 1
[9 empty] | 487 | 37.1746 | 1
[9 empty] | 488 | 37.1746 | 1
[9 empty] | 489 | 37.1746 | 1
[9 empty] | 490 | 37.1746 | 1
[9 empty] | 491 | 37.1746 | 1
[9 empty] | 492 | 37.1746 | 1
[9 empty] | 493 | 37.1746 | 1
[9 empty] | 494 | 37.1746 | 1
[9 empty] | 495 | 37.1746 | 1
[9 empty] | 496 | 37.1746 | 1
[9 empty] | 497 | 37.1746 | 1
[9 empty] | 498 | 37.1746 | 1
[9 empty] | 499 | 37.1746 | 1
[9 empty] | 500 | 37.1746 | 1
[9 empty] | 501 | 37.1746 | 1
[9 empty] | 502 | 37.1746 | 1
[9 empty] | 503 | 37.1746 | 1
[9 empty] | 504 | 37.1746 | 1
[9 empty] | 505 | 37.1746 | 1
[9 empty] | 506 | 37.1746 | 1
[9 empty] | 507 | 37.1746 | 1
[9 empty] | 508 | 37.1746 | 1
[9 empty] | 509 | 37.1746 | 1
[9 empty] | 510 | 37.1746 | 1
[9 empty] | 511 | 37.1746 | 1
[9 empty] | 512 | 37.1746 | 1
[9 empty] | 513 | 37.1746 | 1
[9 empty] | 514 | 37.1746 | 1
[9 empty] | 515 | 37.1746 | 1
[9 empty] | 516 | 37.1746 | 1
[9 empty] | 517 | 37.1746 | 1
[9 empty] | 518 | 37.1746 | 1
[9 empty] | 519 | 37.1746 | 1
[9 empty] | 520 | 37.1746 | 1
[9 empty] | 521 | 37.1746 | 1
[9 empty] | 522 | 37.1746 | 1
[9 empty] | 523 | 37.1746 | 1
[9 empty] | 524 | 37.1746 | 1
[9 empty] | 525 | 37.1746 | 1
[9 empty] | 526 | 37.1746 | 1
[9 empty] | 527 | 37.1746 | 1
[9 empty] | 528 | 37.1746 | 1
[9 empty] | 529 | 37.1746 | 1
[9 empty] | 530 | 37.1746 | 1
[9 empty] | 531 | 37.1746 | 1
[9 empty] | 532 | 37.1746 | 1
[9 empty] | 533 | 37.1746 | 1
[9 empty] | 534 | 37.1746 | 1
[9 empty] | 535 | 37.1746 | 1
[9 empty] | 536 | 37.1746 | 1
[9 empty] | 537 | 37.1746 | 1
[9 empty] | 538 | 37.1746 | 1
[9 empty] | 539 | 37.1746 | 1
[9 empty] | 540 | 37.1746 | 1
[9 empty] | 541 | 37.1746 | 1
[9 empty] | 542 | 37.1746 | 1
[9 empty] | 543 | 37.1746 | 1
[9 empty] | 544 | 37.1746 | 1
[9 empty] | 545 | 37.1746 | 1
[9 empty] | 546 | 37.1746 | 1
[9 empty] | 547 | 37.1746 | 1
[9 empty] | 548 | 37.1746 | 1
[9 empty] | 549 | 37.1746 | 1
[9 empty] | 550 | 37.1746 | 1
[9 empty] | 551 | 37.1746 | 1
[9 empty] | 552 | 37.1746 | 1
[9 empty] | 553 | 37.1746 | 1
[9 empty] | 554 | 37.1746 | 1
[9 empty] | 555 | 37.1746 | 1
[9 empty] | 556 | 37.1746 | 1
[9 empty] | 557 | 37.1746 | 1
[9 empty] | 558 | 37.1746 | 1
[9 empty] | 559 | 37.1746 | 1
[9 empty] | 560 | 37.1746 | 1
[9 empty] | 561 | 37.1746 | 1
[9 empty] | 562 | 37.1746 | 1
[9 empty] | 563 | 37.1746 | 1
[9 empty] | 564 | 37.1746 | 1
[9 empty] | 565 | 37.1746 | 1
[9 empty] | 566 | 37.1746 | 1
[9 empty] | 567 | 37.1746 | 1
[9 empty] | 568 | 37.1746 | 1
[9 empty] | 569 | 37.1746 | 1
[9 empty] | 570 | 37.1746 | 1
[9 empty] | 571 | 37.1746 | 1
[9 empty] | 572 | 37.1746 | 1
[9 empty] | 573 | 37.1746 | 1
[9 empty] | 574 | 37.1746 | 1
[9 empty] | 575 | 37.1746 | 1
[9 empty] | 576 | 37.1746 | 1
[9 empty] | 577 | 37.1746 | 1
[9 empty] | 578 | 37.1746 | 1
[9 empty] | 579 | 37.1746 | 1
[9 empty] | 580 | 37.1746 | 1
[9 empty] | 581 | 37.1746 | 1
[9 empty] | 582 | 37.1746 | 1
[9 empty] | 583 | 37.1746 | 1
[9 empty] | 584 | 37.1746 | 1
[9 empty] | 585 | 37.1746 | 1
[9 empty] | 586 | 37.1746 | 1
[9 empty] | 587 | 37.1746 | 1
[9 empty] | 588 | 37.1746 | 1
[9 empty] | 589 | 37.1746 | 1
[9 empty] | 590 | 37.1746 | 1
[9 empty] | 591 | 37.1746 | 1
[9 empty] | 592 | 37.1746 | 1
[9 empty] | 593 | 37.1746 | 1
[9 empty] | 594 | 37.1746 | 1
[9 empty] | 595 | 37.1746 | 1
[9 empty] | 596 | 37.1746 | 1
[9 empty] | 597 | 37.1746 | 1
[9 empty] | 598 | 37.1746 | 1
[9 empty] | 599 | 37.1746 | 1
[9 empty] | 600 | 37.1746 | 1
[9 empty] | 601 | 37.1746 | 1
[9 empty] | 602 | 37.1746 | 1
[9 empty] | 603 | 37.1746 | 1
[9 empty] | 604 | 37.1746 | 1
[9 empty] | 605 | 37.1746 | 1
[9 empty] | 606 | 37.1746 | 1
[9 empty] | 607 | 37.1746 | 1
[9 empty] | 608 | 37.1746 | 1
[9 empty] | 609 | 37.1746 | 1
[9 empty] | 610 | 37.1746 | 1
[9 empty] | 611 | 37.1746 | 1
[9 empty] | 612 | 37.1746 | 1
[9 empty] | 613 | 37.1746 | 1
[9 empty] | 614 | 37.1746 | 1
[9 empty] | 615 | 37.1746 | 1
[9 empty] | 616 | 37.1746 | 1
[9 empty] | 617 | 37.1746 | 1
[9 empty] | 618 | 37.1746 | 1
[9 empty] | 619 | 37.1746 | 1
[9 empty] | 620 | 37.1746 | 1
[9 empty] | 621 | 37.1746 | 1
[9 empty] | 622 | 37.1746 | 1
[9 empty] | 623 | 37.1746 | 1
[9 empty] | 624 | 37.1746 | 1
[9 empty] | 625 | 37.1746 | 1
[9 empty] | 626 | 37.1746 | 1
[9 empty] | 627 | 37.1746 | 1
[9 empty] | 628 | 37.1746 | 1
[9 empty] | 629 | 37.1746 | 1
[9 empty] | 630 | 37.1746 | 1
[9 empty] | 631 | 37.1746 | 1
[9 empty] | 632 | 37.1746 | 1
[9 empty] | 633 | 37.1746 | 1
[9 empty] | 634 | 37.1746 | 1
[9 empty] | 635 | 37.1746 | 1
[9 empty] | 636 | 37.1746 | 1
[9 empty] | 637 | 37.1746 | 1
[9 empty] | 638 | 37.1746 | 1
[9 empty] | 639 | 37.1746 | 1
[9 empty] | 640 | 37.1746 | 1
[9 empty] | 641 | 37.1746 | 1
[9 empty] | 642 | 37.1746 | 1
[9 empty] | 643 | 37.1746 | 1
[9 empty] | 644 | 37.1746 | 1
[9 empty] | 645 | 37.1746 | 1
[9 empty] | 646 | 37.1746 | 1
[9 empty] | 647 | 37.1746 | 1
[9 empty] | 648 | 37.1746 | 1
[9 empty] | 649 | 37.1746 | 1
[9 empty] | 650 | 37.1746 | 1
[9 empty] | 651 | 37.1746 | 1
[9 empty] | 652 | 37.1746 | 1
[9 empty] | 653 | 37.1746 | 1
[9 empty] | 654 | 37.1746 | 1
[9 empty] | 655 | 37.1746 | 1
[9 empty] | 656 | 37.1746 | 1
[9 empty] | 657 | 37.1746 | 1
[9 empty] | 658 | 37.1746 | 1
[9 empty] | 659 | 37.1746 | 1
[9 empty] | 660 | 37.1746 | 1
[9 empty] | 661 | 37.1746 | 1
[9 empty] | 662 | 37.1746 | 1
[9 empty] | 663 | 37.1746 | 1
[9 empty] | 664 | 37.1746 | 1
[9 empty] | 665 | 37.1746 | 1
[9 empty] | 666 | 37.1746 | 1
[9 empty] | 667 | 37.1746 | 1
[9 empty] | 668 | 37.1746 | 1
[9 empty] | 669 | 37.1746 | 1
[9 empty] | 670 | 37.1746 | 1
[9 empty] | 671 | 37.1746 | 1
[9 empty] | 672 | 37.1746 | 1
[9 empty] | 673 | 37.1746 | 1
[9 empty] | 674 | 37.1746 | 1
[9 empty] | 675 | 37.1746 | 1
[9 empty] | 676 | 37.1746 | 1
[9 empty] | 677 | 37.1746 | 1
[9 empty] | 678 | 37.1746 | 1
[9 empty] | 679 | 37.1746 | 1
[9 empty] | 680 | 37.1746 | 1
[9 empty] | 681 | 37.1746 | 1
[9 empty] | 682 | 37.1746 | 1
[9 empty] | 683 | 37.1746 | 1
[9 empty] | 684 | 37.1746 | 1
[9 empty] | 685 | 37.1746 | 1
[9 empty] | 686 | 37.1746 | 1
[9 empty] | 687 | 37.1746 | 1
[9 empty] | 688 | 37.1746 | 1
[9 empty] | 689 | 37.1746 | 1
[9 empty] | 690 | 37.1746 | 1
[9 empty] | 691 | 37.1746 | 1
[9 empty] | 692 | 37.1746 | 1
[9 empty] | 693 | 37.1746 | 1
[9 empty] | 694 | 37.1746 | 1
[9 empty] | 695 | 37.1746 | 1
[9 empty] | 696 | 37.1746 | 1
[9 empty] | 697 | 37.1746 | 1
[9 empty] | 698 | 37.1746 | 1
[9 empty] | 699 | 37.1746 | 1
[9 empty] | 700 | 37.1746 | 1
[9 empty] | 701 | 37.1746 | 1
[9 empty] | 702 | 37.1746 | 1
[9 empty] | 703 | 37.1746 | 1
[9 empty] | 704 | 37.1746 | 1
[9 empty] | 705 | 37.1746 | 1
[9 empty] | 706 | 37.1746 | 1
[9 empty] | 707 | 37.1746 | 1
[9 empty] | 708 | 37.1746 | 1
[9 empty] | 709 | 37.1746 | 1
[9 empty] | 710 | 37.1746 | 1
[9 empty] | 711 | 37.1746 | 1
[9 empty] | 712 | 37.1746 | 1
[9 empty] | 713 | 37.1746 | 1
[9 empty] | 714 | 37.1746 | 1
[9 empty] | 715 | 37.1746 | 1
[9 empty] | 716 | 37.1746 | 1
[9 empty] | 717 | 37.1746 | 1
[9 empty] | 718 | 37.1746 | 1
[9 empty] | 719 | 37.1746 | 1
[9 empty] | 720 | 37.1746 | 1
[9 empty] | 721 | 37.1746 | 1
[9 empty] | 722 | 37.1746 | 1
[9 empty] | 723 | 37.1746 | 1
[9 empty] | 724 | 37.1746 | 1
[9 empty] | 725 | 37.1746 | 1
[9 empty] | 726 | 37.1746 | 1
[9 empty] | 727 | 37.1746 | 1
[9 empty] | 728 | 37.1746 | 1
[9 empty] | 729 | 37.1746 | 1
[9 empty] | 730 | 37.1746 | 1
[9 empty] | 731 | 37.1746 | 1
[9 empty] | 732 | 37.1746 | 1
[9 empty] | 733 | 37.1746 | 1
[9 empty] | 734 | 37.1746 | 1
[9 empty] | 735 | 37.1746 | 1
[9 empty] | 736 | 37.1746 | 1
[9 empty] | 737 | 37.1746 | 1
[9 empty] | 738 | 37.1746 | 1
[9 empty] | 739 | 37.1746 | 1
[9 empty] | 740 | 37.1746 | 1
[9 empty] | 741 | 37.1746 | 1
[9 empty] | 742 | 37.1746 | 1
[9 empty] | 743 | 37.1746 | 1
[9 empty] | 744 | 37.1746 | 1
[9 empty] | 745 | 37.1746 | 1
[9 empty] | 746 | 37.1746 | 1
[9 empty] | 747 | 37.1746 | 1
[9 empty] | 748 | 37.1746 | 1
[9 empty] | 749 | 37.1746 | 1
[9 empty] | 750 | 37.1746 | 1
[9 empty] | 751 | 37.1746 | 1
[9 empty] | 752 | 37.1746 | 1
[9 empty] | 753 | 37.1746 | 1
[9 empty] | 754 | 37.1746 | 1
[9 empty] | 755 | 37.1746 | 1
[9 empty] | 756 | 37.1746 | 1
[9 empty] | 757 | 37.1746 | 1
[9 empty] | 758 | 37.1746 | 1
[9 empty] | 759 | 37.1746 | 1
[9 empty] | 760 | 37.1746 | 1
[9 empty] | 761 | 37.1746 | 1
[9 empty] | 762 | 37.1746 | 1
[9 empty] | 763 | 37.1746 | 1
[9 empty] | 764 | 37.1746 | 1
[9 empty] | 765 | 37.1746 | 1
[9 empty] | 766 | 37.1746 | 1
[9 empty] | 767 | 37.1746 | 1
[9 empty] | 768 | 37.1746 | 1
[9 empty] | 769 | 37.1746 | 1
[9 empty] | 770 | 37.1746 | 1
[9 empty] | 771 | 37.1746 | 1
[9 empty] | 772 | 37.1746 | 1
[9 empty] | 773 | 37.1746 | 1
[9 empty] | 774 | 37.1746 | 1
[9 empty] | 775 | 37.1746 | 1
[9 empty] | 776 | 37.1746 | 1
[9 empty] | 777 | 37.1746 | 1
[9 empty] | 778 | 37.1746 | 1
[9 empty] | 779 | 37.1746 | 1
[9 empty] | 780 | 37.1746 | 1
[9 empty] | 781 | 37.1746 | 1
[9 empty] | 782 | 37.1746 | 1
[9 empty] | 783 | 37.1746 | 1
[9 empty] | 784 | 37.1746 | 1
[9 empty] | 785 | 37.1746 | 1
[9 empty] | 786 | 37.1746 | 1
[9 empty] | 787 | 37.1746 | 1
[9 empty] | 788 | 37.1746 | 1
[9 empty] | 789 | 37.1746 | 1
[9 empty] | 790 | 37.1746 | 1
[9 empty] | 791 | 37.1746 | 1
[9 empty] | 792 | 37.1746 | 1
[9 empty] | 793 | 37.1746 | 1
[9 empty] | 794 | 37.1746 | 1
[9 empty] | 795 | 37.1746 | 1
[9 empty] | 796 | 37.1746 | 1
[9 empty] | 797 | 37.1746 | 1
[9 empty] | 798 | 37.1746 | 1
[9 empty] | 799 | 37.1746 | 1
[9 empty] | 800 | 37.1746 | 1
[9 empty] | 801 | 37.1746 | 1
[9 empty] | 802 | 37.1746 | 1
[9 empty] | 803 | 37.1746 | 1
[9 empty] | 804 | 37.1746 | 1
[9 empty] | 805 | 37.1746 | 1
[9 empty] | 806 | 37.1746 | 1
[9 empty] | 807 | 37.1746 | 1
[9 empty] | 808 | 37.1746 | 1
[9 empty] | 809 | 37.1746 | 1
[9 empty] | 810 | 37.1746 | 1
[9 empty] | 811 | 37.1746 | 1
[9 empty] | 812 | 37.1746 | 1
[9 empty] | 813 | 37.1746 | 1
[9 empty] | 814 | 37.1746 | 1
[9 empty] | 815 | 37.1746 | 1
[9 empty] | 816 | 37.1746 | 1
[9 empty] | 817 | 37.1746 | 1
[9 empty] | 818 | 37.1746 | 1
[9 empty] | 819 | 37.1746 | 1
[9 empty] | 820 | 37.1746 | 1
[9 empty] | 821 | 37.1746 | 1
[9 empty] | 822 | 37.1746 | 1
[9 empty] | 823 | 37.1746 | 1
[9 empty] | 824 | 37.1746 | 1
[9 empty] | 825 | 37.1746 | 1
[9 empty] | 826 | 37.1746 | 1
[9 empty] | 827 | 37.1746 | 1
[9 empty] | 828 | 37.1746 | 1
[9 empty] | 829 | 37.1746 | 1
[9 empty] | 830 | 37.1746 | 1
[9 empty] | 831 | 37.1746 | 1
[9 empty] | 832 | 37.1746 | 1
[9 empty] | 833 | 37.1746 | 1
[9 empty] | 834 | 37.1746 | 1
[9 empty] | 835 | 37.1746 | 1
[9 empty] | 836 | 37.1746 | 1
[9 empty] | 837 | 37.1746 | 1
[9 empty] | 838 | 37.1746 | 1
[9 empty] | 839 | 37.1746 | 1
[9 empty] | 840 | 37.1746 | 1
[9 empty] | 841 | 37.1746 | 1
[9 empty] | 842 | 37.1746 | 1
[9 empty] | 843 | 37.1746 | 1
[9 empty] | 844 | 37.1746 | 1
[9 empty] | 845 | 37.1746 | 1
[9 empty] | 846 | 37.1746 | 1
[9 empty] | 847 | 37.1746 | 1
[9 empty] | 848 | 37.1746 | 1
[9 empty] | 849 | 37.1746 | 1
[9 empty] | 850 | 37.1746 | 1
[9 empty] | 851 | 37.1746 | 1
[9 empty] | 852 | 37.1746 | 1
[9 empty] | 853 | 37.1746 | 1
[9 empty] | 854 | 37.1746 | 1
[9 empty] | 855 | 37.1746 | 1
[9 empty] | 856 | 37.1746 | 1
[9 empty] | 857 | 37.1746 | 1
[9 empty] | 858 | 37.1746 | 1
[9 empty] | 859 | 37.1746 | 1
[9 empty] | 860 | 37.1746 | 1
[9 empty] | 861 | 37.1746 | 1
[9 empty] | 862 | 37.1746 | 1
[9 empty] | 863 | 37.1746 | 1
[9 empty] | 864 | 37.1746 | 1
[9 empty] | 865 | 37.1746 | 1
[9 empty] | 866 | 37.1746 | 1
[9 empty] | 867 | 37.1746 | 1
[9 empty] | 868 | 37.1746 | 1
[9 empty] | 869 | 37.1746 | 1
[9 empty] | 870 | 37.1746 | 1
[9 empty] | 871 | 37.1746 | 1
[9 empty] | 872 | 37.1746 | 1
[9 empty] | 873 | 37.1746 | 1
[9 empty] | 874 | 37.1746 | 1
[9 empty] | 875 | 37.1746 | 1
[9 empty] | 876 | 37.1746 | 1
[9 empty] | 877 | 37.1746 | 1
[9 empty] | 878 | 37.1746 | 1
[9 empty] | 879 | 37.1746 | 1
[9 empty] | 880 | 37.1746 | 1
[9 empty] | 881 | 37.1746 | 1
[9 empty] | 882 | 37.1746 | 1
[9 empty] | 883 | 37.1746 | 1
[9 empty] | 884 | 37.1746 | 1
[9 empty] | 885 | 37.1746 | 1
[9 empty] | 886 | 37.1746 | 1
[9 empty] | 887 | 37.1746 | 1
[9 empty] | 888 | 37.1746 | 1
[9 empty] | 889 | 37.1746 | 1
[9 empty] | 890 | 37.1746 | 1
[9 empty] | 891 | 37.1746 | 1
[9 empty] | 892 | 37.1746 | 1
[9 empty] | 893 | 37.1746 | 1
[9 empty] | 894 | 37.1746 | 1
[9 empty] | 895 | 37.1746 | 1
[9 empty] | 896 | 37.1746 | 1
[9 empty] | 897 | 37.1746 | 1
[9 empty] | 898 | 37.1746 | 1
[9 empty] | 899 | 37.1746 | 1
[9 empty] | 900 | 37.1746 | 1
[9 empty] | 901 | 37.1746 | 1
[9 empty] | 902 | 37.1746 | 1
[9 empty] | 903 | 37.1746 | 1
[9 empty] | 904 | 37.1746 | 1
[9 empty] | 905 | 37.1746 | 1
[9 empty] | 906 | 37.1746 | 1
[9 empty] | 907 | 37.1746 | 1
[9 empty] | 908 | 37.1746 | 1
[9 empty] | 909 | 37.1746 | 1
[9 empty] | 910 | 37.1746 | 1
[9 empty] | 911 | 37.1746 | 1
[9 empty] | 912 | 37.1746 | 1
[9 empty] | 913 | 37.1746 | 1
[9 empty] | 914 | 37.1746 | 1
[9 empty] | 915 | 37.1746 | 1
[9 empty] | 916 | 37.1746 | 1
[9 empty] | 917 | 37.1746 | 1
[9 empty] | 918 | 37.1746 | 1
[9 empty] | 919 | 37.1746 | 1
[9 empty] | 920 | 37.1746 | 1
[9 empty] | 921 | 37.1746 | 1
[9 empty] | 922 | 37.1746 | 1
[9 empty] | 923 | 37.1746 | 1
[9 empty] | 924 | 37.1746 | 1
[9 empty] | 925 | 37.1746 | 1
[9 empty] | 926 | 37.1746 | 1
[9 empty] | 927 | 37.1746 | 1
[9 empty] | 928 | 37.1746 | 1
[9 empty] | 929 | 37.1746 | 1
[9 empty] | 930 | 37.1746 | 1
[9 empty] | 931 | 37.1746 | 1
[9 empty] | 932 | 37.1746 | 1
[9 empty] | 933 | 37.1746 | 1
[9 empty] | 934 | 37.1746 | 1
[9 empty] | 935 | 37.1746 | 1
[9 empty] | 936 | 37.1746 | 1
[9 empty] | 937 | 37.1746 | 1
[9 empty] | 938 | 37.1746 | 1
[9 empty] | 939 | 37.1746 | 1
[9 empty] | 940 | 37.1746 | 1
[9 empty] | 941 | 37.1746 | 1
[9 empty] | 942 | 37.1746 | 1
[9 empty] | 943 | 37.1746 | 1
[9 empty] | 944 | 37.1746 | 1
[9 empty] | 945 | 37.1746 | 1
[9 empty] | 946 | 37.1746 | 1
[9 empty] | 947 | 37.1746 | 1
[9 empty] | 948 | 37.1746 | 1
[9 empty] | 949 | 37.1746 | 1
[9 empty] | 950 | 37.1746 | 1
[9 empty] | 951 | 37.1746 | 1
[9 empty] | 952 | 37.1746 | 1
[9 empty] | 953 | 37.1746 | 1
[9 empty] | 954 | 37.1746 | 1
[9 empty] | 955 | 37.1746 | 1
[9 empty] | 956 | 37.1746 | 1
[9 empty] | 957 | 37.1746 | 1
[9 empty] | 958 | 37.1746 | 1
[9 empty] | 959 | 37.1746 | 1
[9 empty] | 960 | 37.1746 | 1
[9 empty] | 961 | 37.1746 | 1
[9 empty] | 962 | 37.1746 | 1
[9 empty] | 963 | 37.1746 | 1
[9 empty] | 964 | 37.1746 | 1
[9 empty] | 965 | 37.1746 | 1
[9 empty] | 966 | 37.1746 | 1
[9 empty] | 967 | 37.1746 | 1
[9 empty] | 968 | 37.1746 | 1
[9 empty] | 969 | 37.1746 | 1
[9 empty] | 970 | 37.1746 | 1
[9 empty] | 971 | 37.1746 | 1
[9 empty] | 972 | 37.1746 | 1
[9 empty] | 973 | 37.1746 | 1
[9 empty] | 974 | 37.1746 | 1
[9 empty] | 975 | 37.1746 | 1
[9 empty] | 976 | 37.1746 | 1
[9 empty] | 977 | 37.1746 | 1
[9 empty] | 978 | 37.1746 | 1
[9 empty] | 979 | 37.1746 | 1
[9 empty] | 980 | 37.1746 | 1
[9 empty] | 981 | 37.1746 | 1
[9 empty] | 982 | 37.1746 | 1
[9 empty] | 983 | 37.1746 | 1
[9 empty] | 984 | 37.1746 | 1
[9 empty] | 985 | 37.1746 | 1
[9 empty] | 986 | 37.1746 | 1
[9 empty] | 987 | 37.1746 | 1
[9 empty] | 988 | 37.1746 | 1
[9 empty] | 989 | 37.1746 | 1
[9 empty] | 990 | 37.1746 | 1
[9 empty] | 991 | 37.1746 | 1
[9 empty] | 992 | 37.1746 | 1
[9 empty] | 993 | 37.1746 | 1
[9 empty] | 994 | 37.1746 | 1
[9 empty] | 995 | 37.1746 | 1
[9 empty] | 996 | 37.1746 | 1
[9 empty] | 997 | 37.1746 | 1
[9 empty] | 998 | 37.1746 | 1
[9 empty] | 999 | 37.1746 | 1
[9 empty] | 1000 | 37.1746 | 1

## Project-2 RT(a,b)
Project 1 | [8 empty] | Trial | Project Duration | Success
Task | Immediate Ancestor | a | m | b | Start Time | U(0,1) | Duration | Finsih Time |  | 39.2618 | 1
A |  | 1 | 3 | 4 | 0 | 0.86626 | 3.5988 | 3.5988 | 1 | 33.9792 | 1
B |  | 5 | 7 | 8 | 0 | 0.17513 | 7.5381 | 7.5381 | 2 | 33.6999 | 1
C |  | 6 | 7 | 9 | 0 | 0.86477 | 8.678 | 8.678 | 3 | 36.8028 | 1
D |  | 1 | 2 | 3 | 0 | 0.23121 | 2.349 | 2.349 | 4 | 36.5484 | 1
E | A | 3 | 4 | 5 | 3.5988 | 0.56983 | 4.3608 | 7.9595 | 5 | 35.1821 | 1
F | A | 7 | 8 | 9 | 3.5988 | 0.30432 | 7.6086 | 11.2074 | 6 | 33.1435 | 1
G | B,E | 10 | 15 | 20 | 7.9595 | 0.89927 | 18.9927 | 26.9523 | 7 | 34.9486 | 1
H | B,E | 12 | 13 | 14 | 7.9595 | 0.74529 | 13.4906 | 21.4501 | 8 | 35.1587 | 1
I | C | 10 | 12 | 15 | 8.678 | 0.86097 | 14.3049 | 22.9828 | 9 | 36.4929 | 1
J | C | 8 | 10 | 12 | 8.678 | 0.064758 | 9.9067 | 18.5846 | 10 | 33.2835 | 1
K | F,I | 7 | 8 | 11 | 22.9828 | 0.22279 | 10.9963 | 33.9791 | 11 | 34.4043 | 1
L | F,I | 2 | 4 | 8 | 22.9828 | 0.53886 | 7.4968 | 30.4797 | 12 | 32.0449 | 1
M | D,K | 5 | 6 | 7 | 33.9791 | 0.14135 | 5.2827 | 39.2618 | 13 | 38.2146 | 1
N | H,J,L,M | 0 | 0 | 0 | 39.2618 | 0.59538 | 0 | 39.2618 | 14 | 35.4228 | 1
[9 empty] | 15 | 31.8312 | 1
[9 empty] | 16 | 34.7157 | 1
[9 empty] | 17 | 35.1396 | 1
[9 empty] | 18 | 32.5736 | 1
Deadline | Average Project Duration | Avg Success Rate | [6 empty] | 19 | 35.4822 | 1
48 | 34.1692 | 100 | [6 empty] | 20 | 33.778 | 1
[9 empty] | 21 | 36.5762 | 1
[9 empty] | 22 | 37.3895 | 1
[9 empty] | 23 | 34.8857 | 1
[9 empty] | 24 | 35.2017 | 1
[9 empty] | 25 | 35.1743 | 1
[9 empty] | 26 | 33.994 | 1
[9 empty] | 27 | 34.5918 | 1
[9 empty] | 28 | 35.3977 | 1
[9 empty] | 29 | 34.2225 | 1
[9 empty] | 30 | 33.9004 | 1
[9 empty] | 31 | 35.3639 | 1
[9 empty] | 32 | 36.1552 | 1
[9 empty] | 33 | 33.1995 | 1
[9 empty] | 34 | 32.8046 | 1
[9 empty] | 35 | 34.8434 | 1
[9 empty] | 36 | 34.0158 | 1
[9 empty] | 37 | 33.6903 | 1
[9 empty] | 38 | 33.4761 | 1
[9 empty] | 39 | 32.5115 | 1
[9 empty] | 40 | 34.7765 | 1
[9 empty] | 41 | 33.7756 | 1
[9 empty] | 42 | 32.2571 | 1
[9 empty] | 43 | 35.334 | 1
[9 empty] | 44 | 32.1273 | 1
[9 empty] | 45 | 32.8268 | 1
[9 empty] | 46 | 34.0181 | 1
[9 empty] | 47 | 33.6884 | 1
[9 empty] | 48 | 35.6828 | 1
[9 empty] | 49 | 35.1376 | 1
[9 empty] | 50 | 32.1143 | 1
[9 empty] | 51 | 33.3993 | 1
[9 empty] | 52 | 34.9468 | 1
[9 empty] | 53 | 34.1068 | 1
[9 empty] | 54 | 35.0634 | 1
[9 empty] | 55 | 32.7803 | 1
[9 empty] | 56 | 33.7623 | 1
[9 empty] | 57 | 36.0713 | 1
[9 empty] | 58 | 34.6613 | 1
[9 empty] | 59 | 35.1525 | 1
[9 empty] | 60 | 35.7185 | 1
[9 empty] | 61 | 32.9514 | 1
[9 empty] | 62 | 35.4376 | 1
[9 empty] | 63 | 33.4178 | 1
[9 empty] | 64 | 31.0134 | 1
[9 empty] | 65 | 30.9045 | 1
[9 empty] | 66 | 35.5114 | 1
[9 empty] | 67 | 35.032 | 1
[9 empty] | 68 | 33.3885 | 1
[9 empty] | 69 | 34.8304 | 1
[9 empty] | 70 | 32.9566 | 1
[9 empty] | 71 | 32.2612 | 1
[9 empty] | 72 | 35.0914 | 1
[9 empty] | 73 | 35.2009 | 1
[9 empty] | 74 | 33.8991 | 1
[9 empty] | 75 | 33.1648 | 1
[9 empty] | 76 | 32.2074 | 1
[9 empty] | 77 | 34.244 | 1
[9 empty] | 78 | 33.982 | 1
[9 empty] | 79 | 32.1244 | 1
[9 empty] | 80 | 35.2069 | 1
[9 empty] | 81 | 34.9753 | 1
[9 empty] | 82 | 32.3962 | 1
[9 empty] | 83 | 34.2588 | 1
[9 empty] | 84 | 35.7819 | 1
[9 empty] | 85 | 31.6321 | 1
[9 empty] | 86 | 33.993 | 1
[9 empty] | 87 | 33.4224 | 1
[9 empty] | 88 | 32.7231 | 1
[9 empty] | 89 | 36.2394 | 1
[9 empty] | 90 | 33.6253 | 1
[9 empty] | 91 | 36.936 | 1
[9 empty] | 92 | 36.0952 | 1
[9 empty] | 93 | 35.5244 | 1
[9 empty] | 94 | 35.6531 | 1
[9 empty] | 95 | 34.1974 | 1
[9 empty] | 96 | 34.431 | 1
[9 empty] | 97 | 31.072 | 1
[9 empty] | 98 | 34.322 | 1
[9 empty] | 99 | 33.4648 | 1
[9 empty] | 100 | 34.2691 | 1
[9 empty] | 101 | 33.5209 | 1
[9 empty] | 102 | 36.7146 | 1
[9 empty] | 103 | 36.1457 | 1
[9 empty] | 104 | 33.5997 | 1
[9 empty] | 105 | 32.8895 | 1
[9 empty] | 106 | 35.7396 | 1
[9 empty] | 107 | 36.7397 | 1
[9 empty] | 108 | 33.0481 | 1
[9 empty] | 109 | 32.6206 | 1
[9 empty] | 110 | 35.5 | 1
[9 empty] | 111 | 31.9698 | 1
[9 empty] | 112 | 36.9752 | 1
[9 empty] | 113 | 33.8011 | 1
[9 empty] | 114 | 34.2794 | 1
[9 empty] | 115 | 35.2822 | 1
[9 empty] | 116 | 34.2927 | 1
[9 empty] | 117 | 34.4978 | 1
[9 empty] | 118 | 33.9032 | 1
[9 empty] | 119 | 32.754 | 1
[9 empty] | 120 | 34.5898 | 1
[9 empty] | 121 | 36.6276 | 1
[9 empty] | 122 | 35.5944 | 1
[9 empty] | 123 | 34.6356 | 1
[9 empty] | 124 | 31.9823 | 1
[9 empty] | 125 | 34.2558 | 1
[9 empty] | 126 | 34.3791 | 1
[9 empty] | 127 | 34.1771 | 1
[9 empty] | 128 | 34.1887 | 1
[9 empty] | 129 | 34.2862 | 1
[9 empty] | 130 | 33.2838 | 1
[9 empty] | 131 | 34.9997 | 1
[9 empty] | 132 | 34.0879 | 1
[9 empty] | 133 | 33.8297 | 1
[9 empty] | 134 | 34.1137 | 1
[9 empty] | 135 | 35.2865 | 1
[9 empty] | 136 | 35.6673 | 1
[9 empty] | 137 | 35.0078 | 1
[9 empty] | 138 | 33.6501 | 1
[9 empty] | 139 | 34.4367 | 1
[9 empty] | 140 | 35.6093 | 1
[9 empty] | 141 | 35.6045 | 1
[9 empty] | 142 | 33.1556 | 1
[9 empty] | 143 | 36.9893 | 1
[9 empty] | 144 | 34.3449 | 1
[9 empty] | 145 | 38.0297 | 1
[9 empty] | 146 | 36.4435 | 1
[9 empty] | 147 | 32.8263 | 1
[9 empty] | 148 | 36.8748 | 1
[9 empty] | 149 | 32.0569 | 1
[9 empty] | 150 | 33.0795 | 1
[9 empty] | 151 | 32.0357 | 1
[9 empty] | 152 | 31.7846 | 1
[9 empty] | 153 | 32.4668 | 1
[9 empty] | 154 | 35.6762 | 1
[9 empty] | 155 | 32.5823 | 1
[9 empty] | 156 | 36.4795 | 1
[9 empty] | 157 | 31.3122 | 1
[9 empty] | 158 | 32.4187 | 1
[9 empty] | 159 | 35.6624 | 1
[9 empty] | 160 | 36.0183 | 1
[9 empty] | 161 | 34.0744 | 1
[9 empty] | 162 | 34.6887 | 1
[9 empty] | 163 | 36.2982 | 1
[9 empty] | 164 | 31.6601 | 1
[9 empty] | 165 | 35.578 | 1
[9 empty] | 166 | 37.2724 | 1
[9 empty] | 167 | 33.48 | 1
[9 empty] | 168 | 30.8539 | 1
[9 empty] | 169 | 33.9616 | 1
[9 empty] | 170 | 35.4899 | 1
[9 empty] | 171 | 31.7558 | 1
[9 empty] | 172 | 34.3266 | 1
[9 empty] | 173 | 32.337 | 1
[9 empty] | 174 | 35.6483 | 1
[9 empty] | 175 | 33.982 | 1
[9 empty] | 176 | 34.9091 | 1
[9 empty] | 177 | 34.6252 | 1
[9 empty] | 178 | 34.6829 | 1
[9 empty] | 179 | 34.7594 | 1
[9 empty] | 180 | 35.4515 | 1
[9 empty] | 181 | 33.872 | 1
[9 empty] | 182 | 34.4487 | 1
[9 empty] | 183 | 33.3459 | 1
[9 empty] | 184 | 32.6278 | 1
[9 empty] | 185 | 36.5098 | 1
[9 empty] | 186 | 34.128 | 1
[9 empty] | 187 | 32.7319 | 1
[9 empty] | 188 | 33.2011 | 1
[9 empty] | 189 | 35.1537 | 1
[9 empty] | 190 | 34.3606 | 1
[9 empty] | 191 | 32.5971 | 1
[9 empty] | 192 | 33.4918 | 1
[9 empty] | 193 | 33.6463 | 1
[9 empty] | 194 | 34.6177 | 1
[9 empty] | 195 | 33.2264 | 1
[9 empty] | 196 | 33.3448 | 1
[9 empty] | 197 | 35.5704 | 1
[9 empty] | 198 | 36.3672 | 1
[9 empty] | 199 | 33.7574 | 1
[9 empty] | 200 | 33.1125 | 1
[9 empty] | 201 | 35.9646 | 1
[9 empty] | 202 | 33.4928 | 1
[9 empty] | 203 | 35.3151 | 1
[9 empty] | 204 | 33.672 | 1
[9 empty] | 205 | 34.3145 | 1
[9 empty] | 206 | 32.1852 | 1
[9 empty] | 207 | 36.1986 | 1
[9 empty] | 208 | 37.0513 | 1
[9 empty] | 209 | 35.3683 | 1
[9 empty] | 210 | 34.1375 | 1
[9 empty] | 211 | 32.641 | 1
[9 empty] | 212 | 35.7552 | 1
[9 empty] | 213 | 32.8083 | 1
[9 empty] | 214 | 35.3158 | 1
[9 empty] | 215 | 32.8448 | 1
[9 empty] | 216 | 33.4223 | 1
[9 empty] | 217 | 33.4456 | 1
[9 empty] | 218 | 36.7805 | 1
[9 empty] | 219 | 33.3194 | 1
[9 empty] | 220 | 33.5492 | 1
[9 empty] | 221 | 34.5743 | 1
[9 empty] | 222 | 36.4299 | 1
[9 empty] | 223 | 34.3771 | 1
[9 empty] | 224 | 33.1642 | 1
[9 empty] | 225 | 32.6825 | 1
[9 empty] | 226 | 32.6173 | 1
[9 empty] | 227 | 30.7771 | 1
[9 empty] | 228 | 36.3202 | 1
[9 empty] | 229 | 33.8284 | 1
[9 empty] | 230 | 35.5034 | 1
[9 empty] | 231 | 32.8121 | 1
[9 empty] | 232 | 33.8175 | 1
[9 empty] | 233 | 33.6821 | 1
[9 empty] | 234 | 35.8153 | 1
[9 empty] | 235 | 35.033 | 1
[9 empty] | 236 | 32.0313 | 1
[9 empty] | 237 | 31.7423 | 1
[9 empty] | 238 | 34.8332 | 1
[9 empty] | 239 | 36.5391 | 1
[9 empty] | 240 | 30.579 | 1
[9 empty] | 241 | 33.254 | 1
[9 empty] | 242 | 33.1669 | 1
[9 empty] | 243 | 32.792 | 1
[9 empty] | 244 | 35.339 | 1
[9 empty] | 245 | 33.7114 | 1
[9 empty] | 246 | 33.936 | 1
[9 empty] | 247 | 35.6935 | 1
[9 empty] | 248 | 32.1739 | 1
[9 empty] | 249 | 33.451 | 1
[9 empty] | 250 | 33.0073 | 1
[9 empty] | 251 | 32.8627 | 1
[9 empty] | 252 | 33.9277 | 1
[9 empty] | 253 | 34.612 | 1
[9 empty] | 254 | 33.1833 | 1
[9 empty] | 255 | 36.2843 | 1
[9 empty] | 256 | 32.0159 | 1
[9 empty] | 257 | 34.2296 | 1
[9 empty] | 258 | 32.3103 | 1
[9 empty] | 259 | 35.2631 | 1
[9 empty] | 260 | 32.0557 | 1
[9 empty] | 261 | 34.8749 | 1
[9 empty] | 262 | 33.6888 | 1
[9 empty] | 263 | 35.3787 | 1
[9 empty] | 264 | 32.4429 | 1
[9 empty] | 265 | 33.0499 | 1
[9 empty] | 266 | 34.6896 | 1
[9 empty] | 267 | 35.4621 | 1
[9 empty] | 268 | 33.4532 | 1
[9 empty] | 269 | 36.7204 | 1
[9 empty] | 270 | 33.1382 | 1
[9 empty] | 271 | 36.1472 | 1
[9 empty] | 272 | 34.483 | 1
[9 empty] | 273 | 36.0484 | 1
[9 empty] | 274 | 31.5575 | 1
[9 empty] | 275 | 32.1704 | 1
[9 empty] | 276 | 34.5482 | 1
[9 empty] | 277 | 34.3198 | 1
[9 empty] | 278 | 33.0983 | 1
[9 empty] | 279 | 32.9788 | 1
[9 empty] | 280 | 34.4523 | 1
[9 empty] | 281 | 37.1735 | 1
[9 empty] | 282 | 33.9596 | 1
[9 empty] | 283 | 34.6621 | 1
[9 empty] | 284 | 31.0544 | 1
[9 empty] | 285 | 33.7572 | 1
[9 empty] | 286 | 30.9436 | 1
[9 empty] | 287 | 33.0978 | 1
[9 empty] | 288 | 33.7148 | 1
[9 empty] | 289 | 34.1068 | 1
[9 empty] | 290 | 34.3287 | 1
[9 empty] | 291 | 36.1049 | 1
[9 empty] | 292 | 37.1617 | 1
[9 empty] | 293 | 36.331 | 1
[9 empty] | 294 | 32.6418 | 1
[9 empty] | 295 | 33.7863 | 1
[9 empty] | 296 | 32.5244 | 1
[9 empty] | 297 | 33.2861 | 1
[9 empty] | 298 | 34.6409 | 1
[9 empty] | 299 | 34.3903 | 1
[9 empty] | 300 | 34.0866 | 1
[9 empty] | 301 | 33.9844 | 1
[9 empty] | 302 | 33.4665 | 1
[9 empty] | 303 | 34.0101 | 1
[9 empty] | 304 | 34.0854 | 1
[9 empty] | 305 | 35.3198 | 1
[9 empty] | 306 | 34.2137 | 1
[9 empty] | 307 | 33.7817 | 1
[9 empty] | 308 | 34.0315 | 1
[9 empty] | 309 | 33.6525 | 1
[9 empty] | 310 | 37.1116 | 1
[9 empty] | 311 | 34.2811 | 1
[9 empty] | 312 | 34.8441 | 1
[9 empty] | 313 | 33.2377 | 1
[9 empty] | 314 | 36.5036 | 1
[9 empty] | 315 | 33.3742 | 1
[9 empty] | 316 | 32.7458 | 1
[9 empty] | 317 | 33.7227 | 1
[9 empty] | 318 | 32.2669 | 1
[9 empty] | 319 | 36.4536 | 1
[9 empty] | 320 | 32.2526 | 1
[9 empty] | 321 | 31.9716 | 1
[9 empty] | 322 | 35.0062 | 1
[9 empty] | 323 | 35.8684 | 1
[9 empty] | 324 | 31.5923 | 1
[9 empty] | 325 | 34.9524 | 1
[9 empty] | 326 | 35.1993 | 1
[9 empty] | 327 | 33.4072 | 1
[9 empty] | 328 | 34.195 | 1
[9 empty] | 329 | 34.1726 | 1
[9 empty] | 330 | 34.183 | 1
[9 empty] | 331 | 33.8302 | 1
[9 empty] | 332 | 33.4819 | 1
[9 empty] | 333 | 34.7763 | 1
[9 empty] | 334 | 34.5399 | 1
[9 empty] | 335 | 31.0653 | 1
[9 empty] | 336 | 35.8212 | 1
[9 empty] | 337 | 33.8034 | 1
[9 empty] | 338 | 32.6157 | 1
[9 empty] | 339 | 34.7784 | 1
[9 empty] | 340 | 34.0212 | 1
[9 empty] | 341 | 35.4917 | 1
[9 empty] | 342 | 33.8171 | 1
[9 empty] | 343 | 33.3396 | 1
[9 empty] | 344 | 34.9677 | 1
[9 empty] | 345 | 32.2066 | 1
[9 empty] | 346 | 33.9776 | 1
[9 empty] | 347 | 34.6677 | 1
[9 empty] | 348 | 36.1824 | 1
[9 empty] | 349 | 34.2856 | 1
[9 empty] | 350 | 37.0185 | 1
[9 empty] | 351 | 35.2092 | 1
[9 empty] | 352 | 35.003 | 1
[9 empty] | 353 | 34.6543 | 1
[9 empty] | 354 | 35.9627 | 1
[9 empty] | 355 | 35.8737 | 1
[9 empty] | 356 | 30.7238 | 1
[9 empty] | 357 | 32.857 | 1
[9 empty] | 358 | 31.6134 | 1
[9 empty] | 359 | 33.445 | 1
[9 empty] | 360 | 32.6458 | 1
[9 empty] | 361 | 31.6285 | 1
[9 empty] | 362 | 35.8498 | 1
[9 empty] | 363 | 32.3591 | 1
[9 empty] | 364 | 32.6505 | 1
[9 empty] | 365 | 35.5676 | 1
[9 empty] | 366 | 35.2504 | 1
[9 empty] | 367 | 34.3187 | 1
[9 empty] | 368 | 32.5002 | 1
[9 empty] | 369 | 32.8949 | 1
[9 empty] | 370 | 35.793 | 1
[9 empty] | 371 | 33.9459 | 1
[9 empty] | 372 | 36.0335 | 1
[9 empty] | 373 | 33.7137 | 1
[9 empty] | 374 | 33.2023 | 1
[9 empty] | 375 | 35.5101 | 1
[9 empty] | 376 | 35.9094 | 1
[9 empty] | 377 | 33.5307 | 1
[9 empty] | 378 | 33.7583 | 1
[9 empty] | 379 | 33.3516 | 1
[9 empty] | 380 | 30.8833 | 1
[9 empty] | 381 | 32.2888 | 1
[9 empty] | 382 | 35.8046 | 1
[9 empty] | 383 | 35.8111 | 1
[9 empty] | 384 | 31.9129 | 1
[9 empty] | 385 | 34.7264 | 1
[9 empty] | 386 | 35.7858 | 1
[9 empty] | 387 | 33.0347 | 1
[9 empty] | 388 | 33.1944 | 1
[9 empty] | 389 | 32.1201 | 1
[9 empty] | 390 | 34.1886 | 1
[9 empty] | 391 | 32.8972 | 1
[9 empty] | 392 | 35.1592 | 1
[9 empty] | 393 | 34.595 | 1
[9 empty] | 394 | 36.6956 | 1
[9 empty] | 395 | 36.6146 | 1
[9 empty] | 396 | 35.2898 | 1
[9 empty] | 397 | 31.6002 | 1
[9 empty] | 398 | 33.345 | 1
[9 empty] | 399 | 36.8578 | 1
[9 empty] | 400 | 33.5783 | 1
[9 empty] | 401 | 33.0135 | 1
[9 empty] | 402 | 34.4982 | 1
[9 empty] | 403 | 32.4384 | 1
[9 empty] | 404 | 34.0286 | 1
[9 empty] | 405 | 34.2755 | 1
[9 empty] | 406 | 33.3081 | 1
[9 empty] | 407 | 36.1546 | 1
[9 empty] | 408 | 35.1911 | 1
[9 empty] | 409 | 35.6469 | 1
[9 empty] | 410 | 34.0274 | 1
[9 empty] | 411 | 33.0369 | 1
[9 empty] | 412 | 36.2795 | 1
[9 empty] | 413 | 34.59 | 1
[9 empty] | 414 | 32.9581 | 1
[9 empty] | 415 | 32.9453 | 1
[9 empty] | 416 | 33.4372 | 1
[9 empty] | 417 | 34.2475 | 1
[9 empty] | 418 | 36.3878 | 1
[9 empty] | 419 | 32.2021 | 1
[9 empty] | 420 | 35.1162 | 1
[9 empty] | 421 | 33.4422 | 1
[9 empty] | 422 | 34.3174 | 1
[9 empty] | 423 | 37.5869 | 1
[9 empty] | 424 | 35.5444 | 1
[9 empty] | 425 | 36.5131 | 1
[9 empty] | 426 | 33.6496 | 1
[9 empty] | 427 | 33.3469 | 1
[9 empty] | 428 | 33.431 | 1
[9 empty] | 429 | 33.8046 | 1
[9 empty] | 430 | 35.142 | 1
[9 empty] | 431 | 33.5118 | 1
[9 empty] | 432 | 35.4261 | 1
[9 empty] | 433 | 32.9635 | 1
[9 empty] | 434 | 34.3051 | 1
[9 empty] | 435 | 34.603 | 1
[9 empty] | 436 | 31.9766 | 1
[9 empty] | 437 | 36.4241 | 1
[9 empty] | 438 | 35.1424 | 1
[9 empty] | 439 | 36.0746 | 1
[9 empty] | 440 | 35.8163 | 1
[9 empty] | 441 | 33.473 | 1
[9 empty] | 442 | 31.7443 | 1
[9 empty] | 443 | 35.1008 | 1
[9 empty] | 444 | 34.4233 | 1
[9 empty] | 445 | 32.2593 | 1
[9 empty] | 446 | 35.947 | 1
[9 empty] | 447 | 34.763 | 1
[9 empty] | 448 | 31.9948 | 1
[9 empty] | 449 | 35.2529 | 1
[9 empty] | 450 | 34.5208 | 1
[9 empty] | 451 | 33.3742 | 1
[9 empty] | 452 | 35.8991 | 1
[9 empty] | 453 | 33.511 | 1
[9 empty] | 454 | 34.8382 | 1
[9 empty] | 455 | 33.2847 | 1
[9 empty] | 456 | 31.9859 | 1
[9 empty] | 457 | 34.9741 | 1
[9 empty] | 458 | 31.2658 | 1
[9 empty] | 459 | 33.9106 | 1
[9 empty] | 460 | 36.2284 | 1
[9 empty] | 461 | 33.0252 | 1
[9 empty] | 462 | 32.7205 | 1
[9 empty] | 463 | 35.3679 | 1
[9 empty] | 464 | 33.8203 | 1
[9 empty] | 465 | 32.302 | 1
[9 empty] | 466 | 34.3354 | 1
[9 empty] | 467 | 36.011 | 1
[9 empty] | 468 | 33.1039 | 1
[9 empty] | 469 | 32.6148 | 1
[9 empty] | 470 | 36.1782 | 1
[9 empty] | 471 | 34.311 | 1
[9 empty] | 472 | 34.1359 | 1
[9 empty] | 473 | 33.4264 | 1
[9 empty] | 474 | 35.2625 | 1
[9 empty] | 475 | 32.2605 | 1
[9 empty] | 476 | 33.7849 | 1
[9 empty] | 477 | 33.7787 | 1
[9 empty] | 478 | 34.9501 | 1
[9 empty] | 479 | 33.2616 | 1
[9 empty] | 480 | 35.0305 | 1
[9 empty] | 481 | 34.19 | 1
[9 empty] | 482 | 32.3687 | 1
[9 empty] | 483 | 32.2339 | 1
[9 empty] | 484 | 33.8467 | 1
[9 empty] | 485 | 32.1322 | 1
[9 empty] | 486 | 35.8178 | 1
[9 empty] | 487 | 33.4703 | 1
[9 empty] | 488 | 35.6559 | 1
[9 empty] | 489 | 31.5265 | 1
[9 empty] | 490 | 36.2881 | 1
[9 empty] | 491 | 34.9809 | 1
[9 empty] | 492 | 36.0146 | 1
[9 empty] | 493 | 34.4252 | 1
[9 empty] | 494 | 31.2905 | 1
[9 empty] | 495 | 35.5668 | 1
[9 empty] | 496 | 32.4089 | 1
[9 empty] | 497 | 36.4378 | 1
[9 empty] | 498 | 37.2773 | 1
[9 empty] | 499 | 33.3486 | 1
[9 empty] | 500 | 35.5575 | 1
[9 empty] | 501 | 36.3124 | 1
[9 empty] | 502 | 34.9317 | 1
[9 empty] | 503 | 35.4871 | 1
[9 empty] | 504 | 33.9115 | 1
[9 empty] | 505 | 34.3329 | 1
[9 empty] | 506 | 33.4717 | 1
[9 empty] | 507 | 33.1091 | 1
[9 empty] | 508 | 36.504 | 1
[9 empty] | 509 | 34.7589 | 1
[9 empty] | 510 | 33.4813 | 1
[9 empty] | 511 | 36.0578 | 1
[9 empty] | 512 | 32.3362 | 1
[9 empty] | 513 | 34.578 | 1
[9 empty] | 514 | 34.8796 | 1
[9 empty] | 515 | 33.6899 | 1
[9 empty] | 516 | 32.6696 | 1
[9 empty] | 517 | 35.359 | 1
[9 empty] | 518 | 35.3558 | 1
[9 empty] | 519 | 34.3052 | 1
[9 empty] | 520 | 30.8498 | 1
[9 empty] | 521 | 35.2733 | 1
[9 empty] | 522 | 34.326 | 1
[9 empty] | 523 | 33.0304 | 1
[9 empty] | 524 | 32.8754 | 1
[9 empty] | 525 | 32.7339 | 1
[9 empty] | 526 | 33.4355 | 1
[9 empty] | 527 | 32.6054 | 1
[9 empty] | 528 | 32.2117 | 1
[9 empty] | 529 | 34.0118 | 1
[9 empty] | 530 | 31.3627 | 1
[9 empty] | 531 | 33.9972 | 1
[9 empty] | 532 | 33.5934 | 1
[9 empty] | 533 | 33.772 | 1
[9 empty] | 534 | 32.4448 | 1
[9 empty] | 535 | 34.4946 | 1
[9 empty] | 536 | 33.5275 | 1
[9 empty] | 537 | 33.3922 | 1
[9 empty] | 538 | 33.3552 | 1
[9 empty] | 539 | 35.3866 | 1
[9 empty] | 540 | 34.9614 | 1
[9 empty] | 541 | 32.4158 | 1
[9 empty] | 542 | 32.5542 | 1
[9 empty] | 543 | 36.9053 | 1
[9 empty] | 544 | 33.549 | 1
[9 empty] | 545 | 34.6079 | 1
[9 empty] | 546 | 33.4175 | 1
[9 empty] | 547 | 34.9394 | 1
[9 empty] | 548 | 34.4183 | 1
[9 empty] | 549 | 33.2573 | 1
[9 empty] | 550 | 34.465 | 1
[9 empty] | 551 | 32.3585 | 1
[9 empty] | 552 | 34.7427 | 1
[9 empty] | 553 | 34.7326 | 1
[9 empty] | 554 | 34.1161 | 1
[9 empty] | 555 | 33.8231 | 1
[9 empty] | 556 | 32.9906 | 1
[9 empty] | 557 | 34.9709 | 1
[9 empty] | 558 | 34.2529 | 1
[9 empty] | 559 | 32.732 | 1
[9 empty] | 560 | 36.0213 | 1
[9 empty] | 561 | 33.6891 | 1
[9 empty] | 562 | 32.3134 | 1
[9 empty] | 563 | 34.3839 | 1
[9 empty] | 564 | 36.8624 | 1
[9 empty] | 565 | 32.8102 | 1
[9 empty] | 566 | 33.7962 | 1
[9 empty] | 567 | 32.9974 | 1
[9 empty] | 568 | 33.6321 | 1
[9 empty] | 569 | 34.2421 | 1
[9 empty] | 570 | 31.5306 | 1
[9 empty] | 571 | 32.2508 | 1
[9 empty] | 572 | 35.8914 | 1
[9 empty] | 573 | 34.8373 | 1
[9 empty] | 574 | 32.9794 | 1
[9 empty] | 575 | 36.2623 | 1
[9 empty] | 576 | 33.2665 | 1
[9 empty] | 577 | 34.8905 | 1
[9 empty] | 578 | 33.8993 | 1
[9 empty] | 579 | 36.9142 | 1
[9 empty] | 580 | 32.262 | 1
[9 empty] | 581 | 31.3229 | 1
[9 empty] | 582 | 32.4417 | 1
[9 empty] | 583 | 35.8775 | 1
[9 empty] | 584 | 33.5226 | 1
[9 empty] | 585 | 34.681 | 1
[9 empty] | 586 | 32.6295 | 1
[9 empty] | 587 | 32.4202 | 1
[9 empty] | 588 | 33.7348 | 1
[9 empty] | 589 | 34.3066 | 1
[9 empty] | 590 | 32.9468 | 1
[9 empty] | 591 | 33.0509 | 1
[9 empty] | 592 | 34.8389 | 1
[9 empty] | 593 | 32.0467 | 1
[9 empty] | 594 | 34.7752 | 1
[9 empty] | 595 | 32.9115 | 1
[9 empty] | 596 | 34.942 | 1
[9 empty] | 597 | 34.4038 | 1
[9 empty] | 598 | 32.1234 | 1
[9 empty] | 599 | 34.6582 | 1
[9 empty] | 600 | 33.4287 | 1
[9 empty] | 601 | 31.9181 | 1
[9 empty] | 602 | 34.0519 | 1
[9 empty] | 603 | 32.9088 | 1
[9 empty] | 604 | 34.7495 | 1
[9 empty] | 605 | 36.4837 | 1
[9 empty] | 606 | 32.8788 | 1
[9 empty] | 607 | 37.3467 | 1
[9 empty] | 608 | 33.4412 | 1
[9 empty] | 609 | 33.6808 | 1
[9 empty] | 610 | 33.3955 | 1
[9 empty] | 611 | 37.8983 | 1
[9 empty] | 612 | 34.8038 | 1
[9 empty] | 613 | 37.1097 | 1
[9 empty] | 614 | 33.9568 | 1
[9 empty] | 615 | 36.27 | 1
[9 empty] | 616 | 35.6976 | 1
[9 empty] | 617 | 35.5303 | 1
[9 empty] | 618 | 36.8629 | 1
[9 empty] | 619 | 34.1757 | 1
[9 empty] | 620 | 36.1508 | 1
[9 empty] | 621 | 35.1782 | 1
[9 empty] | 622 | 34.9204 | 1
[9 empty] | 623 | 33.1522 | 1
[9 empty] | 624 | 34.5357 | 1
[9 empty] | 625 | 37.875 | 1
[9 empty] | 626 | 34.2598 | 1
[9 empty] | 627 | 36.2108 | 1
[9 empty] | 628 | 35.6109 | 1
[9 empty] | 629 | 32.1714 | 1
[9 empty] | 630 | 35.1497 | 1
[9 empty] | 631 | 37.143 | 1
[9 empty] | 632 | 33.111 | 1
[9 empty] | 633 | 30.7601 | 1
[9 empty] | 634 | 33.8317 | 1
[9 empty] | 635 | 33.162 | 1
[9 empty] | 636 | 35.5599 | 1
[9 empty] | 637 | 35.4072 | 1
[9 empty] | 638 | 34.7245 | 1
[9 empty] | 639 | 36.8441 | 1
[9 empty] | 640 | 32.14 | 1
[9 empty] | 641 | 35.409 | 1
[9 empty] | 642 | 33.5418 | 1
[9 empty] | 643 | 32.2468 | 1
[9 empty] | 644 | 32.6507 | 1
[9 empty] | 645 | 33.6127 | 1
[9 empty] | 646 | 33.8303 | 1
[9 empty] | 647 | 36.1227 | 1
[9 empty] | 648 | 36.2813 | 1
[9 empty] | 649 | 35.6642 | 1
[9 empty] | 650 | 33.3076 | 1
[9 empty] | 651 | 33.7907 | 1
[9 empty] | 652 | 34.3799 | 1
[9 empty] | 653 | 34.0446 | 1
[9 empty] | 654 | 32.5079 | 1
[9 empty] | 655 | 34.0033 | 1
[9 empty] | 656 | 33.0185 | 1
[9 empty] | 657 | 32.615 | 1
[9 empty] | 658 | 36.1555 | 1
[9 empty] | 659 | 34.958 | 1
[9 empty] | 660 | 32.6831 | 1
[9 empty] | 661 | 32.2906 | 1
[9 empty] | 662 | 34.1652 | 1
[9 empty] | 663 | 35.165 | 1
[9 empty] | 664 | 33.2878 | 1
[9 empty] | 665 | 34.9963 | 1
[9 empty] | 666 | 33.8607 | 1
[9 empty] | 667 | 33.4222 | 1
[9 empty] | 668 | 33.7704 | 1
[9 empty] | 669 | 33.1813 | 1
[9 empty] | 670 | 31.5067 | 1
[9 empty] | 671 | 36.5144 | 1
[9 empty] | 672 | 34.9098 | 1
[9 empty] | 673 | 32.4221 | 1
[9 empty] | 674 | 31.7321 | 1
[9 empty] | 675 | 33.5481 | 1
[9 empty] | 676 | 34.6951 | 1
[9 empty] | 677 | 32.8873 | 1
[9 empty] | 678 | 35.0491 | 1
[9 empty] | 679 | 32.6199 | 1
[9 empty] | 680 | 34.0918 | 1
[9 empty] | 681 | 32.1151 | 1
[9 empty] | 682 | 34.119 | 1
[9 empty] | 683 | 33.9182 | 1
[9 empty] | 684 | 33.5676 | 1
[9 empty] | 685 | 35.6452 | 1
[9 empty] | 686 | 35.1651 | 1
[9 empty] | 687 | 33.7485 | 1
[9 empty] | 688 | 34.0153 | 1
[9 empty] | 689 | 35.1299 | 1
[9 empty] | 690 | 34.07 | 1
[9 empty] | 691 | 33.2216 | 1
[9 empty] | 692 | 33.6546 | 1
[9 empty] | 693 | 33.9787 | 1
[9 empty] | 694 | 33.4964 | 1
[9 empty] | 695 | 36.5478 | 1
[9 empty] | 696 | 32.5683 | 1
[9 empty] | 697 | 34.6413 | 1
[9 empty] | 698 | 32.0737 | 1
[9 empty] | 699 | 35.5252 | 1
[9 empty] | 700 | 34.7602 | 1
[9 empty] | 701 | 35.0673 | 1
[9 empty] | 702 | 33.3957 | 1
[9 empty] | 703 | 36.313 | 1
[9 empty] | 704 | 34.9507 | 1
[9 empty] | 705 | 32.4899 | 1
[9 empty] | 706 | 35.152 | 1
[9 empty] | 707 | 35.167 | 1
[9 empty] | 708 | 33.4559 | 1
[9 empty] | 709 | 33.4365 | 1
[9 empty] | 710 | 37.0625 | 1
[9 empty] | 711 | 34.1622 | 1
[9 empty] | 712 | 33.9406 | 1
[9 empty] | 713 | 34.5693 | 1
[9 empty] | 714 | 35.0751 | 1
[9 empty] | 715 | 32.4396 | 1
[9 empty] | 716 | 36.3734 | 1
[9 empty] | 717 | 34.9775 | 1
[9 empty] | 718 | 35.4458 | 1
[9 empty] | 719 | 35.5836 | 1
[9 empty] | 720 | 31.2791 | 1
[9 empty] | 721 | 33.842 | 1
[9 empty] | 722 | 33.6577 | 1
[9 empty] | 723 | 34.7927 | 1
[9 empty] | 724 | 36.2347 | 1
[9 empty] | 725 | 35.5699 | 1
[9 empty] | 726 | 36.4238 | 1
[9 empty] | 727 | 33.8222 | 1
[9 empty] | 728 | 33.7099 | 1
[9 empty] | 729 | 31.5354 | 1
[9 empty] | 730 | 34.8511 | 1
[9 empty] | 731 | 34.5982 | 1
[9 empty] | 732 | 34.499 | 1
[9 empty] | 733 | 31.6251 | 1
[9 empty] | 734 | 34.1573 | 1
[9 empty] | 735 | 33.0175 | 1
[9 empty] | 736 | 33.8533 | 1
[9 empty] | 737 | 33.4577 | 1
[9 empty] | 738 | 31.3333 | 1
[9 empty] | 739 | 33.838 | 1
[9 empty] | 740 | 34.8784 | 1
[9 empty] | 741 | 33.4317 | 1
[9 empty] | 742 | 34.5822 | 1
[9 empty] | 743 | 31.5186 | 1
[9 empty] | 744 | 34.8304 | 1
[9 empty] | 745 | 36.9221 | 1
[9 empty] | 746 | 31.769 | 1
[9 empty] | 747 | 33.752 | 1
[9 empty] | 748 | 32.5339 | 1
[9 empty] | 749 | 31.8094 | 1
[9 empty] | 750 | 31.5366 | 1
[9 empty] | 751 | 34.5742 | 1
[9 empty] | 752 | 34.441 | 1
[9 empty] | 753 | 33.2641 | 1
[9 empty] | 754 | 36.525 | 1
[9 empty] | 755 | 34.1267 | 1
[9 empty] | 756 | 37.1045 | 1
[9 empty] | 757 | 32.7556 | 1
[9 empty] | 758 | 33.6559 | 1
[9 empty] | 759 | 31.8284 | 1
[9 empty] | 760 | 34.2623 | 1
[9 empty] | 761 | 34.0653 | 1
[9 empty] | 762 | 32.7099 | 1
[9 empty] | 763 | 35.8554 | 1
[9 empty] | 764 | 36.3366 | 1
[9 empty] | 765 | 35.574 | 1
[9 empty] | 766 | 35.5719 | 1
[9 empty] | 767 | 35.8349 | 1
[9 empty] | 768 | 34.912 | 1
[9 empty] | 769 | 30.8953 | 1
[9 empty] | 770 | 33.0762 | 1
[9 empty] | 771 | 33.2279 | 1
[9 empty] | 772 | 33.6912 | 1
[9 empty] | 773 | 34.191 | 1
[9 empty] | 774 | 33.7242 | 1
[9 empty] | 775 | 32.925 | 1
[9 empty] | 776 | 33.0523 | 1
[9 empty] | 777 | 36.5392 | 1
[9 empty] | 778 | 37.4231 | 1
[9 empty] | 779 | 35.0286 | 1
[9 empty] | 780 | 31.803 | 1
[9 empty] | 781 | 37.1781 | 1
[9 empty] | 782 | 36.3094 | 1
[9 empty] | 783 | 33.9995 | 1
[9 empty] | 784 | 35.59 | 1
[9 empty] | 785 | 33.2336 | 1
[9 empty] | 786 | 33.4557 | 1
[9 empty] | 787 | 37.3897 | 1
[9 empty] | 788 | 32.8146 | 1
[9 empty] | 789 | 32.1185 | 1
[9 empty] | 790 | 33.4985 | 1
[9 empty] | 791 | 36.7299 | 1
[9 empty] | 792 | 33.9164 | 1
[9 empty] | 793 | 33.4922 | 1
[9 empty] | 794 | 35.5493 | 1
[9 empty] | 795 | 34.0107 | 1
[9 empty] | 796 | 36.2365 | 1
[9 empty] | 797 | 34.6423 | 1
[9 empty] | 798 | 33.6962 | 1
[9 empty] | 799 | 36.2789 | 1
[9 empty] | 800 | 34.6942 | 1
[9 empty] | 801 | 31.8846 | 1
[9 empty] | 802 | 36.8859 | 1
[9 empty] | 803 | 34.1872 | 1
[9 empty] | 804 | 33.5408 | 1
[9 empty] | 805 | 32.3375 | 1
[9 empty] | 806 | 33.7333 | 1
[9 empty] | 807 | 35.7212 | 1
[9 empty] | 808 | 34.3805 | 1
[9 empty] | 809 | 35.5073 | 1
[9 empty] | 810 | 32.4321 | 1
[9 empty] | 811 | 34.3625 | 1
[9 empty] | 812 | 35.5394 | 1
[9 empty] | 813 | 35.1598 | 1
[9 empty] | 814 | 32.9569 | 1
[9 empty] | 815 | 33.5626 | 1
[9 empty] | 816 | 35.4292 | 1
[9 empty] | 817 | 32.7167 | 1
[9 empty] | 818 | 32.1938 | 1
[9 empty] | 819 | 36.6685 | 1
[9 empty] | 820 | 31.0671 | 1
[9 empty] | 821 | 36.4552 | 1
[9 empty] | 822 | 33.7442 | 1
[9 empty] | 823 | 33.4352 | 1
[9 empty] | 824 | 33.7073 | 1
[9 empty] | 825 | 33.2474 | 1
[9 empty] | 826 | 30.3212 | 1
[9 empty] | 827 | 33.6627 | 1
[9 empty] | 828 | 31.212 | 1
[9 empty] | 829 | 34.4462 | 1
[9 empty] | 830 | 33.0089 | 1
[9 empty] | 831 | 34.7064 | 1
[9 empty] | 832 | 33.8179 | 1
[9 empty] | 833 | 33.8109 | 1
[9 empty] | 834 | 32.931 | 1
[9 empty] | 835 | 38.375 | 1
[9 empty] | 836 | 37.041 | 1
[9 empty] | 837 | 34.5206 | 1
[9 empty] | 838 | 31.9648 | 1
[9 empty] | 839 | 33.7128 | 1
[9 empty] | 840 | 36.1417 | 1
[9 empty] | 841 | 34.5171 | 1
[9 empty] | 842 | 34.4675 | 1
[9 empty] | 843 | 33.4811 | 1
[9 empty] | 844 | 33.8019 | 1
[9 empty] | 845 | 35.971 | 1
[9 empty] | 846 | 38.1442 | 1
[9 empty] | 847 | 34.3071 | 1
[9 empty] | 848 | 36.2102 | 1
[9 empty] | 849 | 34.0652 | 1
[9 empty] | 850 | 32.526 | 1
[9 empty] | 851 | 33.0482 | 1
[9 empty] | 852 | 34.5921 | 1
[9 empty] | 853 | 34.4235 | 1
[9 empty] | 854 | 35.6426 | 1
[9 empty] | 855 | 34.4767 | 1
[9 empty] | 856 | 32.6752 | 1
[9 empty] | 857 | 35.6729 | 1
[9 empty] | 858 | 31.4912 | 1
[9 empty] | 859 | 33.9855 | 1
[9 empty] | 860 | 32.2416 | 1
[9 empty] | 861 | 32.1581 | 1
[9 empty] | 862 | 35.754 | 1
[9 empty] | 863 | 31.5904 | 1
[9 empty] | 864 | 36.74 | 1
[9 empty] | 865 | 36.8615 | 1
[9 empty] | 866 | 35.5728 | 1
[9 empty] | 867 | 34.5347 | 1
[9 empty] | 868 | 34.0499 | 1
[9 empty] | 869 | 33.7662 | 1
[9 empty] | 870 | 32.8004 | 1
[9 empty] | 871 | 37.2557 | 1
[9 empty] | 872 | 32.5289 | 1
[9 empty] | 873 | 36.8465 | 1
[9 empty] | 874 | 30.6699 | 1
[9 empty] | 875 | 32.716 | 1
[9 empty] | 876 | 34.8973 | 1
[9 empty] | 877 | 33.3975 | 1
[9 empty] | 878 | 38.0466 | 1
[9 empty] | 879 | 31.7366 | 1
[9 empty] | 880 | 34.6474 | 1
[9 empty] | 881 | 31.9005 | 1
[9 empty] | 882 | 38.1994 | 1
[9 empty] | 883 | 36.6778 | 1
[9 empty] | 884 | 32.6933 | 1
[9 empty] | 885 | 34.0669 | 1
[9 empty] | 886 | 34.7239 | 1
[9 empty] | 887 | 36.8114 | 1
[9 empty] | 888 | 32.0031 | 1
[9 empty] | 889 | 31.0511 | 1
[9 empty] | 890 | 33.9991 | 1
[9 empty] | 891 | 32.4761 | 1
[9 empty] | 892 | 32.8816 | 1
[9 empty] | 893 | 34.0839 | 1
[9 empty] | 894 | 33.2837 | 1
[9 empty] | 895 | 35.3312 | 1
[9 empty] | 896 | 33.3253 | 1
[9 empty] | 897 | 35.8837 | 1
[9 empty] | 898 | 36.4612 | 1
[9 empty] | 899 | 37.3686 | 1
[9 empty] | 900 | 35.8432 | 1
[9 empty] | 901 | 33.5018 | 1
[9 empty] | 902 | 34.5848 | 1
[9 empty] | 903 | 31.4129 | 1
[9 empty] | 904 | 34.9305 | 1
[9 empty] | 905 | 35.068 | 1
[9 empty] | 906 | 36.8499 | 1
[9 empty] | 907 | 35.0004 | 1
[9 empty] | 908 | 32.4875 | 1
[9 empty] | 909 | 35.9353 | 1
[9 empty] | 910 | 33.7953 | 1
[9 empty] | 911 | 36.4256 | 1
[9 empty] | 912 | 33.5347 | 1
[9 empty] | 913 | 34.8473 | 1
[9 empty] | 914 | 34.447 | 1
[9 empty] | 915 | 33.7175 | 1
[9 empty] | 916 | 36.2554 | 1
[9 empty] | 917 | 34.0656 | 1
[9 empty] | 918 | 33.4957 | 1
[9 empty] | 919 | 33.1296 | 1
[9 empty] | 920 | 35.826 | 1
[9 empty] | 921 | 33.3216 | 1
[9 empty] | 922 | 34.1134 | 1
[9 empty] | 923 | 31.7968 | 1
[9 empty] | 924 | 34.3422 | 1
[9 empty] | 925 | 33.2006 | 1
[9 empty] | 926 | 34.3827 | 1
[9 empty] | 927 | 33.3449 | 1
[9 empty] | 928 | 36.7763 | 1
[9 empty] | 929 | 34.2663 | 1
[9 empty] | 930 | 34.0183 | 1
[9 empty] | 931 | 37.6734 | 1
[9 empty] | 932 | 36.2667 | 1
[9 empty] | 933 | 33.4368 | 1
[9 empty] | 934 | 34.011 | 1
[9 empty] | 935 | 32.5544 | 1
[9 empty] | 936 | 33.7271 | 1
[9 empty] | 937 | 31.8363 | 1
[9 empty] | 938 | 33.6914 | 1
[9 empty] | 939 | 34.5103 | 1
[9 empty] | 940 | 35.301 | 1
[9 empty] | 941 | 34.7898 | 1
[9 empty] | 942 | 32.5129 | 1
[9 empty] | 943 | 34.9984 | 1
[9 empty] | 944 | 33.4935 | 1
[9 empty] | 945 | 32.1459 | 1
[9 empty] | 946 | 34.9212 | 1
[9 empty] | 947 | 33.0395 | 1
[9 empty] | 948 | 34.3903 | 1
[9 empty] | 949 | 30.9619 | 1
[9 empty] | 950 | 35.8648 | 1
[9 empty] | 951 | 34.0016 | 1
[9 empty] | 952 | 34.815 | 1
[9 empty] | 953 | 34.8799 | 1
[9 empty] | 954 | 33.2753 | 1
[9 empty] | 955 | 31.3173 | 1
[9 empty] | 956 | 32.8797 | 1
[9 empty] | 957 | 33.4889 | 1
[9 empty] | 958 | 33.0607 | 1
[9 empty] | 959 | 33.8036 | 1
[9 empty] | 960 | 36.0617 | 1
[9 empty] | 961 | 35.0563 | 1
[9 empty] | 962 | 36.3906 | 1
[9 empty] | 963 | 33.0888 | 1
[9 empty] | 964 | 32.1415 | 1
[9 empty] | 965 | 35.4875 | 1
[9 empty] | 966 | 33.6122 | 1
[9 empty] | 967 | 37.3368 | 1
[9 empty] | 968 | 34.9899 | 1
[9 empty] | 969 | 35.4022 | 1
[9 empty] | 970 | 34.0015 | 1
[9 empty] | 971 | 31.0072 | 1
[9 empty] | 972 | 32.4106 | 1
[9 empty] | 973 | 35.1271 | 1
[9 empty] | 974 | 33.0853 | 1
[9 empty] | 975 | 32.3309 | 1
[9 empty] | 976 | 34.8344 | 1
[9 empty] | 977 | 37.7105 | 1
[9 empty] | 978 | 32.603 | 1
[9 empty] | 979 | 34.4174 | 1
[9 empty] | 980 | 31.9698 | 1
[9 empty] | 981 | 33.0787 | 1
[9 empty] | 982 | 37.1365 | 1
[9 empty] | 983 | 33.3224 | 1
[9 empty] | 984 | 32.7548 | 1
[9 empty] | 985 | 33.6158 | 1
[9 empty] | 986 | 32.2986 | 1
[9 empty] | 987 | 35.5 | 1
[9 empty] | 988 | 37.4221 | 1
[9 empty] | 989 | 33.863 | 1
[9 empty] | 990 | 35.4661 | 1
[9 empty] | 991 | 32.8502 | 1
[9 empty] | 992 | 33.1532 | 1
[9 empty] | 993 | 33.4687 | 1
[9 empty] | 994 | 35.1784 | 1
[9 empty] | 995 | 33.6322 | 1
[9 empty] | 996 | 34.2565 | 1
[9 empty] | 997 | 34.1434 | 1
[9 empty] | 998 | 34.04 | 1
[9 empty] | 999 | 34.6922 | 1
[9 empty] | 1000 | 34.6468 | 1

## Project-2 LT(a,b)
Project 1 | [8 empty] | Trial | Project Duration | Success
Task | Immediate Ancestor | a | m | b | Start Time | U(0,1) | Duration | Finsih Time |  | 39.7982 | 1
A |  | 1 | 3 | 4 | 0 | 0.81201 | 3.436 | 3.436 | 1 | 35.4716 | 1
B |  | 5 | 7 | 8 | 0 | 0.18477 | 7.9286 | 7.9286 | 2 | 34.9838 | 1
C |  | 6 | 7 | 9 | 0 | 0.55642 | 7.6693 | 7.6693 | 3 | 33.8921 | 1
D |  | 1 | 2 | 3 | 0 | 0.26558 | 2.7918 | 2.7918 | 4 | 35.0617 | 1
E | A | 3 | 4 | 5 | 3.436 | 0.58858 | 4.1772 | 7.6132 | 5 | 34.173 | 1
F | A | 7 | 8 | 9 | 3.436 | 0.31813 | 7.6363 | 11.0723 | 6 | 31.8252 | 1
G | B,E | 10 | 15 | 20 | 7.9286 | 0.95579 | 19.5579 | 27.4865 | 7 | 34.024 | 1
H | B,E | 12 | 13 | 14 | 7.9286 | 0.86029 | 13.7206 | 21.6492 | 8 | 33.7761 | 1
I | C | 10 | 12 | 15 | 7.6693 | 0.58211 | 14.9843 | 22.6536 | 9 | 36.4601 | 1
J | C | 8 | 10 | 12 | 7.6693 | 0.38287 | 9.5315 | 17.2007 | 10 | 35.1781 | 1
K | F,I | 7 | 8 | 11 | 22.6536 | 0.89538 | 10.5815 | 33.2351 | 11 | 34.2531 | 1
L | F,I | 2 | 4 | 8 | 22.6536 | 0.028011 | 2.912 | 25.5655 | 12 | 30.9364 | 1
M | D,K | 5 | 6 | 7 | 33.2351 | 0.78158 | 6.5632 | 39.7982 | 13 | 32.2714 | 1
N | H,J,L,M | 0 | 0 | 0 | 39.7982 | 0.50672 | 0 | 39.7982 | 14 | 35.5878 | 1
[9 empty] | 15 | 34.4674 | 1
[9 empty] | 16 | 32.0851 | 1
[9 empty] | 17 | 32.798 | 1
[9 empty] | 18 | 35.2701 | 1
Deadline | Average Project Duration | Avg Success Rate | [6 empty] | 19 | 33.3572 | 1
48 | 34.3778 | 100 | [6 empty] | 20 | 34.361 | 1
[9 empty] | 21 | 34.508 | 1
[9 empty] | 22 | 34.8329 | 1
[9 empty] | 23 | 34.6023 | 1
[9 empty] | 24 | 37.0404 | 1
[9 empty] | 25 | 37.2358 | 1
[9 empty] | 26 | 35.0902 | 1
[9 empty] | 27 | 34.0671 | 1
[9 empty] | 28 | 32.2827 | 1
[9 empty] | 29 | 32.4826 | 1
[9 empty] | 30 | 32.9969 | 1
[9 empty] | 31 | 35.6152 | 1
[9 empty] | 32 | 34.3114 | 1
[9 empty] | 33 | 37.2909 | 1
[9 empty] | 34 | 34.3981 | 1
[9 empty] | 35 | 32.9862 | 1
[9 empty] | 36 | 36.2684 | 1
[9 empty] | 37 | 34.7696 | 1
[9 empty] | 38 | 31.9552 | 1
[9 empty] | 39 | 35.3648 | 1
[9 empty] | 40 | 35.6642 | 1
[9 empty] | 41 | 34.0912 | 1
[9 empty] | 42 | 34.8111 | 1
[9 empty] | 43 | 33.7984 | 1
[9 empty] | 44 | 32.389 | 1
[9 empty] | 45 | 34.7132 | 1
[9 empty] | 46 | 32.9634 | 1
[9 empty] | 47 | 35.7397 | 1
[9 empty] | 48 | 33.8085 | 1
[9 empty] | 49 | 35.3642 | 1
[9 empty] | 50 | 33.9947 | 1
[9 empty] | 51 | 35.2808 | 1
[9 empty] | 52 | 33.7273 | 1
[9 empty] | 53 | 34.0854 | 1
[9 empty] | 54 | 30.7769 | 1
[9 empty] | 55 | 32.3991 | 1
[9 empty] | 56 | 34.434 | 1
[9 empty] | 57 | 32.8009 | 1
[9 empty] | 58 | 33.611 | 1
[9 empty] | 59 | 34.4109 | 1
[9 empty] | 60 | 35.4107 | 1
[9 empty] | 61 | 38.1246 | 1
[9 empty] | 62 | 35.0015 | 1
[9 empty] | 63 | 34.7403 | 1
[9 empty] | 64 | 33.8626 | 1
[9 empty] | 65 | 32.7829 | 1
[9 empty] | 66 | 32.6155 | 1
[9 empty] | 67 | 35.523 | 1
[9 empty] | 68 | 33.4703 | 1
[9 empty] | 69 | 34.4297 | 1
[9 empty] | 70 | 38.2011 | 1
[9 empty] | 71 | 34.0575 | 1
[9 empty] | 72 | 33.3742 | 1
[9 empty] | 73 | 31.6888 | 1
[9 empty] | 74 | 36.7486 | 1
[9 empty] | 75 | 33.8703 | 1
[9 empty] | 76 | 33.7239 | 1
[9 empty] | 77 | 32.293 | 1
[9 empty] | 78 | 33.1331 | 1
[9 empty] | 79 | 32.3364 | 1
[9 empty] | 80 | 34.5495 | 1
[9 empty] | 81 | 34.3171 | 1
[9 empty] | 82 | 36.6898 | 1
[9 empty] | 83 | 35.2439 | 1
[9 empty] | 84 | 35.4418 | 1
[9 empty] | 85 | 32.6051 | 1
[9 empty] | 86 | 34.0526 | 1
[9 empty] | 87 | 33.2963 | 1
[9 empty] | 88 | 32.5919 | 1
[9 empty] | 89 | 31.7798 | 1
[9 empty] | 90 | 35.2963 | 1
[9 empty] | 91 | 34.0969 | 1
[9 empty] | 92 | 36.7215 | 1
[9 empty] | 93 | 35.9365 | 1
[9 empty] | 94 | 35.5662 | 1
[9 empty] | 95 | 34.4462 | 1
[9 empty] | 96 | 35.2805 | 1
[9 empty] | 97 | 33.7398 | 1
[9 empty] | 98 | 33.3438 | 1
[9 empty] | 99 | 34.6204 | 1
[9 empty] | 100 | 35.4712 | 1
[9 empty] | 101 | 33.2372 | 1
[9 empty] | 102 | 33.7861 | 1
[9 empty] | 103 | 34.8927 | 1
[9 empty] | 104 | 38.1207 | 1
[9 empty] | 105 | 33.1306 | 1
[9 empty] | 106 | 32.9938 | 1
[9 empty] | 107 | 36.0877 | 1
[9 empty] | 108 | 33.3004 | 1
[9 empty] | 109 | 34.0376 | 1
[9 empty] | 110 | 35.3503 | 1
[9 empty] | 111 | 34.2263 | 1
[9 empty] | 112 | 33.4417 | 1
[9 empty] | 113 | 34.9335 | 1
[9 empty] | 114 | 33.78 | 1
[9 empty] | 115 | 36.8111 | 1
[9 empty] | 116 | 33.717 | 1
[9 empty] | 117 | 36.2782 | 1
[9 empty] | 118 | 34.2509 | 1
[9 empty] | 119 | 32.226 | 1
[9 empty] | 120 | 34.9505 | 1
[9 empty] | 121 | 35.33 | 1
[9 empty] | 122 | 35.1241 | 1
[9 empty] | 123 | 32.8613 | 1
[9 empty] | 124 | 35.7503 | 1
[9 empty] | 125 | 35.6184 | 1
[9 empty] | 126 | 34.6902 | 1
[9 empty] | 127 | 35.4745 | 1
[9 empty] | 128 | 33.8875 | 1
[9 empty] | 129 | 36.308 | 1
[9 empty] | 130 | 33.1823 | 1
[9 empty] | 131 | 31.9942 | 1
[9 empty] | 132 | 35.5058 | 1
[9 empty] | 133 | 35.0874 | 1
[9 empty] | 134 | 35.6536 | 1
[9 empty] | 135 | 35.6607 | 1
[9 empty] | 136 | 33.352 | 1
[9 empty] | 137 | 34.277 | 1
[9 empty] | 138 | 35.3823 | 1
[9 empty] | 139 | 36.2246 | 1
[9 empty] | 140 | 31.9643 | 1
[9 empty] | 141 | 35.4433 | 1
[9 empty] | 142 | 35.6774 | 1
[9 empty] | 143 | 34.4499 | 1
[9 empty] | 144 | 30.8055 | 1
[9 empty] | 145 | 34.2927 | 1
[9 empty] | 146 | 31.5495 | 1
[9 empty] | 147 | 33.9964 | 1
[9 empty] | 148 | 32.5209 | 1
[9 empty] | 149 | 32.6867 | 1
[9 empty] | 150 | 33.2112 | 1
[9 empty] | 151 | 32.3985 | 1
[9 empty] | 152 | 30.8106 | 1
[9 empty] | 153 | 35.8272 | 1
[9 empty] | 154 | 34.7745 | 1
[9 empty] | 155 | 33.9824 | 1
[9 empty] | 156 | 34.0774 | 1
[9 empty] | 157 | 35.4366 | 1
[9 empty] | 158 | 34.9452 | 1
[9 empty] | 159 | 34.9036 | 1
[9 empty] | 160 | 32.5464 | 1
[9 empty] | 161 | 34.0541 | 1
[9 empty] | 162 | 34.0488 | 1
[9 empty] | 163 | 34.109 | 1
[9 empty] | 164 | 35.6883 | 1
[9 empty] | 165 | 34.7954 | 1
[9 empty] | 166 | 33.7511 | 1
[9 empty] | 167 | 36.825 | 1
[9 empty] | 168 | 34.8248 | 1
[9 empty] | 169 | 32.5881 | 1
[9 empty] | 170 | 31.4423 | 1
[9 empty] | 171 | 35.7889 | 1
[9 empty] | 172 | 34.8381 | 1
[9 empty] | 173 | 37.0167 | 1
[9 empty] | 174 | 32.0009 | 1
[9 empty] | 175 | 33.5555 | 1
[9 empty] | 176 | 34.5305 | 1
[9 empty] | 177 | 34.789 | 1
[9 empty] | 178 | 32.9216 | 1
[9 empty] | 179 | 33.2854 | 1
[9 empty] | 180 | 32.1898 | 1
[9 empty] | 181 | 36.0541 | 1
[9 empty] | 182 | 36.1149 | 1
[9 empty] | 183 | 35.0309 | 1
[9 empty] | 184 | 33.0941 | 1
[9 empty] | 185 | 33.8274 | 1
[9 empty] | 186 | 36.4689 | 1
[9 empty] | 187 | 33.7748 | 1
[9 empty] | 188 | 35.1824 | 1
[9 empty] | 189 | 34.1871 | 1
[9 empty] | 190 | 37.8216 | 1
[9 empty] | 191 | 32.2227 | 1
[9 empty] | 192 | 39.1324 | 1
[9 empty] | 193 | 35.4745 | 1
[9 empty] | 194 | 36.6605 | 1
[9 empty] | 195 | 34.5217 | 1
[9 empty] | 196 | 34.0778 | 1
[9 empty] | 197 | 34.6839 | 1
[9 empty] | 198 | 33.6386 | 1
[9 empty] | 199 | 36.996 | 1
[9 empty] | 200 | 34.9819 | 1
[9 empty] | 201 | 34.7913 | 1
[9 empty] | 202 | 35.1674 | 1
[9 empty] | 203 | 32.9858 | 1
[9 empty] | 204 | 33.0995 | 1
[9 empty] | 205 | 33.8535 | 1
[9 empty] | 206 | 33.477 | 1
[9 empty] | 207 | 34.4907 | 1
[9 empty] | 208 | 33.2473 | 1
[9 empty] | 209 | 32.9214 | 1
[9 empty] | 210 | 35.6597 | 1
[9 empty] | 211 | 33.7659 | 1
[9 empty] | 212 | 32.6442 | 1
[9 empty] | 213 | 32.99 | 1
[9 empty] | 214 | 35.7006 | 1
[9 empty] | 215 | 35.2599 | 1
[9 empty] | 216 | 35.9074 | 1
[9 empty] | 217 | 34.4682 | 1
[9 empty] | 218 | 34.4817 | 1
[9 empty] | 219 | 34.4514 | 1
[9 empty] | 220 | 36.5354 | 1
[9 empty] | 221 | 34.3921 | 1
[9 empty] | 222 | 34.1239 | 1
[9 empty] | 223 | 35.4705 | 1
[9 empty] | 224 | 37.7321 | 1
[9 empty] | 225 | 33.1167 | 1
[9 empty] | 226 | 35.3358 | 1
[9 empty] | 227 | 34.4084 | 1
[9 empty] | 228 | 35.514 | 1
[9 empty] | 229 | 34.9591 | 1
[9 empty] | 230 | 34.4595 | 1
[9 empty] | 231 | 30.4338 | 1
[9 empty] | 232 | 33.5284 | 1
[9 empty] | 233 | 35.8489 | 1
[9 empty] | 234 | 36.3111 | 1
[9 empty] | 235 | 33.5439 | 1
[9 empty] | 236 | 35.7752 | 1
[9 empty] | 237 | 33.7303 | 1
[9 empty] | 238 | 32.966 | 1
[9 empty] | 239 | 34.851 | 1
[9 empty] | 240 | 32.7721 | 1
[9 empty] | 241 | 34.3329 | 1
[9 empty] | 242 | 32.5127 | 1
[9 empty] | 243 | 34.8696 | 1
[9 empty] | 244 | 35.0021 | 1
[9 empty] | 245 | 33.8393 | 1
[9 empty] | 246 | 33.7043 | 1
[9 empty] | 247 | 34.656 | 1
[9 empty] | 248 | 35.4536 | 1
[9 empty] | 249 | 32.7866 | 1
[9 empty] | 250 | 31.4031 | 1
[9 empty] | 251 | 35.6383 | 1
[9 empty] | 252 | 36.497 | 1
[9 empty] | 253 | 39.2469 | 1
[9 empty] | 254 | 34.3028 | 1
[9 empty] | 255 | 37.6036 | 1
[9 empty] | 256 | 33.1601 | 1
[9 empty] | 257 | 32.3357 | 1
[9 empty] | 258 | 36.8738 | 1
[9 empty] | 259 | 34.5918 | 1
[9 empty] | 260 | 36.1533 | 1
[9 empty] | 261 | 34.8569 | 1
[9 empty] | 262 | 36.4609 | 1
[9 empty] | 263 | 33.5913 | 1
[9 empty] | 264 | 34.9698 | 1
[9 empty] | 265 | 32.5574 | 1
[9 empty] | 266 | 32.9684 | 1
[9 empty] | 267 | 32.8822 | 1
[9 empty] | 268 | 32.8836 | 1
[9 empty] | 269 | 32.6983 | 1
[9 empty] | 270 | 33.2863 | 1
[9 empty] | 271 | 34.3658 | 1
[9 empty] | 272 | 35.3561 | 1
[9 empty] | 273 | 32.7015 | 1
[9 empty] | 274 | 34.4386 | 1
[9 empty] | 275 | 33.5793 | 1
[9 empty] | 276 | 32.8858 | 1
[9 empty] | 277 | 34.8158 | 1
[9 empty] | 278 | 34.5193 | 1
[9 empty] | 279 | 34.6102 | 1
[9 empty] | 280 | 32.6821 | 1
[9 empty] | 281 | 34.9476 | 1
[9 empty] | 282 | 32.83 | 1
[9 empty] | 283 | 32.5515 | 1
[9 empty] | 284 | 35.327 | 1
[9 empty] | 285 | 35.5149 | 1
[9 empty] | 286 | 34.5964 | 1
[9 empty] | 287 | 35.508 | 1
[9 empty] | 288 | 34.8052 | 1
[9 empty] | 289 | 35.8278 | 1
[9 empty] | 290 | 35.4975 | 1
[9 empty] | 291 | 32.3156 | 1
[9 empty] | 292 | 33.2805 | 1
[9 empty] | 293 | 34.3088 | 1
[9 empty] | 294 | 33.8572 | 1
[9 empty] | 295 | 32.346 | 1
[9 empty] | 296 | 34.1207 | 1
[9 empty] | 297 | 31.7488 | 1
[9 empty] | 298 | 32.7411 | 1
[9 empty] | 299 | 35.5999 | 1
[9 empty] | 300 | 32.5657 | 1
[9 empty] | 301 | 37.4577 | 1
[9 empty] | 302 | 33.3836 | 1
[9 empty] | 303 | 35.8684 | 1
[9 empty] | 304 | 35.1528 | 1
[9 empty] | 305 | 36.0115 | 1
[9 empty] | 306 | 35.9 | 1
[9 empty] | 307 | 31.5225 | 1
[9 empty] | 308 | 34.5366 | 1
[9 empty] | 309 | 32.2529 | 1
[9 empty] | 310 | 32.0371 | 1
[9 empty] | 311 | 33.6066 | 1
[9 empty] | 312 | 32.3482 | 1
[9 empty] | 313 | 33.6804 | 1
[9 empty] | 314 | 35.0539 | 1
[9 empty] | 315 | 34.9367 | 1
[9 empty] | 316 | 34.2436 | 1
[9 empty] | 317 | 34.9499 | 1
[9 empty] | 318 | 34.7494 | 1
[9 empty] | 319 | 33.0989 | 1
[9 empty] | 320 | 32.3538 | 1
[9 empty] | 321 | 33.8591 | 1
[9 empty] | 322 | 32.1212 | 1
[9 empty] | 323 | 32.5827 | 1
[9 empty] | 324 | 35.6537 | 1
[9 empty] | 325 | 33.363 | 1
[9 empty] | 326 | 33.9386 | 1
[9 empty] | 327 | 35.2633 | 1
[9 empty] | 328 | 33.33 | 1
[9 empty] | 329 | 33.3788 | 1
[9 empty] | 330 | 34.3184 | 1
[9 empty] | 331 | 34.6443 | 1
[9 empty] | 332 | 34.4711 | 1
[9 empty] | 333 | 33.282 | 1
[9 empty] | 334 | 34.1483 | 1
[9 empty] | 335 | 33.8516 | 1
[9 empty] | 336 | 35.1961 | 1
[9 empty] | 337 | 35.3462 | 1
[9 empty] | 338 | 34.299 | 1
[9 empty] | 339 | 33.5408 | 1
[9 empty] | 340 | 31.6418 | 1
[9 empty] | 341 | 35.0845 | 1
[9 empty] | 342 | 31.9463 | 1
[9 empty] | 343 | 34.3016 | 1
[9 empty] | 344 | 35.4008 | 1
[9 empty] | 345 | 34.513 | 1
[9 empty] | 346 | 34.2865 | 1
[9 empty] | 347 | 38.6749 | 1
[9 empty] | 348 | 32.7273 | 1
[9 empty] | 349 | 33.3544 | 1
[9 empty] | 350 | 34.8798 | 1
[9 empty] | 351 | 33.9838 | 1
[9 empty] | 352 | 33.5472 | 1
[9 empty] | 353 | 36.4637 | 1
[9 empty] | 354 | 33.9048 | 1
[9 empty] | 355 | 36.2966 | 1
[9 empty] | 356 | 31.9734 | 1
[9 empty] | 357 | 32.4391 | 1
[9 empty] | 358 | 36.1151 | 1
[9 empty] | 359 | 34.6 | 1
[9 empty] | 360 | 33.9571 | 1
[9 empty] | 361 | 35.2935 | 1
[9 empty] | 362 | 34.989 | 1
[9 empty] | 363 | 33.4447 | 1
[9 empty] | 364 | 31.8189 | 1
[9 empty] | 365 | 34.9664 | 1
[9 empty] | 366 | 35.4321 | 1
[9 empty] | 367 | 32.5515 | 1
[9 empty] | 368 | 33.6216 | 1
[9 empty] | 369 | 34.7173 | 1
[9 empty] | 370 | 32.4858 | 1
[9 empty] | 371 | 35.2228 | 1
[9 empty] | 372 | 35.083 | 1
[9 empty] | 373 | 35.4757 | 1
[9 empty] | 374 | 32.8208 | 1
[9 empty] | 375 | 33.1166 | 1
[9 empty] | 376 | 35.1837 | 1
[9 empty] | 377 | 33.1567 | 1
[9 empty] | 378 | 36.5323 | 1
[9 empty] | 379 | 33.4004 | 1
[9 empty] | 380 | 33.0887 | 1
[9 empty] | 381 | 34.2716 | 1
[9 empty] | 382 | 37.2057 | 1
[9 empty] | 383 | 36.1398 | 1
[9 empty] | 384 | 31.887 | 1
[9 empty] | 385 | 35.6786 | 1
[9 empty] | 386 | 34.1834 | 1
[9 empty] | 387 | 36.5452 | 1
[9 empty] | 388 | 31.9962 | 1
[9 empty] | 389 | 35.5415 | 1
[9 empty] | 390 | 36.2579 | 1
[9 empty] | 391 | 37.3969 | 1
[9 empty] | 392 | 32.5753 | 1
[9 empty] | 393 | 35.1349 | 1
[9 empty] | 394 | 36.9163 | 1
[9 empty] | 395 | 32.9506 | 1
[9 empty] | 396 | 34.7173 | 1
[9 empty] | 397 | 36.0033 | 1
[9 empty] | 398 | 33.9601 | 1
[9 empty] | 399 | 34.3738 | 1
[9 empty] | 400 | 35.082 | 1
[9 empty] | 401 | 33.1453 | 1
[9 empty] | 402 | 32.1141 | 1
[9 empty] | 403 | 35.5484 | 1
[9 empty] | 404 | 34.6785 | 1
[9 empty] | 405 | 32.2859 | 1
[9 empty] | 406 | 33.8397 | 1
[9 empty] | 407 | 35.7989 | 1
[9 empty] | 408 | 33.3335 | 1
[9 empty] | 409 | 33.1459 | 1
[9 empty] | 410 | 33.5201 | 1
[9 empty] | 411 | 34.534 | 1
[9 empty] | 412 | 34.1607 | 1
[9 empty] | 413 | 34.0709 | 1
[9 empty] | 414 | 36.4109 | 1
[9 empty] | 415 | 32.688 | 1
[9 empty] | 416 | 34.8054 | 1
[9 empty] | 417 | 31.1683 | 1
[9 empty] | 418 | 34.0637 | 1
[9 empty] | 419 | 33.5408 | 1
[9 empty] | 420 | 33.3671 | 1
[9 empty] | 421 | 30.2608 | 1
[9 empty] | 422 | 32.3489 | 1
[9 empty] | 423 | 35.5877 | 1
[9 empty] | 424 | 33.9677 | 1
[9 empty] | 425 | 37.4032 | 1
[9 empty] | 426 | 31.6318 | 1
[9 empty] | 427 | 34.5423 | 1
[9 empty] | 428 | 37.1882 | 1
[9 empty] | 429 | 34.3779 | 1
[9 empty] | 430 | 36.5712 | 1
[9 empty] | 431 | 34.6715 | 1
[9 empty] | 432 | 34.8117 | 1
[9 empty] | 433 | 35.8851 | 1
[9 empty] | 434 | 39.2414 | 1
[9 empty] | 435 | 32.755 | 1
[9 empty] | 436 | 35.4689 | 1
[9 empty] | 437 | 32.0261 | 1
[9 empty] | 438 | 33.215 | 1
[9 empty] | 439 | 34.6091 | 1
[9 empty] | 440 | 32.2436 | 1
[9 empty] | 441 | 33.5702 | 1
[9 empty] | 442 | 32.4435 | 1
[9 empty] | 443 | 32.2263 | 1
[9 empty] | 444 | 32.2596 | 1
[9 empty] | 445 | 37.4357 | 1
[9 empty] | 446 | 37.4825 | 1
[9 empty] | 447 | 35.1907 | 1
[9 empty] | 448 | 35.6081 | 1
[9 empty] | 449 | 33.4698 | 1
[9 empty] | 450 | 32.5304 | 1
[9 empty] | 451 | 36.3457 | 1
[9 empty] | 452 | 38.6087 | 1
[9 empty] | 453 | 34.121 | 1
[9 empty] | 454 | 37.4571 | 1
[9 empty] | 455 | 33.4302 | 1
[9 empty] | 456 | 31.6406 | 1
[9 empty] | 457 | 32.5072 | 1
[9 empty] | 458 | 32.5414 | 1
[9 empty] | 459 | 35.5163 | 1
[9 empty] | 460 | 34.1037 | 1
[9 empty] | 461 | 36.2209 | 1
[9 empty] | 462 | 34.6036 | 1
[9 empty] | 463 | 32.447 | 1
[9 empty] | 464 | 32.7034 | 1
[9 empty] | 465 | 32.5414 | 1
[9 empty] | 466 | 37.0652 | 1
[9 empty] | 467 | 32.8588 | 1
[9 empty] | 468 | 35.1801 | 1
[9 empty] | 469 | 37.7297 | 1
[9 empty] | 470 | 33.5707 | 1
[9 empty] | 471 | 33.528 | 1
[9 empty] | 472 | 36.1534 | 1
[9 empty] | 473 | 34.2473 | 1
[9 empty] | 474 | 33.8534 | 1
[9 empty] | 475 | 35.5549 | 1
[9 empty] | 476 | 36.5245 | 1
[9 empty] | 477 | 34.2055 | 1
[9 empty] | 478 | 32.4704 | 1
[9 empty] | 479 | 33.572 | 1
[9 empty] | 480 | 34.977 | 1
[9 empty] | 481 | 35.7054 | 1
[9 empty] | 482 | 34.5761 | 1
[9 empty] | 483 | 33.8549 | 1
[9 empty] | 484 | 33.9535 | 1
[9 empty] | 485 | 31.7755 | 1
[9 empty] | 486 | 35.2653 | 1
[9 empty] | 487 | 33.5363 | 1
[9 empty] | 488 | 34.3888 | 1
[9 empty] | 489 | 32.735 | 1
[9 empty] | 490 | 34.2696 | 1
[9 empty] | 491 | 35.0758 | 1
[9 empty] | 492 | 32.551 | 1
[9 empty] | 493 | 35.3799 | 1
[9 empty] | 494 | 35.6915 | 1
[9 empty] | 495 | 35.3519 | 1
[9 empty] | 496 | 31.4012 | 1
[9 empty] | 497 | 32.6828 | 1
[9 empty] | 498 | 33.9776 | 1
[9 empty] | 499 | 35.2617 | 1
[9 empty] | 500 | 34.3141 | 1
[9 empty] | 501 | 34.6908 | 1
[9 empty] | 502 | 33.8141 | 1
[9 empty] | 503 | 35.7588 | 1
[9 empty] | 504 | 36.0522 | 1
[9 empty] | 505 | 33.4474 | 1
[9 empty] | 506 | 35.0466 | 1
[9 empty] | 507 | 35.1386 | 1
[9 empty] | 508 | 35.7981 | 1
[9 empty] | 509 | 31.6708 | 1
[9 empty] | 510 | 33.9634 | 1
[9 empty] | 511 | 34.6523 | 1
[9 empty] | 512 | 38.2123 | 1
[9 empty] | 513 | 32.5673 | 1
[9 empty] | 514 | 37.7465 | 1
[9 empty] | 515 | 35.5339 | 1
[9 empty] | 516 | 35.6462 | 1
[9 empty] | 517 | 34.4444 | 1
[9 empty] | 518 | 33.6927 | 1
[9 empty] | 519 | 33.7463 | 1
[9 empty] | 520 | 36.0001 | 1
[9 empty] | 521 | 35.292 | 1
[9 empty] | 522 | 33.9429 | 1
[9 empty] | 523 | 35.1732 | 1
[9 empty] | 524 | 33.2237 | 1
[9 empty] | 525 | 32.993 | 1
[9 empty] | 526 | 35.2572 | 1
[9 empty] | 527 | 35.5106 | 1
[9 empty] | 528 | 35.7411 | 1
[9 empty] | 529 | 33.8636 | 1
[9 empty] | 530 | 33.7594 | 1
[9 empty] | 531 | 35.2264 | 1
[9 empty] | 532 | 34.4884 | 1
[9 empty] | 533 | 33.0555 | 1
[9 empty] | 534 | 33.6717 | 1
[9 empty] | 535 | 32.9437 | 1
[9 empty] | 536 | 31.8864 | 1
[9 empty] | 537 | 33.5074 | 1
[9 empty] | 538 | 33.5109 | 1
[9 empty] | 539 | 33.9554 | 1
[9 empty] | 540 | 34.5613 | 1
[9 empty] | 541 | 34.0595 | 1
[9 empty] | 542 | 34.38 | 1
[9 empty] | 543 | 32.9937 | 1
[9 empty] | 544 | 35.9607 | 1
[9 empty] | 545 | 37.7253 | 1
[9 empty] | 546 | 33.9361 | 1
[9 empty] | 547 | 37.6463 | 1
[9 empty] | 548 | 33.3499 | 1
[9 empty] | 549 | 33.4863 | 1
[9 empty] | 550 | 33.1709 | 1
[9 empty] | 551 | 35.9119 | 1
[9 empty] | 552 | 35.2976 | 1
[9 empty] | 553 | 33.9394 | 1
[9 empty] | 554 | 34.0864 | 1
[9 empty] | 555 | 33.0012 | 1
[9 empty] | 556 | 32.084 | 1
[9 empty] | 557 | 37.2887 | 1
[9 empty] | 558 | 34.2558 | 1
[9 empty] | 559 | 33.4554 | 1
[9 empty] | 560 | 32.9431 | 1
[9 empty] | 561 | 34.3734 | 1
[9 empty] | 562 | 32.7135 | 1
[9 empty] | 563 | 35.5879 | 1
[9 empty] | 564 | 35.4707 | 1
[9 empty] | 565 | 34.0812 | 1
[9 empty] | 566 | 33.9313 | 1
[9 empty] | 567 | 33.1448 | 1
[9 empty] | 568 | 35.1213 | 1
[9 empty] | 569 | 34.1049 | 1
[9 empty] | 570 | 33.5378 | 1
[9 empty] | 571 | 33.6371 | 1
[9 empty] | 572 | 34.3228 | 1
[9 empty] | 573 | 37.0541 | 1
[9 empty] | 574 | 33.6634 | 1
[9 empty] | 575 | 32.8465 | 1
[9 empty] | 576 | 37.2786 | 1
[9 empty] | 577 | 33.5446 | 1
[9 empty] | 578 | 33.2539 | 1
[9 empty] | 579 | 32.3535 | 1
[9 empty] | 580 | 34.6418 | 1
[9 empty] | 581 | 33.9042 | 1
[9 empty] | 582 | 35.1082 | 1
[9 empty] | 583 | 33.4081 | 1
[9 empty] | 584 | 35.1261 | 1
[9 empty] | 585 | 33.9319 | 1
[9 empty] | 586 | 38.1427 | 1
[9 empty] | 587 | 33.7409 | 1
[9 empty] | 588 | 39.0843 | 1
[9 empty] | 589 | 34.4992 | 1
[9 empty] | 590 | 33.2549 | 1
[9 empty] | 591 | 34.2576 | 1
[9 empty] | 592 | 32.9521 | 1
[9 empty] | 593 | 34.077 | 1
[9 empty] | 594 | 34.2424 | 1
[9 empty] | 595 | 32.2451 | 1
[9 empty] | 596 | 33.0387 | 1
[9 empty] | 597 | 34.4648 | 1
[9 empty] | 598 | 34.1015 | 1
[9 empty] | 599 | 36.9852 | 1
[9 empty] | 600 | 34.8327 | 1
[9 empty] | 601 | 37.0324 | 1
[9 empty] | 602 | 35.2705 | 1
[9 empty] | 603 | 32.2489 | 1
[9 empty] | 604 | 35.2426 | 1
[9 empty] | 605 | 33.6855 | 1
[9 empty] | 606 | 36.2973 | 1
[9 empty] | 607 | 32.0827 | 1
[9 empty] | 608 | 33.1726 | 1
[9 empty] | 609 | 33.65 | 1
[9 empty] | 610 | 38.3775 | 1
[9 empty] | 611 | 34.8775 | 1
[9 empty] | 612 | 34.5255 | 1
[9 empty] | 613 | 34.4944 | 1
[9 empty] | 614 | 33.1764 | 1
[9 empty] | 615 | 30.6611 | 1
[9 empty] | 616 | 33.9464 | 1
[9 empty] | 617 | 35.0873 | 1
[9 empty] | 618 | 33.1322 | 1
[9 empty] | 619 | 37.8512 | 1
[9 empty] | 620 | 35.445 | 1
[9 empty] | 621 | 33.3918 | 1
[9 empty] | 622 | 35.1163 | 1
[9 empty] | 623 | 35.0035 | 1
[9 empty] | 624 | 34.9802 | 1
[9 empty] | 625 | 32.8498 | 1
[9 empty] | 626 | 35.9753 | 1
[9 empty] | 627 | 35.2761 | 1
[9 empty] | 628 | 34.9912 | 1
[9 empty] | 629 | 35.019 | 1
[9 empty] | 630 | 32.6347 | 1
[9 empty] | 631 | 31.9902 | 1
[9 empty] | 632 | 36.3861 | 1
[9 empty] | 633 | 35.4563 | 1
[9 empty] | 634 | 36.7534 | 1
[9 empty] | 635 | 37.4487 | 1
[9 empty] | 636 | 33.7443 | 1
[9 empty] | 637 | 34.9333 | 1
[9 empty] | 638 | 34.874 | 1
[9 empty] | 639 | 34.9022 | 1
[9 empty] | 640 | 33.4706 | 1
[9 empty] | 641 | 35.5555 | 1
[9 empty] | 642 | 35.0629 | 1
[9 empty] | 643 | 34.3049 | 1
[9 empty] | 644 | 35.2073 | 1
[9 empty] | 645 | 35.3847 | 1
[9 empty] | 646 | 35.6448 | 1
[9 empty] | 647 | 34.7774 | 1
[9 empty] | 648 | 35.3629 | 1
[9 empty] | 649 | 35.9026 | 1
[9 empty] | 650 | 37.139 | 1
[9 empty] | 651 | 35.8583 | 1
[9 empty] | 652 | 36.4509 | 1
[9 empty] | 653 | 33.7876 | 1
[9 empty] | 654 | 32.6233 | 1
[9 empty] | 655 | 33.8743 | 1
[9 empty] | 656 | 34.2878 | 1
[9 empty] | 657 | 37.0368 | 1
[9 empty] | 658 | 35.3645 | 1
[9 empty] | 659 | 34.2896 | 1
[9 empty] | 660 | 37.0737 | 1
[9 empty] | 661 | 35.2854 | 1
[9 empty] | 662 | 37.7248 | 1
[9 empty] | 663 | 35.6017 | 1
[9 empty] | 664 | 35.8716 | 1
[9 empty] | 665 | 34.434 | 1
[9 empty] | 666 | 33.6593 | 1
[9 empty] | 667 | 34.9669 | 1
[9 empty] | 668 | 35.3083 | 1
[9 empty] | 669 | 36.302 | 1
[9 empty] | 670 | 33.0959 | 1
[9 empty] | 671 | 33.0164 | 1
[9 empty] | 672 | 34.0064 | 1
[9 empty] | 673 | 35.1311 | 1
[9 empty] | 674 | 35.7133 | 1
[9 empty] | 675 | 34.8066 | 1
[9 empty] | 676 | 36.9783 | 1
[9 empty] | 677 | 34.2255 | 1
[9 empty] | 678 | 31.5472 | 1
[9 empty] | 679 | 33.1802 | 1
[9 empty] | 680 | 34.5627 | 1
[9 empty] | 681 | 34.4218 | 1
[9 empty] | 682 | 34.4555 | 1
[9 empty] | 683 | 34.3248 | 1
[9 empty] | 684 | 34.8864 | 1
[9 empty] | 685 | 35.1564 | 1
[9 empty] | 686 | 34.0021 | 1
[9 empty] | 687 | 36.4462 | 1
[9 empty] | 688 | 35.0177 | 1
[9 empty] | 689 | 34.4033 | 1
[9 empty] | 690 | 30.5475 | 1
[9 empty] | 691 | 33.3003 | 1
[9 empty] | 692 | 33.2779 | 1
[9 empty] | 693 | 34.8807 | 1
[9 empty] | 694 | 34.0279 | 1
[9 empty] | 695 | 34.147 | 1
[9 empty] | 696 | 34.9701 | 1
[9 empty] | 697 | 35.3742 | 1
[9 empty] | 698 | 32.1519 | 1
[9 empty] | 699 | 35.2922 | 1
[9 empty] | 700 | 32.2755 | 1
[9 empty] | 701 | 33.0456 | 1
[9 empty] | 702 | 35.8419 | 1
[9 empty] | 703 | 34.6496 | 1
[9 empty] | 704 | 34.9489 | 1
[9 empty] | 705 | 32.92 | 1
[9 empty] | 706 | 34.5703 | 1
[9 empty] | 707 | 33.1761 | 1
[9 empty] | 708 | 32.9693 | 1
[9 empty] | 709 | 38.0956 | 1
[9 empty] | 710 | 33.5266 | 1
[9 empty] | 711 | 36.7603 | 1
[9 empty] | 712 | 36.2792 | 1
[9 empty] | 713 | 33.8839 | 1
[9 empty] | 714 | 34.6408 | 1
[9 empty] | 715 | 34.9636 | 1
[9 empty] | 716 | 33.4698 | 1
[9 empty] | 717 | 34.3018 | 1
[9 empty] | 718 | 34.5947 | 1
[9 empty] | 719 | 31.9508 | 1
[9 empty] | 720 | 35.2214 | 1
[9 empty] | 721 | 33.7995 | 1
[9 empty] | 722 | 34.4808 | 1
[9 empty] | 723 | 32.313 | 1
[9 empty] | 724 | 33.6449 | 1
[9 empty] | 725 | 33.2643 | 1
[9 empty] | 726 | 37.2221 | 1
[9 empty] | 727 | 36.6707 | 1
[9 empty] | 728 | 36.0505 | 1
[9 empty] | 729 | 33.8537 | 1
[9 empty] | 730 | 32.6464 | 1
[9 empty] | 731 | 30.4879 | 1
[9 empty] | 732 | 36.3732 | 1
[9 empty] | 733 | 37.0598 | 1
[9 empty] | 734 | 33.9916 | 1
[9 empty] | 735 | 37.3208 | 1
[9 empty] | 736 | 31.584 | 1
[9 empty] | 737 | 33.9508 | 1
[9 empty] | 738 | 34.296 | 1
[9 empty] | 739 | 34.5329 | 1
[9 empty] | 740 | 32.2318 | 1
[9 empty] | 741 | 34.535 | 1
[9 empty] | 742 | 34.2283 | 1
[9 empty] | 743 | 34.71 | 1
[9 empty] | 744 | 33.0271 | 1
[9 empty] | 745 | 35.1561 | 1
[9 empty] | 746 | 31.8847 | 1
[9 empty] | 747 | 32.4295 | 1
[9 empty] | 748 | 35.1032 | 1
[9 empty] | 749 | 33.8548 | 1
[9 empty] | 750 | 37.9003 | 1
[9 empty] | 751 | 36.0685 | 1
[9 empty] | 752 | 33.5637 | 1
[9 empty] | 753 | 34.1632 | 1
[9 empty] | 754 | 34.3336 | 1
[9 empty] | 755 | 30.9681 | 1
[9 empty] | 756 | 35.7242 | 1
[9 empty] | 757 | 31.6163 | 1
[9 empty] | 758 | 31.8157 | 1
[9 empty] | 759 | 36.5917 | 1
[9 empty] | 760 | 34.0826 | 1
[9 empty] | 761 | 35.3777 | 1
[9 empty] | 762 | 32.6439 | 1
[9 empty] | 763 | 34.9812 | 1
[9 empty] | 764 | 32.2969 | 1
[9 empty] | 765 | 33.7146 | 1
[9 empty] | 766 | 33.3087 | 1
[9 empty] | 767 | 33.1512 | 1
[9 empty] | 768 | 31.4144 | 1
[9 empty] | 769 | 35.399 | 1
[9 empty] | 770 | 33.3479 | 1
[9 empty] | 771 | 35.3161 | 1
[9 empty] | 772 | 35.1044 | 1
[9 empty] | 773 | 32.7093 | 1
[9 empty] | 774 | 32.5165 | 1
[9 empty] | 775 | 35.2145 | 1
[9 empty] | 776 | 34.7367 | 1
[9 empty] | 777 | 34.2156 | 1
[9 empty] | 778 | 34.7343 | 1
[9 empty] | 779 | 35.5622 | 1
[9 empty] | 780 | 35.7717 | 1
[9 empty] | 781 | 33.6859 | 1
[9 empty] | 782 | 34.8851 | 1
[9 empty] | 783 | 38.2388 | 1
[9 empty] | 784 | 34.0878 | 1
[9 empty] | 785 | 37.4842 | 1
[9 empty] | 786 | 33.3224 | 1
[9 empty] | 787 | 34.2778 | 1
[9 empty] | 788 | 35.1605 | 1
[9 empty] | 789 | 33.4039 | 1
[9 empty] | 790 | 35.8909 | 1
[9 empty] | 791 | 36.6226 | 1
[9 empty] | 792 | 32.3027 | 1
[9 empty] | 793 | 34.9601 | 1
[9 empty] | 794 | 30.5807 | 1
[9 empty] | 795 | 34.5929 | 1
[9 empty] | 796 | 38.5528 | 1
[9 empty] | 797 | 32.5184 | 1
[9 empty] | 798 | 35.0784 | 1
[9 empty] | 799 | 36.3027 | 1
[9 empty] | 800 | 34.4693 | 1
[9 empty] | 801 | 34.8323 | 1
[9 empty] | 802 | 32.9055 | 1
[9 empty] | 803 | 33.0818 | 1
[9 empty] | 804 | 34.5945 | 1
[9 empty] | 805 | 34.2182 | 1
[9 empty] | 806 | 34.7263 | 1
[9 empty] | 807 | 33.6753 | 1
[9 empty] | 808 | 32.8841 | 1
[9 empty] | 809 | 34.2835 | 1
[9 empty] | 810 | 33.6215 | 1
[9 empty] | 811 | 32.0876 | 1
[9 empty] | 812 | 33.892 | 1
[9 empty] | 813 | 33.9231 | 1
[9 empty] | 814 | 33.4948 | 1
[9 empty] | 815 | 36.6272 | 1
[9 empty] | 816 | 31.8124 | 1
[9 empty] | 817 | 34.0739 | 1
[9 empty] | 818 | 32.8355 | 1
[9 empty] | 819 | 30.482 | 1
[9 empty] | 820 | 34.2555 | 1
[9 empty] | 821 | 33.8615 | 1
[9 empty] | 822 | 33.6783 | 1
[9 empty] | 823 | 36.2802 | 1
[9 empty] | 824 | 33.1646 | 1
[9 empty] | 825 | 32.7765 | 1
[9 empty] | 826 | 33.6701 | 1
[9 empty] | 827 | 35.4637 | 1
[9 empty] | 828 | 34.7711 | 1
[9 empty] | 829 | 34.2732 | 1
[9 empty] | 830 | 32.0778 | 1
[9 empty] | 831 | 36.0535 | 1
[9 empty] | 832 | 34.9806 | 1
[9 empty] | 833 | 33.3753 | 1
[9 empty] | 834 | 32.7035 | 1
[9 empty] | 835 | 34.5328 | 1
[9 empty] | 836 | 35.0166 | 1
[9 empty] | 837 | 33.0027 | 1
[9 empty] | 838 | 32.3565 | 1
[9 empty] | 839 | 34.7241 | 1
[9 empty] | 840 | 32.8873 | 1
[9 empty] | 841 | 32.6555 | 1
[9 empty] | 842 | 33.6597 | 1
[9 empty] | 843 | 36.3824 | 1
[9 empty] | 844 | 37.3453 | 1
[9 empty] | 845 | 34.5494 | 1
[9 empty] | 846 | 36.2697 | 1
[9 empty] | 847 | 37.2979 | 1
[9 empty] | 848 | 35.8207 | 1
[9 empty] | 849 | 34.0692 | 1
[9 empty] | 850 | 33.4438 | 1
[9 empty] | 851 | 34.2381 | 1
[9 empty] | 852 | 35.6372 | 1
[9 empty] | 853 | 34.6696 | 1
[9 empty] | 854 | 35.2061 | 1
[9 empty] | 855 | 36.2397 | 1
[9 empty] | 856 | 35.8115 | 1
[9 empty] | 857 | 33.8297 | 1
[9 empty] | 858 | 34.2062 | 1
[9 empty] | 859 | 32.8361 | 1
[9 empty] | 860 | 35.7167 | 1
[9 empty] | 861 | 36.863 | 1
[9 empty] | 862 | 33.6188 | 1
[9 empty] | 863 | 36.1065 | 1
[9 empty] | 864 | 34.9729 | 1
[9 empty] | 865 | 33.4713 | 1
[9 empty] | 866 | 33.4479 | 1
[9 empty] | 867 | 32.33 | 1
[9 empty] | 868 | 36.3004 | 1
[9 empty] | 869 | 32.7025 | 1
[9 empty] | 870 | 34.1202 | 1
[9 empty] | 871 | 35.8276 | 1
[9 empty] | 872 | 35.7472 | 1
[9 empty] | 873 | 34.4481 | 1
[9 empty] | 874 | 31.1263 | 1
[9 empty] | 875 | 34.6337 | 1
[9 empty] | 876 | 33.0691 | 1
[9 empty] | 877 | 36.4961 | 1
[9 empty] | 878 | 32.4091 | 1
[9 empty] | 879 | 34.618 | 1
[9 empty] | 880 | 34.4541 | 1
[9 empty] | 881 | 33.974 | 1
[9 empty] | 882 | 35.6798 | 1
[9 empty] | 883 | 31.7547 | 1
[9 empty] | 884 | 33.3405 | 1
[9 empty] | 885 | 37.9819 | 1
[9 empty] | 886 | 34.5074 | 1
[9 empty] | 887 | 32.0097 | 1
[9 empty] | 888 | 35.1746 | 1
[9 empty] | 889 | 34.7897 | 1
[9 empty] | 890 | 36.8471 | 1
[9 empty] | 891 | 36.3082 | 1
[9 empty] | 892 | 34.7344 | 1
[9 empty] | 893 | 35.0685 | 1
[9 empty] | 894 | 34.1102 | 1
[9 empty] | 895 | 33.3907 | 1
[9 empty] | 896 | 32.4029 | 1
[9 empty] | 897 | 34.7315 | 1
[9 empty] | 898 | 36.9699 | 1
[9 empty] | 899 | 32.9385 | 1
[9 empty] | 900 | 36.6134 | 1
[9 empty] | 901 | 32.5163 | 1
[9 empty] | 902 | 34.5702 | 1
[9 empty] | 903 | 32.3657 | 1
[9 empty] | 904 | 33.3577 | 1
[9 empty] | 905 | 32.5882 | 1
[9 empty] | 906 | 33.898 | 1
[9 empty] | 907 | 34.4107 | 1
[9 empty] | 908 | 34.6337 | 1
[9 empty] | 909 | 35.4371 | 1
[9 empty] | 910 | 32.9537 | 1
[9 empty] | 911 | 34.9073 | 1
[9 empty] | 912 | 38.7357 | 1
[9 empty] | 913 | 35.1697 | 1
[9 empty] | 914 | 37.6224 | 1
[9 empty] | 915 | 33.318 | 1
[9 empty] | 916 | 34.7334 | 1
[9 empty] | 917 | 32.6996 | 1
[9 empty] | 918 | 33.3462 | 1
[9 empty] | 919 | 35.6852 | 1
[9 empty] | 920 | 32.805 | 1
[9 empty] | 921 | 35.1856 | 1
[9 empty] | 922 | 33.1457 | 1
[9 empty] | 923 | 34.0662 | 1
[9 empty] | 924 | 36.1328 | 1
[9 empty] | 925 | 31.9244 | 1
[9 empty] | 926 | 33.1342 | 1
[9 empty] | 927 | 35.0185 | 1
[9 empty] | 928 | 34.6432 | 1
[9 empty] | 929 | 38.4464 | 1
[9 empty] | 930 | 32.2197 | 1
[9 empty] | 931 | 33.4107 | 1
[9 empty] | 932 | 35.9093 | 1
[9 empty] | 933 | 31.6749 | 1
[9 empty] | 934 | 31.9594 | 1
[9 empty] | 935 | 35.6374 | 1
[9 empty] | 936 | 36.4162 | 1
[9 empty] | 937 | 34.869 | 1
[9 empty] | 938 | 31.8565 | 1
[9 empty] | 939 | 36.5557 | 1
[9 empty] | 940 | 36.0191 | 1
[9 empty] | 941 | 34.5852 | 1
[9 empty] | 942 | 32.8825 | 1
[9 empty] | 943 | 35.1208 | 1
[9 empty] | 944 | 35.7079 | 1
[9 empty] | 945 | 31.5373 | 1
[9 empty] | 946 | 35.2295 | 1
[9 empty] | 947 | 36.3763 | 1
[9 empty] | 948 | 35.1963 | 1
[9 empty] | 949 | 34.3296 | 1
[9 empty] | 950 | 34.8565 | 1
[9 empty] | 951 | 34.1902 | 1
[9 empty] | 952 | 35.8351 | 1
[9 empty] | 953 | 35.2695 | 1
[9 empty] | 954 | 34.0858 | 1
[9 empty] | 955 | 36.1002 | 1
[9 empty] | 956 | 34.6685 | 1
[9 empty] | 957 | 33.9632 | 1
[9 empty] | 958 | 32.4699 | 1
[9 empty] | 959 | 32.6846 | 1
[9 empty] | 960 | 32.2248 | 1
[9 empty] | 961 | 34.7168 | 1
[9 empty] | 962 | 31.7542 | 1
[9 empty] | 963 | 36.5701 | 1
[9 empty] | 964 | 36.0392 | 1
[9 empty] | 965 | 36.1931 | 1
[9 empty] | 966 | 36.1046 | 1
[9 empty] | 967 | 35.3868 | 1
[9 empty] | 968 | 36.1881 | 1
[9 empty] | 969 | 35.8977 | 1
[9 empty] | 970 | 33.4125 | 1
[9 empty] | 971 | 35.4797 | 1
[9 empty] | 972 | 32.6331 | 1
[9 empty] | 973 | 35.8771 | 1
[9 empty] | 974 | 35.0663 | 1
[9 empty] | 975 | 33.4042 | 1
[9 empty] | 976 | 33.5411 | 1
[9 empty] | 977 | 34.8904 | 1
[9 empty] | 978 | 34.2398 | 1
[9 empty] | 979 | 34.6463 | 1
[9 empty] | 980 | 31.0179 | 1
[9 empty] | 981 | 36.1022 | 1
[9 empty] | 982 | 33.4652 | 1
[9 empty] | 983 | 35.5269 | 1
[9 empty] | 984 | 37.0515 | 1
[9 empty] | 985 | 33.9793 | 1
[9 empty] | 986 | 33.6051 | 1
[9 empty] | 987 | 33.7053 | 1
[9 empty] | 988 | 34.7431 | 1
[9 empty] | 989 | 33.521 | 1
[9 empty] | 990 | 35.2351 | 1
[9 empty] | 991 | 34.489 | 1
[9 empty] | 992 | 32.9001 | 1
[9 empty] | 993 | 32.9988 | 1
[9 empty] | 994 | 34.8136 | 1
[9 empty] | 995 | 34.6739 | 1
[9 empty] | 996 | 36.2438 | 1
[9 empty] | 997 | 32.8575 | 1
[9 empty] | 998 | 34.301 | 1
[9 empty] | 999 | 34.1337 | 1
[9 empty] | 1000 | 32.6896 | 1

## Instructions
Instructions
1. This file is set up to simulate project completion times using triangular distributions.
2. Use Excel formulas in new columns to simulate durations for each task based on (a, b, m) values provided.
3. For regular triangular distribution, use the formula:
=IF(RAND() < (m - a) / (b - a), a + SQRT(RAND() * (b - a) * (m - a)), b - SQRT((1 - RAND()) * (b - a) * (b - m)))
4. For 1000 simulations, copy the formulas across 1000 rows.
5. Calculate total duration per project by summing task durations, ensuring dependencies are respected.
6. Check if each simulation's total duration meets project deadlines (32 days for Project 1, 48 for Project 2)
7. Calculate success rate by averaging the successful trials.
8. Average project duration can be calculated using =AVERAGE() over the total duration for all trials.